## MUNICIPALITY DETAILS
City | Utility Info: | PERMITTING NOTES:
Bloomington | Shape files built into CAD template | Per Ted w/ GP - will be the most difficult City to get permits from & regardless of how thorough permit & CAD is, it will be rejected w/ lots of redlines from the City, so suggested to permit asap, correct from redlines & resubmit for fastest approval. 11/27 - request that Tom go into the City of Bloomington to have a conversation to get POC and info for permitting, specs, etc. 11/30 - Tom spoke to City Engineer, Eric via phone call and said design option 2 okay, road crossings must be perpendicular not diagonal & permits accepted in 1/2 (2640') mile sections
Eagan | None provided, city okay without lines | Accept general TCP’s unless we need to do a full road closure or some sort of detour plan. They do not require us to show existing facilities on the construction prints, but they said if we have the information it is helpful to have when they are reviewing our permit request. Point of Contact: Dave Westermayer DWestermayer@cityofeagan.com 651-675-5641. They use the same permit portal as City of Apple Valley.
Eden Prairie | Shape files built into CAD template | For larger projects they will require a field meeting before submitting. Meeting with the utility owner before placing in the city is required. Can provide utility maps
Burnsville | Web viewer provided | City of Burnsville has maps or has a mapping GIS system.
Savage |  | Per city engineer John Wichman: 2 other utility companies expanding their fiber network in our city currently and it’s gotten really messy. Their contractors/sub contractors and not doing good with restoration. Noone is contacting the property owners and the city is getting a lot of complaints. They may start to require all permits to be signed off by the property owners. They are going to start limiting the size of the projects to a “cabinet site” and only being able to do one cabinet site at a time. Permit fee is $200, but also there will be licensing, insurance, registration and escrow fee’s that may cost anywhere from $30,000-$50,000
Shakopee |  | City of Shakopee maps public utilities such as sanitary, storm and water but do not have maps of other small utilities. We will have to have those located via a locate ticket
Apple Valley | 1/3 of Shape files built into CAD template, remaining 2/3 sent by AV
Farmington | CAD will show visible utilities from FN and Street view, none provided by city
Lakeville | Web viewer provided
Minnetonka
Chanhassan
Chaska
Prior Lake
Rosemount

## MISC NOTES
Fielding Team
Name | Role | Phone # | Email | Start Date | Last Date | OOO | OOO | OOO | OOO | OOO | Count
Junior Rogers | Project Manager | [9 empty] | 0
Jaeger Kahn | Fielder | 612-236-3067 | jkahn@mountainltd.com | 2023-12-11 |  | 3/14 - 3/21 |  |  |  |  | 1
Samuel Jackson | Fielder | 801-680-9691 | sjackson@mountainltd.com | 2024-01-19 |  | 2/16 - 2/19 |  |  |  |  | 2
Hunter Lee | Fielder | 651-398-7178 | hlee@mountainltd.com | 2024-03-08 | [6 empty] | 3
Joshua Dahlen | Fielder - OUT OF TOWN UNTIL 9/27, send assignment then | 612-272-0277 | jdahlen@mountainltd.com | 2024-03-25 | [6 empty] | 5
Cody Lee | Fielder | 612-387-0718 | cslee@mountainltd.com | 2024-03-25 | [6 empty] | 6
Hannah Edwards | Fielder | 952-465-8151 | hedwards@mountainltd.com | 2024-04-15 | [6 empty] | 7
Jacob Messer | Fielder | 650-504-8098 | jacobpmesser@gmail.com | 2024-03-26 | [6 empty] | 9
Erik Ferguson | Fielder | 480-236-5410 | erikferguson671@gmail.com | 2024-03-30 | [6 empty] | 10
Brian McCombs (PT) | Fielder | 303-868-2083 | bmccombs@mountainltd.com | 2024-04-03 | [6 empty] | 8
Drew (Andrew) Krejci (PT) | Fielder | 720-209-0096 | akrejci@mountainltd.com | 2024-03-19 |  | 3/23 - 3/25 | 4/1 -4/7 |  |  |  | 4
David 'Chris' Duncan
Scott Meissner (PT) | 307-699-2118 | smeissner@mountainltd.com | 2023-11-07 | 2024-04-01 | 11/24 - 12/14 | 12/22 - 1/7 | 1/15 - 2/3 | 2/12 - 2/27 | 3/4 - 3/25? | 4/1 Not coming back due to new unit rate
Jeff Jorgensen | 208-571-0402 | jjorgensen@mountainltd.com | 2023-11-27 | 2024-01-07 | 12/16 - 1/1
Tom Rathman | 612-388-3228 | trathman@usfamily.net | 2023-11-13 | 2023-12-13
HLD Planners - Reporting to Mark Hatfield - GP-105495 |  | Email
Darlene White |  | dwhite@mountaintld.com | 2023-10-09
Eric Lynn |  | elynn@lmountainltd.com |  | 2024-03-01
Tammi Baker |  | tbaker@mountainltd.com |  | 2024-02-23
Carla Jeffers |  | cjeffers@mountainltd.com |  | 2024-02-23
Joseph Smith |  | jsmith@mountainltd.com |  | 2024-02-09
Aubre Thompson | 801-577-6324 | athompson@mountainltd.com
Merylene Hickman |  | mhickman@mountainltd.com |  | 2024-02-09
LAYOUT TEAM - Allow 80 hours for layout per PSA |  | Email
Henry Brown | Project Manager | hbrown@mountainltd.com |  | 1
Curtis Adams | GPON Designer - QC, Special Projects | cadams@mountainltd.com |  | 2
James Frank | GPON Designer - QC | jfrank@mountainltd.com |  | 3
Nicole Stricklan | GPON Designer | nstricklan@mountainltd.com |  | 4
Juston Nichols | GPON Designer | jnichols@mountainltd.com |  | 5
Holly Withrow | GPON Designer | hwithrow@mountainltd.com |  | 6
Bradley Scott | GPON Designer | bscott@mountainltd.com |  | 7
Joseph Dinnison | GPON Designer | jdinnison@mountainltd.com |  | 8
Kaitlyn Matyuch | GPON Designer | kmatyuch@mountainltd.com |  | 9
Sean Hendrickson | GPON Designer | shendrickson@mountainltd.com |  | 10
Leonardo Ramirez Martinez | GPON Designer | lmartinez@mountainltd.com |  | 11
Nathan Schneider-Ortiz | GPON Designer | nortiz@mountainltd.com |  | 12
CAD TEAM
Name | Role | Office | Email | Count
Michael Johnson | Project Manager | Office, ME | mjohnson@mountainltd.com | 1
Reese Preston | Team Lead | Remote, VA | rpreston@mountainltd.com | 2
Matt Kenison | Drafter | Office, ME | mkenison@mountainltd.com | 3
Daniel Fransiscus | Drafter | Office, ME | dfransiscus@mountainltd.com | 4
Tyler Crepeau | Team Lead | Office, ME | tcrepeau@mountainltd.com | 5
Jacob Collette | Drafter | Office, ME | jcollette@mountainltd.com | 6
Megan Mathison | Drafter | Remote, WA | mmathison@mountainltd.com | 7
Jeff Norris | Team Lead | Remote, GA | jnorris@mountainltd.com | 8
Brian Terranova | Drafter | Remote, FL | bterranova@mountainltd.com | 9
Tinaca Hill | Drafter | Office, AZ | thill@mountainltd.com | 10
Kaitlyn Webb | Drafter | Office, ME | kwebb@mountainltd.com | 11
Lucia Fulwood | Project Manager | Remote, NC | lfulwood@mountainltd.com | 1
Joshua Cherry | Team Lead | Remote, IN | jcherry@mountainltd.com | 2
Laquane Lewis | Drafter | Remote, FL | llewis@mountainltd.com | 3
Julio Mendoza | Sr. Drafter | Remote, CA | jmendoza@mountainltd.com | 4
Marina Zorina | Sr. Drafter | Remote, TX | mzorina@mountainltd.com | 5
IQGEO TEAM
Name | Role | Office | Email | Count
Chris Bettencourt | Project Manager | Remote, WA | cbettencourt@mountainltd.com | 1
Cheryl Turk | PSA Designer | Remote, CO | cturk@mountainltd.com | 2
James Lugo | PSA Designer - Prefield Layout | Remote, FL | jlugo@mountainltd.com | 3
Jordan Struck | PSA Designer | Remote, ID | jstruck@mountainltd.com | 4
Eric Lynn | PSA Designer - Planner | Remote, ID | elynn@mountainltd.com | 5
Jermaine Scott | PSA Designer | Remote, GA | jscott@mountainltd.com | 6
Spencer Lynn | PSA Designer | Remote, ID | slynn@mountainltd.com | 7
Timothy Miller | PSA Designer | Remote, TX | tmiller@mountainltd.com | 8
Yuliet Munoz | PSA Designer | Remote, FL | ymunoz@mountainltd.com | 9
Elizabeth Heinl | PSA Designer - Part Time | Remote, WA | eheinl@mountainltd.com | 10
Joseph Smith | BBF Designer - Planner | Remote, ID | jsmith@mountainltd.com | 11
PERMITTING MANAGERS
Kaylie Aldous | 208-576-4008 | kaldous@mountainltd.com
Erica Bailiff | 208-576-4031 | ebailiff@mountainltd.com
build order of priority | POP ADDRESS | POP CILLI | BUILD PRIORITY
BLOOMINGTON | 510 Hasley Ln, Bloomington, MN | BLTNMNAT | 1
EAGAN (Databank) | 3255 Neil Armstrong Blvd, Eagan, MN | EAGNMN82 | 2
EDEN PRAIRIE | 6875 Shady Oak Road, Eden Prairie, MN | EDPRMNPL | 3
SHAKOPEE | Cystera, 4450 Dean Lakes Blvd | REMOTE OLT - need feeder from Eagan Databank
APPLE VALLEY | PENDING |  | 4
ROSEMOUNT | PENDING |  | 5
BURNSVILLE | 15501 Lac Lavon Dr, Burnsville, MN | BRVLMNYF | LAC LAVON FIELD PARK (LAC LAVON DR & 160TH ST)
FARMINGTON
LAKEVILLE
SAVAGE

## Don's Pivot
PROJECT STATUS | (All)
PERMIT EXECUTED (A) | (blank)
Row Labels | Sum of PATH FOOTAGE
2024-03-19 | 3408
2024-03-21 | 7638
2024-03-25 | 22977
2024-04-01 | 28826
2024-04-05 | 40275
2024-04-08 | 2797
2024-04-17 | 57844
2024-04-18 | 30669
2024-04-22 | 52909
2024-04-26 | 40605
2024-04-29 | 60405
2024-05-01 | 27396 |  | Fielded | Permit (Sub) | Permit (App) |  | Fielded | Permit (Sub) | Permit (App)
2024-05-08 | 12765 | Bloomington | 1714546 | 1020814 | 677814 | Bloomington | 324.7246 | 193.336 | 128.3739
2024-05-10 | 17418 | Eagan | 1376312 | 689125 | 203651 | Eagan | 260.6652 | 130.5161 | 38.5703
2024-05-17 | 19418 | Eden Prairie | 1368145 | 111695 | 8605 | Eden Prairie | 259.1184 | 21.1544 | 1.6297
2024-05-20 | 4106 | Burnsville | 722065 |  |  | Burnsville | 136.7547 | 0 | 0
2024-05-22 | 7102 | Total | 5181068 | 1821634 | 890070 | Total | 981.2629 | 345.0064 | 168.5739
2024-05-23 | 50860
2024-05-29 | 34499
2024-05-30 | 20998
2024-05-31 | 12982
2024-06-04 | 61894
2024-06-07 | 57015
2024-06-11 | 20376
2024-06-13 | 6695
2024-06-19 | 20867
2024-06-25 | 45098
2024-06-26 | 16583
2024-07-01
2024-07-02 | 33648
2024-07-05 | 43638
2024-07-08 | 9853
2024-07-09 | 72989
2024-07-10 | 6171
2024-07-18 | 41578
2024-07-19 | 44987
2024-07-31 | 17044
2024-08-01 | 76250
2024-08-02 | 41493
2024-08-08
2024-08-28
2024-09-06
Grand Total | 1172076

## ACTIVE BUILD AREAS
ST JOB NUMBER | GIGAPOWER PRIORITY | PROJECT STATUS | PERMIT FORECAST MONTH | CONST FORECAST MONTH | PROJECT TYPE | LU TYPE | NAME | CLLI | ROUTE | BBF & SECTION | CITY | LU FORECAST | LU ACTUAL | LU Asbuilt | PLANNER | SPLIT RATIO | PLANNING COMPLETE | HLD DESIGNER | HLD COMPLETE | FIELDING SURVEY EX COMP. START | FIELDING SURVEY EX COMP. COMPLETE | PREFIELD LAYOUT COMPLETE | FIELDER | FIELDING START | FIELDING COMPLETE ECD | FIELDING COMPLETE | SITE DETAIL PROVIDED | FIELDED BBF FOOTAGE | FIELDED F1 FOOTAGE | FIELDED F2 FOOTAGE | COMBINED F1/F2 FOOTAGE | FOOTAGE TO LU RATIO | LAYOUT ASSIGNED | LAYOUT DUE DATE (FACTOR 80 HRS) | LAYOUT COMP | LAYOUT REVISION REQUESTED | LAYOUT REVISION COMPLETE | FDH SIZE | FDH ADDRESS | LAYOUT MARKUP COMPLETE | CAD PERMIT ASSIGNED | CAD DD | CAD COMPLETE | CAD REVISION REQUESTED | CAD REVISION COMPLETE | LATEST VERSION FILE NAME | PATH FOOTAGE | DESIGNER | DESIGN ASSIGNED | DESIGN DD (Factor 40-80 hrs) | DESIGN COMPLETE | DESIGN REVISION REQUESTED | DESIGN REVISION COMPLETE | VITRUVI UPLOAD | F1 FIBER TRACE REPORT | FINAL CAD REVIEW COMPLETE & SENT TO PERMITTING | PERMIT SUBMITTAL COMPLETE (A) | HOW MANY PERMITS IN PSA APPROVED | PERMIT EXECUTED (A) | Construction Status | Handoff to Construction | Construction Start (F) | Construction Start (A) | Placing Asbuilt Received | Splicing Asbuilt Received | Asbuilt Assigned | Asbuilt Complete (F) | Notification of PSA Launch | Designer Asbuilt Deliverables Uploaded | NOTES | GP JOB NUMBER (CM PROJECT TRACKING #) | GP PROJECT NUMBER | HLD MS 0 BUDGET SUBMISSION | HLD MS 0 APPROVAL | HLD MS1 SUBMISSION | HLD MS1 APPROVAL | MS2 SUBMISSION | MS2 APPROVAL | MS3 SUBMISSION | MS3 APPROVAL | MS4 SUBMISSION | MS4 APPROVAL | GP Billing Notes | SORT ID | M/S Billed to ITG | Fld Cmp YR | Fld Cmp Mo | Fld Cmp Wk | Job Status | Complete Month
ITG-121826 | 1 | Active | Feb | Jul | BBF | NA | BBF-AT101-RT1-SEC1-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 1 | Bloomington | 1611 | 1508 |  | Joseph Smith |  | 2024-03-25 | Joseph Smith | 2023-12-01 |  |  | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-02-01 | 2024-02-15 | 2024-02-14 | 2024-07-17 | 2024-07-18 | 2024-07-18 | 6869 | Joseph Smith | 2024-05-06 | 2024-05-07 | 2024-05-07 | 2024-07-24 | 2024-08-29 |  |  |  | 2024-02-19 | 3 | 2024-03-06 | In Construction | 2024-03-18 |  | 2024-03-18 | [6 empty] | 9/23 PATH CREATION FOOTAGE = 4,891'. /11 ZAK-job complete 8/16 REVISION HOLDING FOR RESPONSE ON FIBER CABLE CHANGE OUT OF CO FROM 864F TO 288F. 7/24 sent for revisions to CAD7/8 - REVISIONS MADE NEW PATH CREATION FOOTAGE = 6,869'. 5/7 BBF Rt1 Sec 1 published in IQGEO; Path Creation footage = 6,830'. 4/8 Pending Gigapower decision on BBF-currently structure and fiber built separately. 3/5 - BBF structure complete; 3/25 - BBF COMPLETE; 1/11/24 - RXR 854432H CAD DRAWING COMPLETE | ATT-7425 | MIN001.G0000002 | 2024-05-07 | 2024-05-07 | 2024-05-16 | 2024-05-17 | 2024-09-23 | 2024-09-25 |  |  |  |  | Per Ted - For MS3, 4, & 5 Budget sheet will need to reflect the installed footage of about 5300' | 1 | 1 | #VALUE! | #VALUE! | #VALUE! | Permit Complete | 2024-05-24
ITG-110414 | 1 | Active | Feb | Jul | PSA | MIX | PSA-1101PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 1 | Bloomington | 513 | 436 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-08 | SCOTT | 2023-11-10 |  | 2023-11-13 | NO | 3716 | 2326 | 11734 | 14060 | 27.4074 | 2023-12-08 | 2024-01-12 | 2024-01-16 |  |  | 864 | PFP 510 HALSEY LN |  | 2024-01-16 | 2024-01-30 | 2024-04-08 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 8954 | Cheryl Turk (hrly) | 2024-01-16 | 2024-01-30 | 2024-03-26 |  | 2024-07-05 | 2024-07-05 |  | 2024-02-07 | 2024-02-12 | 8 | HH:1-11-24/ CITY: 3/11/24 | In Construction | 2024-04-17 |  | 2024-04-22 | 2024-07-26 | [5 empty] | 8/28 City approved final CAD, forwarded to const.7/26 Final Asbuilt to CAD & IQGEO 7/23 updated running line on sheet 11 & BBF for City per D. Rudy 4/11/24 Handoff to construction 4/17/24 Revision to construction BBF overlap 3/22 - FDH location is good; 3/14/2024 - COMPLETE - MST ERRORS (3) + SERVICE INTEGRATION; 3/11/24 - Pending RR approvals. | ATT-7819 | MIN001.G0000123 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-04-09 | 2024-06-26 | 2024-06-26 | 2024-07-30 |  |  |  | 7/30 MS3 Approval pending verification of completed air gaps | 2 | 1 & 2 | 2023 | 11 | 46 | Permit Complete | 2024-06-28
ITG-110112 | 1 | Active | Feb | Aug | PSA | SFU | PSA-1102PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 1 | Bloomington | 446 | 441 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-02 | SCOTT | 2023-11-03 |  | 2023-11-12 | YES | 0 | 3642 | 42669 | 46311 | 103.8363 | 2023-12-07 | 2023-12-28 | 2024-01-08 |  |  | 864 | PFP 1200 W 89TH ST |  | 2024-01-08 | 2024-01-23 | 2024-03-14 | 2024-07-26 | 2024-08-12 | 2024-08-12 | 36546 | Cheryl Turk (hrly) | 2024-01-08 | 2024-01-23 | 2024-03-26 |  | 2024-07-05 | 2024-07-05 |  | 2024-02-01 | 2024-02-06 | 17 | 2024-02-14 | In Construction | 2024-03-18 |  | 2024-03-18 | 2024-07-26 | [5 empty] | 1/30 - PENDING MST ERRORS; 3/13 FDH location was moved per DH. 2/16 - MST ERROR FIX NOT RESOLVED; 1/30 - PENDING ERRORS ESC. TO IQGEO SUPPORT - "FIX" TO BE COMPLETE NIGHT OF 2/15 & RESOLVED 2/16; 12/20 - Provided updated field notes to layout team from Scott with additional fielding details; 12/12 - Put on hold pending additional fielding details | ATT-7427 | MIN001.G0000003 | 2024-03-06 | 2024-03-21 | 2024-03-22 | 2024-04-04 | 2024-05-06 | 2024-05-07 | 2024-07-30 |  |  |  | 7/30 MS3 Approval pending verification of completed air gaps | 3 | 1 & 2 | 2023 | 11 | 46 | Permit Complete | 2024-06-28
ITG-110773 | 1 | Active | Mar | Aug | PSA | SFU | PSA-1103PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 1 | Bloomington | 533 | 528 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-02 | JAEGER | 2023-12-14 |  | 2023-12-26 | YES | 2550 | 2367 | 28896 | 31263 | 58.6548 | 2023-12-28 | 2024-01-08 | 2024-01-08 |  |  | 864 | PFP 8236 EMERSON AVE S |  | 2024-01-08 | 2024-01-17 | 2024-02-15 | 2024-08-06 | 2024-08-12 | 2024-08-07 | 30142 | Christian Weller (hrly) | 2024-01-08 | 2024-01-19 | 2024-03-28 |  | 2024-07-05 | 2024-07-05 |  | 2024-02-05 | 2024-03-20 | 16 | 2024-05-21 | In Construction | 2024-03-18 |  | 2024-03-18 | 2024-07-26 | [5 empty] | 8/5 Dan sent additional asbuilt info, forwarded to Michael. Published in IQGEO 3/22 *NEED TO SEND THIS OUT* FDH location is good, was moved out of intersection. 3/15/2024 - design complete pending BBF & service integration errors; 2/27 - Received MNDOT CAD; FOSCs updated; 2/22 - Need to update FOSCs; 12/21 - Per Jaeger, Vocomm International has new fiber HH at & slack loops on poles starting Lyndale & 82nd - will get build out percentage | ATT-7820 | MIN001.G0000124 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-04-09 | 2024-05-06 | 2024-05-07 | 2024-07-30 |  |  |  | 7/30 MS3 Approval pending verification of completed air gaps | 4 | 1 & 2 | 2023 | 12 | 52 | Permit Complete | 2024-07-19
ITG-110774 | 3 | NO BUILD |  |  | PSA | BCL/MDU | PSA-1104PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 1 | Bloomington | 99 | 92 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-15 | JAEGER | 2024-01-10 |  | 2024-01-23 | YES | 0 | 1736 | 7435 | 9171 | 92.6364 | 2024-03-11 | 2024-03-26 | 2024-03-29 |  |  | 288 | PFP 1114 AMERICAN BLVD W | [7 empty] | 6079 | James Lugo | 2024-05-14 | 2024-05-28 | 2024-05-14 | [18 empty] | 5/28 Per email from Ted-Heavy hardscape 4/3 - PER ANGELA PAUSE ON BUILD; 3/29 - MOVE FORECAST MONTHS OUT FROM MAY & JUL TO JUN & AUG; 3/14 - MOVE FORECAST MONTHS OUT FROM APR & JUN TO MAY & JUL; 12/15 - Scott sent revised F1 field notes w/ additional BBF details; 12/11 - Sent to Scott to capture 2 more sections of BBF that need fielded | ATT-7821 | MIN001.G0000125 | 2024-03-20 | 2024-03-28 | 2024-05-29 | 2024-05-29 | 2024-06-03 | 2024-06-04 | Stop | Stop | Stop | Stop |  | 5 | 1 & 2 | 2024 | 1 | 4 | #REF! | 2028-06-13
ITG-110712 | 3 | NO BUILD |  |  | PSA | BCL | PSA-1105PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 1 | Bloomington | 20 | 11 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-15 | SCOTT | 2023-11-13 |  | 2023-11-14 | YES | 1476 | 1814 | 13024 | 14838 | 741.9 | 2024-03-11 | 2024-03-26 | 2024-03-29 |  |  | 288 | PFP 351 AMERICAN BLVD W |  | 2024-04-01 | 2024-04-15 | 2024-04-17 |  |  | [4-10-24] V2 | 3859 | Jermaine Scott | 2024-05-14 | 2024-05-21 | 2024-05-16 |  |  |  |  | 2024-05-17 | [13 empty] | 5/28 Per email from Ted-Heavy hardscape5/24 Pending Ted's const. approval befor moving forward w/MNDOT CAD and permitting.4/3 - PER ANGELA PAUSE ON BUILD; 3/29 - MOVE FORECAST MONTHS OUT FROM MAY & JUL TO JUN & AUG; 3/14 - MOVE FORECAST MONTHS OUT FROM APR & JUN TO MAY & JUL; 12/15 - Scott sent revised F1 field notes w/ additional BBF details; 12/11 - Sent to Scott to capture 2 more sections of BBF that need fielded | ATT-7822 | MIN001.G0000126 | 2024-03-20 | 2024-04-16 | 2024-05-29 | 2024-05-29 | 2024-06-03 | 2024-06-04 | Stop | Stop | Stop | Stop |  | 6 | 1 & 2 | 2023 | 11 | 46 | #REF! | 2028-06-13
ITG-122495 | 1 | Active | Mar | Aug | BBF | NA | BBF-AT101-RT1-SEC3-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 3 | Bloomington | 2878 | 2865 |  | Joseph Smith |  | 2024-03-28 | Joseph Smith | 2023-12-01 |  |  | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-02-06 | 2024-02-21 | 2024-04-16 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 9134 | Joseph Smith | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-08-02 | 2024-08-29 |  |  | 2024-07-31 | 2024-03-13 | 6 | 2024-05-07 | In Construction | 2024-05-08 |  | InProgress | [6 empty] | 9/11 Zak-Partially complete. East side in path creation8/27 REVISIONS COMPLETED FROM CITY REQUEST, NEW PATH CREATION FOOTAGE = 9,134' . HOLDING ON GP FOR SPLICING.8/16 REVISON HOLDING FOR RESPONSE ON CO FIBER CABLE CHANGE8/6 CAD revision sent to Michael.7/31 Nate: Revision request look good, Michael sent back to permitting today. 7/31 Nate reviewed city request. Nate 7/23 CAD revison requested on 7/22 by permitting for city request waiting on CAD revison.7/9 REVISION COMPLETED NEW PATH CREATION FOOTAGE = 9,084'. 5/13 Revised version for permitting issued-under S/W to bypass poles, sent rev. to const. 5/7 BBF Rt1 Sec 3 published in IQGEO; Path Creation footage = 9,179'. | ATT-7894 | MIN001.G0000177 | 2024-05-08 | 2024-05-08 | 2024-05-09 | 2024-05-09 | 2024-07-23 | 2024-07-24 | See notes |  |  |  | Capture New path creation footage = 9,134 in MS3 budget sheet | 7 | 1 & 2 | #VALUE! | #VALUE! | #VALUE! | Permit Complete | 2024-06-14
ITG-109891 | 1 | Active | Mar | Aug | PSA | SFU | PSA-1301PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 3 | Bloomington | 226 | 225 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-08 | SCOTT | 2023-11-08 |  | 2023-11-12 | YES | 1786 | 3985 | 32461 | 36446 | 161.2655 | 2024-01-03 | 2024-01-15 | 2024-01-29 | 2024-08-15 | 2024-08-22 | 432 | (PFP 8745 1ST AVE S) PFP 8800 1ST AVE S |  | 2024-01-29 | 2024-02-15 | 2024-04-22 | 2024-08-27 | 2024-08-28 | 2024-08-28 | 18833 | Cheryl Turk (hrly) | 2024-01-29 | 2024-02-13 | 2024-03-29 | 2024-08-09 | 2024-08-30 |  |  | 2024-08-09 | 2024-03-13 | 11 | 2024-03-25 | In Construction | 2024-08-09 |  | 2024-08-27 | 2024-08-27 | [5 empty] | 8/27 sent asbuilt to CAD due 9/4. 8/9 Sent Kaylie to amend permit and sent to Dan for const. 8/6 CAD revisions requested due end of week addressing overlap w/1306 4/12 Revisions from Henry, emailed Cheryl w/rush**RUSH on re-design, ITG wants to start soon**4/8 FDH needs to be relocated out of intersection to 8800 1st Ave S. sent out to the team. 2/16 - Design started; 12/30 - Scott sent revised F2 field notes w/ LU assignments; 12/15 - Scott sent revised F1 field notes w/ additional BBF details; 12/11 - Sent to Scott to capture 2 more sections of BBF that need fielded | ATT-7824 | MIN001.G0000128 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-04-09 | 2024-05-06 | 2024-05-07 | 2024-08-28 |  |  |  |  | 8 | 1 & 2 | 2023 | 11 | 46 | Permit Complete | 2024-06-28
ITG-110113 | 1 | Active | Mar | Sep | PSA | SFU/MDU | PSA-1302PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 3 | Bloomington | 621 | 564 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-15 | SCOTT | 2023-11-15 |  | 2023-11-21 | YES | 3360 | 122 | 53517 | 53639 | 86.3752 | 2024-01-04 | 2024-01-31 | 2024-03-12 |  |  | 864 | PFP 8600 4TH AVE S |  | 3/18/2024 | 2024-04-29 | 2024-07-03 | 2024-09-06 | 2024-09-06 | 9/6v3 | 48039 | Cheryl Turk | 2024-02-06 | 2024-03-04 | 2023-03-21 | 2024-08-09 | 2024-09-20 |  |  | 2024-08-13 | 2024-03-14 | 24 | 2024-07-10 | In Construction | 2024-08-13 | [8 empty] | 9/6 To CAD for missing 2" at 84th & Portland. 8/13 CAD approved forwarded to expedite permit amendment.8/13 sent back with missed CAD corrections 8/6 CAD revision requested addresses overlap w/1306 7/10 permit approved by city 3/21 - PENDING BBF JOB 3/22 FDH location looks good. 2/22 - Moved design due date from 3/1; 12/19 - Sent Scott request to update F2 field notes w/ CL/LU addresses assigned to MSTs, correcitons & adding fiber running line, etc; 12/15 - Scott sent revised F1 field notes w/ additional BBF details; 12/11 - Sent to Scott to capture 2 more sections of BBF that need fielded CAD - Base Map assigned to Thomas Benedict 12/14, Due 12/21 | ATT-7825 | MIN001.G0000129 | 2024-03-20 | 2024-03-21 | 2024-04-04 | 2024-04-09 | 2024-07-24 | 2024-07-24 | [5 empty] | 9 | 1 & 2 | 2023 | 11 | 47 | Permit Complete | 2024-07-19
ITG-110775 | 1 | Active | Feb | Sep | PSA | SFU | PSA-1303PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 3 | Bloomington | 400 | 399 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-15 | SCOTT | 2023-11-16 |  | 2023-12-17 | YES | 3359 | 1420 | 43104 | 44524 | 111.31 | 2023-12-17 | 2023-12-26 | 2023-12-29 |  |  | 576 | PFP 1126 E 88TH ST |  | 2023-12-29 | 2024-01-12 | 2024-04-16 | 2024-08-13 | 2024-08-15 | 2024-08-14 | 38371 | Jordan (Christian) | 2023-12-29 | 2024-01-19 | 2024-04-05 | 2024-08-16 | 2024-08-21 |  |  | 2024-01-23 | 2024-01-30 | 19 | 2024-02-08 | In Construction | 2024-04-24 |  | 2024-04-22 | [6 empty] | 8/13 Nate sent back to CAD for revisons to bring to current standards. 4/12 Michael to have BBF Sec 3 and PSA job corrected by 4/16 for overlap/duplication issues. 3/22 FDH location is good. 3/7 - FIBER TRACE REPORT FIXED W/ CHANGING FROM 2K' CONDUIT SECTIONS; 2/29 - FOCS & FRC codes updated; 2/22 - FIBER TRACE ISSUES; 2/13 - IQGEO team fixed zip code issue on 250 LUs; 2/2 - IQGEO Zip Code Errors; 12/15 - Scott sent revised F1 field notes w/ additional BBF details; 12/11 - Sent to Scott to capture 2 more sections of BBF that need fielded | ATT-7826 | MIN001.G0000130 | 2024-03-20 | 2024-03-21 | 2024-04-04 | 2024-04-09 | 2024-05-07 | 2024-05-07 | [5 empty] | 10 | 1 & 2 | 2023 | 12 | 51 | Permit Complete | 2024-06-28
ITG-112372 | 1 | Active | Apr | Oct | PSA | SFU | PSA-1304PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 3 | Bloomington | 585 | 595 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-15 | JEFF | 2023-11-28 |  | 2024-01-21 | YES | 0 | 1400 | 51403 | 52803 | 90.2615 | 2024-01-25 | 2024-02-05 | 2024-03-11 | 2024-08-30 | 2024-09-03 | 864 | PFP 8345 11TH AVE S (Re-located 4/5/24) |  | 2024-03-11 | 2024-03-28 | 2024-04-02 | 2024-09-05 | 2024-09-09 | 2024-09-09 | 45226 | Jordan (Christian) | 2024-03-11 | 2024-03-25 | 2024-04-11 | 2024-09-04 |  |  |  | 2024-09-09 | 2024-04-10 | 25 | 2024-09-13 | In Construction | 2024-09-18 | [8 empty] | 9/18 handed off to Zak 9/11 Submitted to the city 9/9 Nate: Redline corrections have been made I have moved this over to Kaylie and Permitting. 9/5 Nate: CAD print redlined and sent back to CAD for revision. 8/30 PFP relocation, layout complete pending CAD 8/2 city requested placement corrections 7/31 additional city corrections requested 7/24 additional city corrections 7/23 CAD needs review for recent City and design changes. 4/11 - PENDING BBF JOB 4/5 on CAD design PFP has been re-located 3/22 FDH is at intersection needs to be moved. 2/26 - Layout needs updated | ATT-7465 | MIN001.G0000012 | 2024-03-06 | 2024-03-28 | 2024-04-18 | 2024-04-18 | see note | [5 empty] | Preapproved permits pending | 11 | 1 | 2024 | 1 | 4 | Permit Complete | 2024-08-16
ITG-112798 | 1 | Active | Mar | Sep | PSA | SFU/MDU | PSA-1305PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 3 | Bloomington | 535 | 574 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-15 | SCOTT | 2023-12-14 |  | 2023-12-20 | YES | 0 | 1440 | 36429 | 37869 | 70.7832 | 2023-12-28 | 2024-01-09 | 2024-01-22 |  |  | 864 | PFP 8680 OLD CEDAR AVENUE S |  | 2024-01-23 | 2024-02-06 | 2024-03-27 |  |  | [3/27/24] v2 | 33683 | Cheryl Turk (hrly) | 2024-01-23 | 2024-02-06 | 2024-04-08 | 2024-07-05 | 2024-07-05 | 2024-07-05 |  | 2024-02-13 | 2024-02-23 | 19 | 2024-03-18 | In Construction | 2024-05-03 | [8 empty] | This job is placing on the east side of Bloomington Ave. S. from address 8113 south to E. 90th St. ITG-110775 PSA 1303 is placing on the wet side of Bloomington Ave S. from E. 88th St south to E. 90th St. 3/26 sent PFP relocation sketch-IQGOE complete | ATT-7827 | MIN001.G0000131 | 2024-03-20 | 2024-04-16 | 2024-04-22 | 2024-04-24 | 2024-05-20 | 2024-05-21 | [5 empty] | 12 | 1 & 2 | 2023 | 12 | 51 | Permit Complete | 2024-06-28
ITG-113311 | 1 | Active | Apr | Oct | PSA | SFU/MDU | PSA-1306PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 3 | Bloomington | 511 | 508 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2024-01-09 |  |  | 2024-01-09 | SEE NOTE | SEE NOTE |  | 2024-02-06 | NO | 1233 | SEE NOTE | SEE NOTE | 48649 | SEE NOTE | 2024-01-24 | 2024-02-02 | 2024-02-08 |  |  | 864 | PFP 8600 W 86TH ST |  | 2024-02-08 | 2024-02-22 | 2024-04-08 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 16781 | Cheryl (Cody) | 2024-03-04 | 2024-03-18 | 2024-04-11 | 2024-08-09 |  |  |  | 2024-08-09 | 2024-08-23 | 9 | 2024-09-19 | In Construction | 2024-08-28 | [8 empty] | 8/28 City has approved the permit forwarded to const.8/22 County corrections completed, sent to construction.8/9 Sent Kaylie to amend permit and sent to Dan for const.8/6 Nate: Redline Layout sent to Michael and Kaitlyn for revision to rework overlap and duct placement to stay on one side of the street. 8/1 MJ - CAD revised based on city feedback 7/24 requested permit amendment/Kaylie 7/22 revised to feed PSA 1401 & 1402 4/11 - PENDING BBF JOB 4/8 Michael will assign the 432 move 3/6 - CHANGED PFP ADDRESS FROM 8600 W 86TH ST; FIELDED AS PART OF 1101 & 1301; 1/9/24 - MOVED PSA BOUNDARIES TO ELIMINATE RXR CROSSING | ATT-7589 | MIN001.G0000119 | 2024-03-06 | 2024-04-16 | 2024-04-22 | 2024-04-23 | [7 empty] | 13 | 1 | 2024 | 2 | 6 | Permit Complete | #N/A
ITG-160787 |  | Active |  | Oct | PSA |  | PSA-1307PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 3 | Bloomington | 247 | 245 | [19 empty] | 2024-09-17 | 2024-09-20 | 2024-09-20 |  |  | NA | NA |  | 2024-09-17 | 2024-09-27 | 2024-09-23 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 0 | [8 empty] | 2024-09-24 | NA | NA | NA | In Construction | 2024-09-24 | [8 empty] | 9/24 sent bot CAD and rev laout to construction. 9/20 sent both 1304 & 1307 layout to Zak. | ATT-9303 | MIN001.G0000432 | [11 empty] | 14
ITG-160789 |  | Active |  | Oct | PSA |  | PSA-1308PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 3 | Bloomington | 490 | 343 | [19 empty] | 2024-09-17 | 2024-09-20 | 2024-09-20 |  |  | NA | NA |  | 2024-09-17 | 2024-09-27 | 2024-09-23 |  |  | 2024-09-23 | 0 | [8 empty] | 2024-09-24 | NA | NA | NA | In Construction | 2024-09-24 | [8 empty] | 9/24 sent CAD and layout to const. | ATT-9304 | MIN001.G0000433 | [11 empty] | 15
ITG-122622 | 1 | NO BUILD | Apr | Jul | BBF | NA | BBF-AT101-RT1-SEC4-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 4 | Bloomington | 865 | 862 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-01 |  |  | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-05-23 | 2024-05-28 | 2024-05-28 |  |  | 2024-05-28 | 3667 | Joseph Smith | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-08-29 | 2024-08-29 |  |  | 2024-03-04 | 2024-03-19 | 1 | 2024-03-22 | In Construction | 2024-05-02 | [8 empty] | 8/21 REVISIONS ON THIS SECTION HAVE BEEN MADE IN IQGEO, WAITING ON RESPONSE ABOUT CABLE COMING OUT OF CO NEEDING CHANGED FROM 864F TO 288F SO THAT I CAN SPLICE EVERYTHING BACK UP. 8/16 REVISION HOLDING ON RESPONSE FOR CO FIBER CABLE CHANGE7/24 changed to NO BUILD, PSA 1401 & 1402 fed from PSA 1306 7/9 - REVISIONS COMPLETED NEW PATH CREATION FOOTAGE = 4,258'. 5/28 revision sent to Zak 5/8 BBF Rt1 Sec 4 published in IQGEO; Path Creation footage = 4,243'. 5/6 checking with H. County on ammending permit or not. 5/2/24 Handed off revision to const. 4/25/Pending Revision w/Reese 4/9 AT101,1-360 left spare in HH 132 | ATT-7584/9058 | MIN001.G0000118/MIN001.G0000431 | 2024-05-13 | 2024-05-13 | 2024-05-16 | 2024-05-17 | See Note | [5 empty] | 3 jobs bring billed here - MIN001.G0000118 had an extra dash in name, was billed through MS1. MIN001.G0000431 was created to fix project name - needs to bill MS2 only with footage of 4243'. Need MIN for REV project with footage of 3667'. | 16 | 1 | #VALUE! | #VALUE! | #VALUE! | Permit Complete | 2024-06-28
ITG-113104 | 1 | Active | Apr | Aug | PSA | MIX | PSA-1401PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 4 | Bloomington | 239 | 236 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-15 | JEFF | 2023-11-29 |  | 2024-01-08 | YES | 1058 | 1876 | 28671 | 30547 | 127.8117 | 2024-01-08 | 2024-01-23 | 2024-01-23 |  |  | 432 | PFP 8247 PILLSBURY AVE S |  | 2024-04-23 | 2024-05-23 | 2024-05-23 | 2024-08-27 | 2024-08-28 | 2024-08-28 | 10683 | Cheryl (Christian) | 2024-01-29 | 2024-05-08 | 2024-05-15 | 2024-08-02 | 2024-08-16 | 2024-07-05 |  | 2024-07-29 | 2024-08-09 | 8 | 2024-03-18 | In Construction | 2024-07-29 |  | 2024-08-27 | 2024-08-27 | [5 empty] | 9/5 sent to Kaylie for permit amend. w/asbult redlines. 8/27 sent asbuilt to CAD due by 9/4. 8/9 Permit amendment requested, 2nd duct was dropped from design on sht 4,5 & 8. 8/2 city requested placement corrected on sht 16, Pleasant Av. 7/29 Requested permit amendment, sent to const/Kaylie Feeder revision sent out 7/18 per leadership 5/28 sent Zak revised CAD 5/17 sent redline to Zak-move to north side on 82nd 5/8 tie into BBF 5/6 Permit 8 to be ammended. 5/2/24 Revision sent to const Nicollet moved to the east side of the st w/BBF 4/15 hand off to const.3/26 - PENDING BBF JOB 2/22 - Moved design due date from 2/12 | ATT-7467 | MIN001.G0000013 | 2024-03-06 | 2024-04-01 | 2024-04-22 | 2024-04-23 | 2024-05-13 | 2024-05-13 | 2024-08-28 |  |  |  |  | 17 | 1 & 2 | 2024 | 1 | 2 | Permit Complete | 2024-08-16
ITG-113291 | 1 | Active | Apr | Aug | PSA | SFU/MDU | PSA-1402PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 4 | Bloomington | 626 | 626 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-15 | JAEGER | 2023-12-11 |  | 2023-12-19 | YES | 3996 | 1244 | 39868 | 41112 | 65.6741 | 2023-12-20 | 2023-12-28 | 2024-01-19 | 2024-08-22 | 2024-08-23 | 864 | PFP 8144 3RD AVE S |  | 2024-06-25 | 2024-07-05 | 2024-06-19 | 2024-09-24 | 2024-09-24 | 2024-08-28 | 36804 | Cheryl (Christian) | 2024-01-19 | 2024-05-08 | 2024-05-15 | 2024-09-24 |  | 2024-07-05 |  | 2024-07-29 | 2024-09-09 | 21 | 2024-08-27 | In Construction | 2024-07-29 |  | 2024-04-23 | [6 empty] | 9/25 City has accepted the revised permit. 9/24 Revised CAD sent to const & Kaylie for city to amend 9/24 sent const revision to CAD for 82nd east of Portland.8/2 city requested placement corrections 7/29 Requested permit amendment, sent to const Feeder revision sent out 7/18 per leadership 5/17 sent redline to Zak-move to north side on 82nd .5/8 tie into BBF 5/6 permit 21 to be ammended. 5/2/24 Revision sent to const Nicollet moved to the east side of the st w/BBF 4/22 Revision send to construction 4/12 handoff to construction 3/25 - PENDING BBF JOB 4/22/24 PFP moved north to PL, sent Zac new copy. 2/22 - Moved design due date from 2/2; 1/26 - RECEIVED SITE DETAILS & BBF FIELD NOTES; 1/19 - LU COUNT WAS 631 BUT 5 ADDRESSES WERE INVALID MAKING COUNT 626; 1/16 - STILL NEED BBF DETAILS; 12/28 - SENT TO ADD BBF | ATT-7468 | MIN001.G0000014 | 2024-03-06 | 2024-04-16 | 2024-04-22 | 2024-04-23 | 2024-06-25 | 2024-06-25 | [5 empty] | 18 | 1 & 2 | 2023 | 12 | 51 | Permit Complete | 2024-06-28
ITG-122625 | 3 | NO BUILD | May | Aug | BBF | NA | BBF-AT101-RT1-SEC5-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 5 | Bloomington | 1035 | 0 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-01 |  |  | NA | SCOTT | 2024-02-08 |  | 2024-02-25 | NA | 7454 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-02-27 | 2024-03-12 | 2024-03-06 |  |  | 2/29/24 V3 | 7638 | Joseph Smith | 2024-06-06 | 2024-06-06 | 2024-06-06 |  |  |  |  | 2024-03-08 | 2024-03-21 | 2 out of 4 | [11 empty] | 7/22 NO BUILD PER TED7/17 Nate job is on hold due to RT1 BBF reroute please wait until we receive a response from GigaPower . 6/6 - BBF Rt1 Sec 5 published in IQGEO; Path Creation footage = 7,638'. | ATT-8683 | MIN001.G0000349 | 2024-06-21 | Rejected/Cancelled | [8 empty] | Has been cancelled in CMPM | 19 |  | 2024 | 2 | 9 | #REF! | 2024-07-26
ITG-113299 | 3 | NO BUILD |  |  | PSA | BCL/MDU | PSA-1501PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 5 | Bloomington | 407 |  |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-15 | [8 empty] | 0 | 0 | [37 empty] | 7/22 NO BUILD PER TED4/3 - PER ANGELA PAUSE ON BUILD; 3/29 - MOVE FORECAST MONTHS OUT FROM MAY & JUL TO SEP & NOV | ATT-7469 | MIN001.G0000015 | 2024-03-14 | 2024-04-16 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 20 | 1 | 1900 | 1 | 0 | #REF! | 2025-06-13
ITG-113301 | 3 | NO BUILD |  |  | PSA | BCL/MDU | PSA-1502PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 5 | Bloomington | 628 |  |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-15 | [8 empty] | 0 | 0 | [37 empty] | 7/22 NO BUILD PER TED4/3 - PER ANGELA PAUSE ON BUILD; 3/29 - MOVE FORECAST MONTHS OUT FROM MAY & JUL TO SEP & NOV | ATT-7470 | MIN001.G0000016 | 2024-03-14 | 2024-04-16 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 21 | 1 | 1900 | 1 | 0 | #REF! | 2025-06-13
ITG-122683 | 3 | NO BUILD | May | Aug | BBF | NA | BBF-AT101-RT1-SEC6-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 6 | Bloomington | 1591 | 218 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-01 |  |  | NA | Scott | 2024-02-08 |  | 2024-03-01 | NA | 6254 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-06-25 | 2024-07-01 | 2024-07-04 |  |  | 2024-07-01 | 6171 | Joseph Smith | 2024-06-06 | 2024-06-06 | 2024-06-06 |  |  |  |  | 2024-03-07 | 2024-07-10 | 2 out of 4 | [11 empty] | 7/22 NO BUILD PER TED7/17 Nate job is on hold due to RT1 BBF reroute please wait until we receive a response from GigaPower 6/6 - BBF Rt1 Sec 6 published in IQGEO; Path Creation footage = 6,171'. | ATT-7895 | MIN001.G0000178 | 2024-06-21 | Rejected/Cancelled | [8 empty] | Has been cancelled in CMPM | 22 |  | 2024 | 3 | 9 | #REF! | 2024-10-12
ITG-113303 | 3 | NO BUILD |  |  | PSA | BCL | PSA-1601PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 6 | Bloomington | 188 |  |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-16 | [8 empty] | 0 | 0 | [37 empty] | 7/22 NO BUILD PER TED4/3 - PER ANGELA PAUSE ON BUILD; 3/29 - MOVE FORECAST MONTHS OUT FROM PERMITTING MAY & CONSTRUCTION JUL TO PERMITTING SEP & CONSTRUCTION NOV | ATT-7471 | MIN001.G0000017 | 2024-03-14 | 2024-04-16 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 23 | 1 | 1900 | 1 | 0 | #REF! | 2028-12-31
ITG-113304 | 3 | NO BUILD |  |  | PSA | BCL/MDU | PSA-1602PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 6 | Bloomington | 471 |  |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-16 | [8 empty] | 0 | 0 | [37 empty] | 7/22 NO BUILD PER TED4/3 - PER ANGELA PAUSE ON BUILD; 3/29 - MOVE FORECAST MONTHS OUT FROM PERMITTING JUN & CONSTRUCTION AUG TO PERMITTING SEP & CONSTRUCTION NOV | ATT-7472 | MIN001.G0000018 | 2024-03-14 | 2024-04-16 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 24 | 1 | 1900 | 1 | 0 | #REF! | 2028-12-31
ITG-113305 | 3 | NO BUILD |  |  | PSA | BCL/MDU | PSA-1603PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 6 | Bloomington | 656 |  |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-16 | [8 empty] | 0 | 0 | [37 empty] | 7/22 NO BUILD PER TED4/3 - PER ANGELA PAUSE ON BUILD; 3/29 - MOVE FORECAST MONTHS OUT FROM PERMITTING JUN & CONSTRUCTION AUG TO PERMITTING SEP & CONSTRUCTION NOV; 1/30/24 - PER TED - MAY NOT FEED PSA 1603 DUE TO BCL & DUE TO METCOUNCIL (LITE RAIL) CROSSING FEES | ATT-7473 | MIN001.G0000019 | 2024-03-14 | 2024-04-16 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 25 | 1 | 1900 | 1 | 0 | #REF! | 2028-12-31
ITG-133307 | 3 | NO BUILD |  |  | PSA | BCL/MDU | PSA-1604PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 6 | Bloomington | 276 |  |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-16 | [8 empty] | 0 | 0 | [37 empty] | 7/22 NO BUILD PER TED4/3 - PER ANGELA PAUSE ON BUILD; 3/29 - MOVE FORECAST MONTHS OUT FROM PERMITTING JUN & CONSTRUCTION AUG TO PERMITTING SEP & CONSTRUCTION NOV; 1/30/24 - PER TED - MAY NOT FEED PSA 1604 DUE TO BCL & DUE TO METCOUNCIL (LITE RAIL) CROSSING FEES | ATT-7475 | MIN001.G0000020 | 2024-03-14 | 2024-04-16 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 26 | 1 | 1900 | 1 | 0 | #REF! | 2028-12-31
ITG-122760 | 3 | NO BUILD | Jun | Aug | BBF | NA | BBF-AT101-RT1-SEC7-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 7 | Bloomington | 1329 | 218 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-01 |  |  | NA | Scott | 2024-02-08 |  | 2024-03-01 | NA | 2801 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-03-05 | 2024-03-20 | 2024-03-07 |  |  | 3/6/24 V2 | 4354 | Joseph Smith | 2024-06-06 | 2024-06-06 | 2024-06-06 | [18 empty] | 7/22 NO BUILD PER TED7/17 Nate job is on hold due to RT1 BBF reroute please wait until we receive a response from GigaPower 6/6 - BBF Rt1 Sec 7 published in IQGEO; Path Creation footage = 4,354'. 4/9 AT101,385-408 left spare in HH 149. 3/29 - MOVE FORECAST MONTHS OUT FROM PERMITTING MAY & CONSTRUCTION JUL TO PERMITTING JUN & CONSTRUCTION AUG; 3/13 - SENT EMAIL TO FIELDER TO GET STATUS OF RXR CROSSING DRAWING | ATT-7896 | MIN001.G0000179 | 2024-06-21 | Rejected/Cancelled | [8 empty] | Has been cancelled in CMPM | 27 |  | 2024 | 3 | 9 | #REF! | 2024-10-12
ITG-133308 | 3 | NO BUILD |  |  | PSA | BCL | PSA-1701PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 7 | Bloomington | 588 |  |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-16 | [8 empty] | 0 | 0 | [37 empty] | 7/22 NO BUILD PER TED4/3 - PER ANGELA PAUSE ON BUILD; 3/29 - MOVE FORECAST MONTHS OUT FROM PERMITTING MAY & CONSTRUCTION JUL TO PERMITTING SEP & CONSTRUCTION NOV | ATT-7476 | MIN001.G0000021 | 2024-03-14 | 2024-04-16 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 28 | 1 | 1900 | 1 | 0 | #REF! | 2028-12-31
ITG-113310 | 3 | NO BUILD |  |  | PSA | BCL/MDU | PSA-1702PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 7 | Bloomington | 639 |  |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-16 | [8 empty] | 0 | 0 | [37 empty] | 7/22 NO BUILD PER TED4/3 - PER ANGELA PAUSE ON BUILD; 3/29 - MOVE FORECAST MONTHS OUT FROM PERMITTING MAY & CONSTRUCTION JUL TO PERMITTING SEP & CONSTRUCTION NOV | ATT-7477 | MIN001.G0000022 | 2024-05-14 | 2024-05-14 | 2024-05-15 | 2024-05-20 | Stop | Stop | Stop | Stop | Stop | Stop |  | 29 | 1 | 1900 | 1 | 0 | #REF! | 2028-12-31
ITG-137998 |  | No Build - Ex Comp |  |  | PSA | SFU/MDU | PSA-1703PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 7 | Bloomington | 402 |  |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 | [50 empty] | PER TED - 125 SFUs & 55 MDU units. No Build - competition | ATT-8509 | MIN001.G0000345 | 2024-05-29 | 2024-05-30 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 30 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-112362 | 3 | NO BUILD |  |  | PSA | SFU | PSA-1704PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #1 | BBF RTE 1 SEC 7 | Bloomington | 102 | 98 |  | Darlene White |  | 2023-10-31 | Christian Weller | 2023-12-01 |  |  | 2023-11-16 | SCOTT | 2023-11-21 |  | 2023-11-29 | YES | 1129 | 264 | 8426 | 8690 | 85.1961 | 2023-11-30 | 2023-12-08 | 2023-12-08 |  |  | 288 | PFP 2220 E 88TH ST |  | 2023-12-07 | 2024-01-03 | 2024-01-03 |  |  |  | 7097 | Christian Weller (hrly) |  | N/A | N/A |  |  |  |  | N/A | [13 empty] | 7/22 NO BUILD PER TED4/22/24 HOLD note sent to Christian. CAD Permit will need utilities which have been requested 12/18/23 | ATT-7478 | MIN001.G0000023 | 2024-03-14 | 2024-04-16 | 2024-06-27 | 2024-07-24 | ? | [5 empty] | CAD Complete - Do we want to take this further than MS1. Per Ted at MS1 approval - don’t go past MS1 | 31 | 1 | 2023 | 11 | 48 | #REF! | 2028-12-31
ITG-123513 | 1 | Active | Mar | Aug | BBF | NA | BBF-AT201-RT2-SEC1-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 1 | Bloomington | 176 | 218 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-11 |  |  | NA | NA | NA |  | NA | NA | 3177 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-02-14 | 2024-02-29 | 2024-02-26 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2169 | Joseph Smith | 2024-05-06 | 2024-05-09 | 2024-05-09 | 2024-08-21 |  |  |  | 2024-08-21 | 2024-03-05 | 1 | 2024-03-21 | In Construction | 2024-04-17 |  | 2023-04-22 | [6 empty] | 9/11 Zak-Path created.8/21 sent to Kaylie and const. 8/21 missing second duct on sht 10 8/1 Nate: that job has already been handed off to construction 4/22 please disregard 7/30 note. 7/30 Nate: Reviewing. 5/9 BBF Rt2 Sec 1 published in IQGEO; Path Creation footage = 2,169'. 4/17/2024 Overlaps with PSA's correctted, version 3 issued, requires additional permitting. | ATT-7897 | MIN001.G0000180 | 5/9/2024 | 2024-05-09 | 2024-05-16 | 2024-05-17 | 2024-08-13 | 2024-08-14 | [5 empty] | 32 | 1 & 2 | #VALUE! | #VALUE! | #VALUE! | Permit Complete | 2024-06-21
ITG-114042 | 1 | Active | Mar | Oct | PSA | SFU | PSA-2101PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 1 | Bloomington | 176 | 218 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-06 | SCOTT | 2023-12-13 |  | 2023-12-15 | YES | 3177 | 1359 | 15743 | 17102 | 97.1705 | 2023-12-28 | 2024-01-12 | 2024-02-12 |  |  | 432 | PFP 9149 DUPONT AVE S |  | 2024-05-31 | 2024-06-06 | 2024-06-06 | 2024-09-24 | 2024-09-25 | 2024-09-25 | 11345 | Tammi Baker | 2024-02-22 | 2024-03-13 | 2024-03-15 | 2024-08-15 | 2024-08-28 |  |  | 2024-08-15 | 2024-08-15 | 10 | 2024-05-21 | In Construction | 2024-08-16 | [8 empty] | 8/20 STOP work, emailed Kaylie & const. 8/15 Nate requested permit ammendment 8/2 Nate: CAD redline corrections requested to bring print to current standards. 8/1 Nate: under review. 5/6 no overlap, PFP address is 9149 Colfax per CAD, emailed Tammi to confirm IQGEO. 3/15 - PENDING BBF JOB 4/8 sent email to move FDH out of the intersection.; MNDOT PERMIT IS UNDER THE BBF RTE 4 SEC 1 SUBMITTED TO MNDOT ON 3/20 | ATT-7479 | MIN001.G0000024 | 2024-03-07 | 2024-03-28 | 2024-04-04 | 2024-04-04 | 2024-06-20 | 2024-06-24 | [5 empty] | 33 | 1 & 2 | 2023 | 12 | 50 | Permit Complete | 2024-08-16
ITG-124862 | 1 | Active | Apr | Jul | BBF | NA | BBF-AT201-RT2-SEC2-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 2 | Bloomington | 3319 | 2839 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-11 |  |  | NA | NA | NA |  | NA | NA | 8331 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-02-22 | 2024-05-23 | 2024-05-26 |  |  | 2024-08-27 | 10078 | Joseph Smith | 2024-05-06 | 2024-05-09 | 2024-05-24 | 2024-07-16 | 2024-07-16 |  |  | 2024-03-05 | 2024-04-19 | 6 | COUNTY: 3/22/24 RR: 5/7/24 CITY: 5/28/24 | In Construction | 2024-05-28 |  | 2024-08-15 | [6 empty] | 9/11 Zak-Partially complete. East side path nearly complete 9/11 BBF RTE 2 SEC 2 ITG-124862 City & County accepted the updated print, uploaded revised approved permit pkg into GP's sharepoint. good to go! 7/16 - REVISIONS MADE NEW PATH CREATION FOOTAGE = 10,078'. 5/24 BBF Rt2 Sec 2 published in IQGEO; Path Creation footage = 10,067'. 5/23 HH location correction sent to Joe, const & CAD, 2nd & 92nd 5/10 Path Creation footage is 3,302’ 5/1 overlap issues have been updated. | ATT-7898 | MIN001.G0000181 | 2024-06-25 | 2024-06-25 | 2024-06-28 | 2024-06-28 | 2024-08-27 | 2024-08-28 |  |  |  |  | Need to double check footage before submitting ms2 - joe just re-validated the footage | 34 | 1 & 2 | #VALUE! | #VALUE! | #VALUE! | Permit Complete | 2024-06-24
ITG-114046 | 1 | Active | Apr | Oct | PSA | SFU/MDU | PSA-2201PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 2 | Bloomington | 517 | 522 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-06 | SCOTT | 2023-12-17 |  | 2023-12-26 | YES | 1126 | 953 | 22779 | 23732 | 45.9033 | 2024-01-04 | 2024-04-23 | 2024-04-24 |  |  | 864 | PFP 9304 NICOLLET AVE S |  | 2024-01-23 | 2024-05-03 | 2024-05-01 | 2024-09-17 | 2024-09-18 | 9/18 v3 | 21589 | Jordan (Christian) | 2024-01-23 | 2024-03-11 | 2024-03-11 | 2024-09-19 |  | 2024-07-03 |  | 2024-07-10 | 2024-07-26 | 10 | 2024-03-22 | In Construction | 2024-07-10 | [8 empty] | 9/19 sent to Kaylie for amendment and to ITG. 9/3 Dan's redlines sent to CAD for final permit and facilities on 95th St. move to the south side of street. 5/7 sent Dan's redline update on latest CAD version4/24 sent layout revisions to Christian 4/17 Revision sent to construction 4/16 PENDING 92ND & SYNDICATE CHANGES (HYDRANT ISSUE) 4/17/2024 revision for BBF overlap 4/16 Pending easement resolution per City 4/12 Handoff to construciton 4/2 - RECEIVED UPDATED LAYOUT FOR HYDRANT ISSUE & 4 LUS ON SYNDICATE BEING SERVED BY FUTURE AERIAL DROPS; 2/22 - Move design due date from 2/7 | ATT-7480 | MIN001.G0000025 | 2024-03-07 | 2024-04-16 | 2024-04-22 | 2024-04-22 | 2024-06-25 | 2024-06-25 | [5 empty] | 35 | 1 & 2 | 2023 | 12 | 52 | Permit Complete | 2024-06-28
ITG-114049 | 1 | Active | Apr | Jul | PSA | SFU/MDU | PSA-2202PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 2 | Bloomington | 461 | 486 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-07 | SCOTT | 2023-12-18 |  | 2023-12-30 | YES | 1866 | 1294 | 31945 | 33239 | 72.102 | 2024-01-05 | 2024-01-22 | 2024-02-01 |  |  | 864 | PFP 9337 2ND AVE S |  | 2024-05-14 | 2024-05-15 | 2024-05-15 | 2024-07-24 | 2024-07-25 | 2024-07-25 | 29412 | Jordan (Christian) | 2024-02-05 | 2024-06-28 | 2024-06-26 | 2024-07-26 | 2024-08-15 | 2024-07-03 |  | 2024-07-25 | 2024-07-30 | 18 | 2024-03-15 | In Construction | 2024-04-10 | [8 empty] | 8/28 City has approved CAD revision. 6/26 - Due to Christian being out of office, had to issue to Cheryl Turk to finish design as this wa s a priority ask needed from GP this week 6/24 - Moved design DD out - Christian took PTO last week for personal matter and design still has errors to clean up 6/10 - IQG complete but errors showing up that Christian needs assistance to resolve 5/29 - Field revisions were needed to complete design. information received. Design will be done 5/29 5/15 Dan field revisions updated and sent to Dan & Kaylie (no permit changes required) 4/26 ROW issues on 92nd St East, pending solution from construciton 4/10 Pending City approval for updated cad. 4/9 CAD updated w/VZW HH on sht 19. Verizon Dark Fiber along with Eagan PSA2803-BLOOM meet point permit applied for on 4/4. 4/2 - SEND UPDATED CAD TO PERMITTING AND CHRISTIAN; 3/27 - UPDATED CAD W/ ADDITIONAL 2 HHS & 2" CONDUIT FOR DEDICATED 24FOC TO VERIZON SITE; 2/22 - Move design due date from 2/23 | ATT-7481 | MIN001.G0000026 | 2024-03-07 | 2024-04-16 | 2024-04-22 | 2024-04-22 | 2024-06-20 | 2024-06-20 | 2024-06-28 | 2024-06-28 | 2024-07-08 |  |  | 36 | 1 & 2 | 2023 | 12 | 52 | Permit Complete | 2024-07-19
ITG-114050 | 1 | Active | Apr |  | PSA | SFU/MDU | PSA-2203PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 2 | Bloomington | 570 | 555 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-06 | JAEGER | 2023-12-26 |  | 2024-01-02 | YES | 1679 | 1287 | 40391 | 41678 | 73.1193 | 2024-01-10 | 2024-01-25 | 2024-02-01 |  |  | 864 | PFP 9350 PORTLAND AVE S |  | 2024-02-07 | 2024-05-03 | 2024-05-01 | 2024-08-15 | 2024-08-27 | 2024-08-27 | 35863 | Cheryl Turk (hrly) | 2024-02-05 | 2024-03-11 | 2024-03-11 | [5 empty] | 2024-03-21 | 15 | 2024-06-27 | [10 empty] | 8/15 Sync needed with 2205PA CAD Revision Requested 3/11/2024 Pending BBF 2/22 - Moved design due date from 2/23; 1/2 - BBF FIELDED; 12/23/23 - SENT TO FIELD BBF | ATT-7482 | MIN001.G0000027 | 2024-03-07 | 2024-04-16 | 2024-04-22 | 2024-04-22 | 2024-07-24 | 2024-07-24 | [5 empty] | 37 | 1 & 2 | 2024 | 1 | 1 | Permit Complete | 2024-09-27
ITG-114051 | 1 | Active | Apr | Nov | PSA | SFU | PSA-2204PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 2 | Bloomington | 478 | 447 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-06 | JAEGER | 2023-12-28 |  | 2024-01-11 | YES | 1665 | 114 | 41417 | 41531 | 86.8849 | 2024-01-12 | 2024-01-26 | 2024-02-16 |  |  | 864 | PFP 900 E 92ND ST |  | 2024-02-16 | 2024-05-03 | 2024-05-01 | 2024-09-10 | 2024-09-19 | 2024-09-19 | 40275 | Cheryl Turk | 2024-03-08 | 2024-03-20 | 2024-04-04 | 2024-07-11 | 2024-07-11 |  |  | 2024-09-19 | 2024-04-05 | 6 out of 22 | [11 empty] | 9/19 Nate: CAD Revions approved and moved to CAD with a expidte due to construction waiting on permit approval. 9/10 NATE: Job sent back to CAD for revision to place HH's and FP's to PL's and to update some conduts size. 4/4 - PENDING BBF JOB | ATT-7483 | MIN001.G0000028 | 2024-03-07 | 2024-04-01 | 2024-08-26 | 2024-08-26 | [7 empty] | 38 | 1 | 2024 | 1 | 2 | #REF! | 2024-09-27
ITG-114052 | 1 | Active | Apr | Sep | PSA | SFU | PSA-2205PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 2 | Bloomington | 419 | 430 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-06 | SCOTT | 2024-01-05 |  | 2024-01-11 | YES | 1995 | 136 | 34452 | 34588 | 82.5489 | 2024-01-19 | 2024-02-02 | 2024-02-02 | 2024-08-15 | 2024-08-28 | 864 | PFP 9137 14TH AVE S |  | 2024-02-02 | 2024-05-03 | 2024-05-01 | 2024-08-14 | 2024-08-15 | 2024-08-15 | 32868 | Jordan (Christian) | 2024-02-05 | 2024-07-31 | 2024-07-31 | 2024-09-04 | 2024-09-10 | 2024-09-19 |  | 2024-08-15 | 2024-03-20 | 16 | 2024-03-22 | In Construction | 2024-08-15 |  | 2024-09-16 | [6 empty] | 8/23 City & County approved permits 8/21 amendment sent to city/county8/15 requested permit amend. Layout revision needed. 8/14 sent CAD revision back to Brian T. Const has built the north side of 92nd already. 7/29 Job from Christian only 30% completed. Reassigned to Jordan Check for Overlap issues 2/22 - CAD corrections completed; Move design due date from 3/1 | ATT-7484 | MIN001.G0000029 | 2024-03-07 | 2024-04-16 | 2024-04-22 | 2024-04-22 | 2024-05-13 | 2024-05-13 | [5 empty] | 39 | 1 & 2 | 2024 | 1 | 2 | Permit Complete | 2024-08-16
ITG-114053 | 1 | Active | Apr |  | PSA | SFU/MDU | PSA-2206PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 2 | Bloomington | 412 | 399 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-06 | SCOTT | 2024-01-09 |  | 2024-01-17 | YES | 0 | 1949 | 33465 | 35414 | 85.9563 | 2024-01-19 | 2024-02-02 | 2024-02-08 |  |  | 576 | PFP 1505 OLD SHAKOPEE RD E |  | 2024-02-08 | 2024-05-08 | 2024-05-08 |  |  | 5/8 V2 | 30669 | Eric Lynn | 2024-03-14 | 2024-05-14 | 2024-05-14 | 2024-07-15 | 2024-07-15 |  |  |  | 2024-04-18 | 14 out of 16 | [11 empty] | 5/8 Layout changes sent to Eric 4/1 - PENDING BBF 3/7 - NEED MNDOT CAD FOR MNDOT ROW | ATT-7485 | MIN001.G0000030 | 2024-03-07 | 2024-04-16 | 2024-04-22 | 2024-04-22 | [7 empty] | 40 | 1 | 2024 | 1 | 3 | #REF! | 2024-09-27
ITG-114054 | 1 | Active | Apr | Dec | PSA | BCL/MDU | PSA-2207PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 2 | Bloomington | 462 | 466 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-06 | SCOTT | 2024-01-11 |  | 2024-01-18 | YES | 0 | 971 | 3414 | 4385 | 9.4913 | 2024-01-19 | 2024-02-02 | 2024-02-08 |  |  | 576 | PFP 9140 OLD CEDAR S |  | 2024-02-08 | 2024-05-03 | 2024-05-01 | 2024-09-10 | 2024-09-12 | 2024-09-11 | 4328 | Eric Lynn | 2024-03-04 | 2024-03-18 | 2024-03-15 | 2024-07-10 | 2024-07-10 |  |  |  | 2024-03-20 | 3 | 2024-03-26 | In Construction | 2024-05-06 | [8 empty] | Check for Overlap issues 3/15 - PENDING BBF STRUCTURE JOB | ATT-7486 | MIN001.G0000031 | 2024-03-14 | 2024-04-16 | 2024-04-22 | 2024-04-22 | 2024-05-13 | 2024-05-13 | [5 empty] | 41 | 1 & 2 | 2024 | 1 | 3 | Permit Complete | 2024-08-16
ITG-123728 | 1 | Active | Apr | Aug | BBF | NA | BBF-AT201-RT2-SEC3-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 3 | Bloomington | 513 | 408 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-11 |  |  | NA | NA | NA |  | NA | NA | 7532 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-05-09 | 2024-05-13 | 2024-05-13 | 2024-07-18 | 2024-07-31 | 2024-07-31 | 3408 | Joseph Smith | 2024-05-06 | 2024-05-09 | 2024-05-09 | 2024-07-31 | 2024-07-31 |  |  | 2024-07-31 | 2024-03-19 | 1 out of 3 | [11 empty] | 7/31 IQGEO REVISIONS COMPLETED, NEW PATH CREATION FOOTAGE = 3,408'. 7/31 Nate: CAD dated 7/31 approved and submited to permitting for amendment. 7/18 Nate Design and CAD revisions requested due to BFF Overlap RT2 SEC3 no easement on east side of Lyndale between 93rd and 94th. 5/9 BBF Rt2 Sec 3 published in IQGEO; Path Creation footage = 3,179'. 5/8/2024 Overlap issues updated 4/18 | ATT-7899 | MIN001.G0000182 | 2024-06-03 | 2024-06-04 | 2024-06-11 | 2024-06-11 | [6 empty] | Need to double check footage before submitting ms2 - joe just re-validated the footage | 42 | 1 & 2 | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-06-28
ITG-114043 | 1 | Active | Apr | Nov | PSA | BCL/6 SFU | PSA-2301PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 3 | Bloomington | 382 | 273 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-06 | JAEGER | 2024-01-02 |  | 2024-01-08 | YES | 5434 | 86 | 16010 | 16096 | 42.1361 | 2024-01-11 | 2024-01-26 | 2024-02-12 |  |  | 864 | PFP 9225 W 93RD ST |  | 2024-06-18 | 2024-06-12 | 2024-06-21 | 2024-08-28 | 2024-08-29 | 2024-08-29 | 7752 | Jordan Struck | 2024-03-22 | 2024-04-05 | 2024-03-29 | 2024-07-10 |  |  |  | 2024-07-31 | 2024-04-26 | 6 out of 7 | [11 empty] | 8/28 City requested correction on permit 5 8/23 CAD correction of City request completed. 8/19 City requested revision7/31 Nate: CAD dated 7/31 approved and submited to permitting for amendment. 7/18 Nate Design and CAD revisions requested due to BFF Overlap RT2 SEC3 no easement on east side of Lyndale between 93rd and 94th. 6/21 sent CAD corrections6/12 reviewed sent to Kaylie for permit 6/11 sent CAD corrections -Zak is looking at this one.3/29 - PENDING BBF JOB 4/17/24 Revision for BBF overlap 4/8 Ted's priority list has moved this project to level 1. 4/2 - RECEIVED EMAIL FRO GP - CHRIS MCDERMOTT THAT THIS PSA IS NO BUILD; 1/12/24 - RXR 854436K & 854432D CAD DRAWINGS COMPLETE | ATT-7487 | MIN001.G0000032 | 2024-03-14 | 2024-03-21 | 2024-03-22 | 2024-04-09 | [7 empty] | 43 | 1 | 2024 | 1 | 2 | #REF! | 2024-10-18
ITG-114044 | 1 | Active | Jun |  | PSA | BCL/MDU | PSA-2302PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 3 | Bloomington | 131 | 135 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-06 | JAEGER | 2024-01-09 |  | 2024-01-24 | YES | 2098 | 42 | 6755 | 6797 | 51.8855 | 2024-05-27 | 2024-06-05 | 2024-06-03 |  |  | 288 | PFP 9701 LYNDAL AVE SE |  | 2024-06-06 | 2024-06-14 | 2024-06-12 |  |  | [6-12-24] | 4106 | James Lugo | 2024-06-04 | 2024-06-11 | 2024-06-04 |  |  |  |  | 2024-05-17 | 2024-05-20 | [12 empty] | 6/12 Ammended copy for permitting 4/29 - Hold for BCL/MDU 3/29 - MOVE FORECAST MONTHS OUT FROM MAY & JUL TO SEPT & NOV | ATT-7488 | MIN001.G0000033 | 2024-03-14 | 2024-04-16 | 2024-04-22 | 2024-04-22 | [7 empty] | 44 | 1 | 2024 | 1 | 4 | #REF! | 2024-10-18
ITG-127087 | 1 | Active | Apr | Oct | BBF | NA | BBF-AT201-RT2-SEC4-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 4 | Bloomington | 724 | 716 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-11 |  |  | NA | NA | NA |  | NA | NA | 2653 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-05-09 | 2024-05-13 | 2024-05-13 |  |  | 2024-05-13 | 3359 | Joseph Smith | 2024-05-06 | 2024-05-09 | 2024-05-10 | 2024-07-22 | 2024-07-23 |  |  | 2024-07-23 | 2024-03-22 | 2 | 2024-09-11 | In Construction | 2024-09-11 | [8 empty] | 9/11County accepted udate print, City pre-approved ITG needs to contact them to release permit. 7/23 Nate Final CAD sent to permitting for resubmittal. 7/23 Path Creation footage =3,359'. Nate 7/22 Waiting on disscussion with Zak at ITG before moving forward to Permitting updates. 5/9 BBF Rt2 Sec 4 published in IQGEO; Path Creation footage =3,302'. 5/8 CAD corrections due 5/13 for overlap w/PSA 2401. | ATT-7900 | MIN001.G0000183 | 2024-05-13 | 2024-05-13 | 2024-05-16 | 2024-05-17 | 2024-09-23 | [6 empty] | 45 | 1 & 2 | #VALUE! | #VALUE! | #VALUE! | Permit Complete | 2024-10-12
ITG-114047 | 1 | Active | Apr | Nov | PSA | MIX | PSA-2401PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 4 | Bloomington | 553 | 550 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-06 | JAEGER | 2024-01-12 |  | 2024-01-25 | YES | 2653 | 1 | 7782 | 7783 | 14.0741 | 2024-01-30 | 2024-02-12 | 2024-02-16 |  |  | 576 | PFP 9706 BLAISDELL AVE S |  | 2024-05-09 | 2024-05-13 | 2024-05-13 | 2024-09-11 | 2024-09-13 | 2024-09-13 | 5464 | Tammi Baker | 2024-05-10 | 2024-05-20 | 2024-05-29 | 2024-09-26 |  |  |  | 2024-09-26 | 2024-03-22 | 3 | 2024-06-27 | [10 empty] | 9/26 Nate: Print has been reviewed and approved and sent to permitting. 9/11 Nate: CAD revision requested to bring up to current standards. 5/10/2024 handed off BBF complete 4/3/2024 - PENDING BBF JOB | ATT-7489 | MIN001.G0000034 | 2024-03-07 | 2024-03-21 | 2024-04-23 | 2024-04-25 | 2024-07-24 | 2024-07-24 | [5 empty] | 46 | 1 & 2 | 2024 | 1 | 4 | Permit Complete | 2024-09-27
ITG-114048 | 1 | Active | Apr | Dec | PSA | SFU/MDU | PSA-2402PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 4 | Bloomington | 171 | 166 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-06 | JAEGER | 2024-01-18 |  | 2024-01-22 | YES | 0 | 1098 | 2384 | 3482 | 20.3626 | 2024-01-30 | 2024-02-09 | 2024-02-14 |  |  | 288 | PFP 9912 NICOLLET AVE S |  | 2024-02-15 | 2024-03-01 | 2024-02-26 |  |  | [2/20/24] V3 | 2406 | Jordan Struck | 2024-05-10 | 2024-05-20 | 2024-04-01 | 2024-07-10 |  |  |  | 2024-08-02 | 2024-03-22 | 2 | 2024-04-04 | In Construction | 2024-05-06 | [8 empty] | 8/2 Nate: Reviewed CAD 2/20/24v3 still good to go, no need to for permit amendment. 5/10/2024 handed off BBF complete 5/6 no overlap issues 4/1/2024 - PENDING BBF JOB | ATT-7490 | MIN001.G0000035 | 2024-03-07 | 2024-04-16 | 2024-04-22 | 2024-04-23 | 2024-05-13 | 2024-05-13 | [5 empty] | 47 | 1 & 2 | 2024 | 1 | 4 | Permit Complete | 2024-07-22
ITG-127104 | 1 | Active | Apr |  | BBF | NA | BBF-AT201-RT2-SEC5-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 5 | Bloomington | 411 | 390 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-11 |  |  | NA | NA | NA |  | NA | NA | 2755 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-03-05 | 2024-03-20 | 2024-03-21 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2797 | Joseph Smith | 2024-05-13 | 2024-05-14 | 2024-05-14 | 2024-07-24 | 2024-08-27 |  |  | 2024-07-24 | 2024-04-08 | 1 out of 3 | [11 empty] | 8/27 went through updated CAD have made these changes already Pathh Creation Footage = 2,797'.8/20 City has ROW revisions.Nate 7/24 CAD revisions 7/10 look good and have been submitted to permitting for resubmittal. Nate 7/22 Waiting on disscussion with Zak at ITG before moving forward to Permitting updates. 5/14 BBF Rt2 Sec 5 published in IQGEO; Path Creation footage =2,797'. 5/8 Overlaps corrected. 5/7 notified Zak & Kaylie of revision 5/6 this job overlaps w/PSA 2501 placement on east side of Lyndale. Email Michael for a revision. | ATT-7901 | MIN001.G0000184 | 2024-05-14 | 2024-05-14 | 2024-05-16 | 2024-05-17 | [6 empty] | Update footage for MS2 per Joes revision | 48 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-07-26
ITG-114061 | 1 | Active | Apr |  | PSA | MIX | PSA-2501PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 5 | Bloomington | 411 | 390 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-06 | SCOTT | 2024-01-11 |  | 2024-01-20 | YES | 2755 | 1238 | 6374 | 7612 | 18.5207 | 2024-01-31 | 2024-02-13 | 2024-02-20 |  |  | 576 | PFP 9900 LYNDALE AVE S |  | 2024-02-20 | 2024-03-06 | 2024-02-26 |  |  | [2-29-24] V3 | 2849 | Cheryl Turk | 2024-04-01 | 2024-04-10 | 2024-04-10 |  |  |  |  | 2024-08-02 | 2024-03-20 | 4 | 2024-04-04 | In Construction | 2024-05-06 | [8 empty] | 8/2 Nate: Reviewed CAD 2/29/24v3 still good to go, no need to for permit amendment.5/7 sent to const. 5/6 overlaps with BBF rte2 sec5, emailed MJ & Zak. | ATT-7491 | MIN001.G0000036 | 2024-03-07 | 2024-04-16 | 2024-04-22 | 2024-04-23 | 2024-05-14 | 2024-05-14 | [5 empty] | 49 | 1 & 2 | 2024 | 1 | 3 | Permit Complete | 2024-07-22
ITG-160790 |  | Active |  | Dec | PSA |  | PSA-2502PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 5 | Bloomington | 250 | [58 empty] | ATT-9305 | MIN001.G0000434 | [11 empty] | 50
ITG-129467 | 1 | Active | Apr | Nov | BBF | NA | BBF-AT201-RT2-SEC6-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 6 | Bloomington | 1650 | 1119 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-11 |  |  | NA | NA | NA |  | NA | NA | 6371 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-03-20 | 2024-04-19 | 2024-04-19 |  |  | 4/19/24 V2 | 6554 | Joseph Smith | 2024-06-13 | 2024-06-13 | 2024-06-13 |  |  |  |  | 2024-07-30 | 2024-05-08 | [12 empty] | Nate 7/24 CAD dated 4/19V2 has been reviewed and already submitted to city (5/8) and waiting on approval. 6/13 BBF Rt2 Sec 6 published in IQGEO; Path Creation footage = 6,554'. 5/8/2024 Overlap issues corrected on 4/19 | ATT-7902 | MIN001.G0000185 | 2024-06-12 | 2024-06-12 | 2024-06-24 | 2024-06-24 | [7 empty] | 51 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-07-26
ITG-114062 | 1 | Active | Apr |  | PSA | SFU/MDU | PSA-2601PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 6 | Bloomington | 308 | 305 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-07 | SCOTT | 2024-01-12 |  | 2024-01-25 | YES | 2485 | 1304 | 25153 | 26457 | 85.8994 | 2024-01-30 | 2024-02-12 | 2024-02-14 |  |  | 576 | PFP 10001 PLEASANT AVE S |  | 2024-02-15 | 2024-03-04 | 2024-03-11 |  |  | [4-19-24] V2 | 22977 | Tammi Baker | 2024-04-01 | 2024-04-27 | 2024-04-24 |  |  |  |  | 2024-03-14 | 2024-03-25 | 5 out of 14 | [12 empty] | ATT-7492 | MIN001.G0000037 | 2024-03-07 | 2024-04-16 | 2024-04-22 | 2024-04-23 | [7 empty] | 52 | 1 | 2024 | 1 | 4 | #REF! | 2024-09-27
ITG-114063 | 1 | Active | Apr |  | PSA | SFU | PSA-2602PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 6 | Bloomington | 501 | 515 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-07 | SAM | 2024-01-19 |  | 2024-02-01 | YES | 3266 | 1328 | 48729 | 50057 | 99.9142 | 2024-02-06 | 2024-02-16 | 2024-02-22 |  |  | 864 | PFP 8 104TH ST E |  | 2024-02-23 | 2024-03-13 | 2024-03-14 |  |  | [4-19-24] V2 | 52909 | Jordan Struck | 2024-04-01 | 2024-04-15 | 2024-04-11 | [5 empty] | 2024-04-22 | 9 out of 27 | [11 empty] | 4/11/24 submitted revised design 4/11 sent Jordan updated layout 4/3 - PSA BOUNDARY CHANGE W/ 2701; 3/14 - RECEIVED REVISED LAYOUT; 3/5 - MOVE FORECAST MONTHS IN FROM JUN & AUG TO MAY & JUL | ATT-7493 | MIN001.G0000038 | 2024-03-08 | 2024-04-23 | 2024-04-30 | 2024-05-02 | [7 empty] | 53 | 1 | 2024 | 2 | 5 | #REF! | 2024-09-27
ITG-114064 | 1 | No Build - Ex Comp | May |  | PSA | SFU/MDU | PSA-2603PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 6 | Bloomington | 542 |  |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-07 | SAMUEL | 2024-01-29 |  |  |  | 0 | 0 | 0 | 0 | 0 | [37 empty] | 4/23 Moved to hold for competition in area, On KMZ from Gigapower on Tenielle Email 4/1 - MOVED FORECAST MONTHS OUT FROM JUN & AUG TO AUG & OCT. | ATT-7494 | MIN001.G0000039 | 2024-03-14 | 2024-04-01 | 2024-05-31 | 2024-06-03 | Stop | Stop | Stop | Stop | Stop | Stop |  | 54 | 1 | 1900 | 1 | 0 | #REF! | 2024-09-13
ITG-114068 | 1 | Active | May |  | PSA | SFU | PSA-2604PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 6 | Bloomington | 299 | 299 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-07 | SAM | 2024-02-02 |  | 2024-02-08 | YES | 620 | 1420 | 27615 | 29035 | 97.107 | 2024-02-08 | 2024-02-20 | 2024-02-27 |  |  | 432 | PFP 9937 CHICAGO AVE S |  | 2024-02-27 | 2024-03-13 | 2024-03-08 |  |  | [4-19-24] | 28826 | Eric Lynn | 2024-04-22 | 2024-05-06 | 2024-05-06 | [5 empty] | 2024-04-01 | 13 out of 16 | [11 empty] | 3/5 - MOVE FORECAST MONTHS IN FROM JUN & AUG TO MAY & JUL | ATT-7495 | MIN001.G0000040 | 2024-03-08 | 2024-04-23 | 2024-04-30 | 2024-05-01 | [7 empty] | 55 | 1 | 2024 | 2 | 6 | #REF! | 2024-10-18
ITG-130382 | 1 | Active | May | Nov | BBF | NA | BBF-AT201-RT2-SEC7-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 7 | Bloomington | 638 | 386 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-11 |  |  | NA | NA | NA |  | NA | NA | 5769 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-03-27 | 2024-04-17 | 2024-04-12 | 2024-08-29 | 2024-09-10 | 2024-09-10 | 3306 | Joseph Smith | 2024-06-13 | 2024-06-13 | 2024-06-13 | 2024-07-30 | 2024-08-28 |  |  | 2024-07-30 | 2024-08-02 | [12 empty] | 8/28 REVISIONS COMPLETED IN IQGEO, NEW PATH CREATION FOOTAGE = 3,306'. 7/30 Nate: New CAD dated 7/30 recived and corrections have been made sent over to permiting to amend and Design to update to new CAD. Nate 7/24 Redlines sent to CAD and Design to add overlap from PSA 2701PA. 6/13 BBF Rt2 Sec 7 published in IQGEO; Path Creation footage = 3,307'. 5/8 Overlap issues updated on 4/19 | ATT-7903 | MIN001.G0000186 | 2024-06-21 | 2024-06-25 | 2024-06-25 | 2024-06-25 | [7 empty] | 56 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-07-26
ITG-114069 | 1 | Active | May |  | PSA | SFU/MDU | PSA-2701PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 7 | Bloomington | 513 | 386 |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2023-12-07 | JAEGER | 2024-02-05 |  | 2024-02-09 | YES | 5769 | 115 | 31997 | 32112 | 62.5965 | 2024-02-12 | 2024-02-20 | 2024-03-07 |  |  | 864 | PFP 10361 HARRIET AVE S |  | 3/20/2024 | 2024-05-10 | 2024-05-02 | 2024-07-24 | 2024-09-10 | 2024-09-10 | 19620 | Jordan (Christian) | 2024-04-01 | 2024-04-10 | 2024-04-19 | 2024-07-26 | 2024-08-15 |  |  | 2024-07-30 | 2024-08-02 | 1 out of 14 | [11 empty] | 7/30 Nate approved design and requested permit to be ammended. Nate 7/24 Redlines sent to CAD and Design for corrections and to add overlap from RT2 SEC7. 4/3 - PSA BOUNDARY CHANGE W/ 2602; 4/21 FDH location was moved east out of intersection. 3/5 - MOVE FORECAST MONTHS IN FROM JUN & AUG TO MAY & JUL | ATT-7590 | MIN001.G0000120 | 2024-03-08 | 2024-04-16 | 2024-04-22 | 2024-04-23 | [7 empty] | 57 | 1 | 2024 | 2 | 6 | #REF! | 2024-10-18
ITG-114071 | 1 | Active | Jun |  | PSA | BCL | PSA-2702PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #2 | BBF RTE 2 SEC 7 | Bloomington | 125 |  |  | Darlene White |  | 2023-11-07 | Christian Weller | 2023-12-11 |  |  | 2024-06-11 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | [37 empty] | 9/6 sent an email for this BCL job, only a HH is needed, might be able to combine with PSA-2701. 6/12 fielding not needed, BBF route leading to POF HH was fielded and placed on permit for PSA-2701PA, only a cabinet requireD as buildings are 500' from POF HH. 4/29 Hold for BCL/MDU direction 3/29 - MOVE FORECAST MONTHS OUT FROM PERMITTING JUN & CONSTRUCTION AUG TO PERMITTING SEPT & CONSTRUCTION NOV | ATT-7496 | MIN001.G0000041 | 2024-03-14 | 2024-04-16 | 2024-04-23 | 2024-04-25 | [7 empty] | 58 | 1 & 2 | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-09-20
ITG-130635 | 1 | Active | Jul | Oct | BBF | NA | BBF-AT301-RT3-SEC1-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 1 | Bloomington | 441 | 380 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-06-18 | 2024-06-06 | 2024-06-20 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 12227 | Joseph Smith | 2024-05-13 | 2024-05-16 | 2024-05-16 | 2024-07-22 | 2024-09-09 |  |  | 2024-09-16 | 2024-09-18 | 2 out of 6 | [11 empty] | 9/16 Nate: CAD revisions completed job has moved to permitting. 9/16 Nate: Redlines sent to CAD for minor revisions. 9/9 REVISIONS TO ADD SECTION RUNNING TO SOUTH EAST - NEW PATH CREATION FOOTAGE = 15,302'. 7/29 Path was decided, sync needed with PSA3101 changes 7/25 Nate reached out to Michael to see if Juniors 7/9 revision request was started pending response.7/23 PATH CREATION FOOTAGE = 11,861'. 7/9 Revision required per Junior for overlap. 6/21 sent CAD corrections5/17 CAD revision required at Freeway x-ing. 5/16 BBF Rt3 Sec 1 published in IQGEO; Path Creation footage =11,871'. 5/8 CAD will move all structure placing to PSA 3101, this permit is approved, if no changes good to go per Kaylie NO PERMIT REQ'D FOR THIS JOB 3/27 - MOVED FORECAST MONTHS OUT FROM MAY & JUL TO JUL & SEP | ATT-7904 | MIN001.G0000187 | 2024-05-17 | 2024-05-20 | 2024-05-21 | 2024-05-24 | [6 empty] | Need to double check footage before submitting ms2 - joe just re-validated the footage | 59 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-10-12
ITG-114998 | 1 | Active | Jul |  | PSA | MDU | PSA-3101PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 1 | Bloomington | 441 | 380 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2023-12-07 | SCOTT | 2024-01-12 |  | 2024-02-05 | YES | 0 | 9 | 4947 | 4956 | 11.2381 | 2024-02-12 | 2024-02-20 | 2024-02-27 |  |  | 576 | PFP 1701 W OLD SHAKOPEE RD |  | 2024-05-31 | 2024-06-03 | 2024-06-03 | 2024-07-24 | 2024-08-19 | 2024-08-16 | 3078 | Jordan Struck | 2024-04-04 | 2024-04-19 | 2024-04-12 | 2024-07-10 | 2024-07-10 |  |  | 2024-03-12 | 2024-03-25 | 1 | 2024-03-28 | In Construction | 2024-05-17 | [8 empty] | 5/8 CAD to add BBF structure to this job, if no change to bore footage we are good to go per Kaylie. 3/27 - MOVED FORECAST MONTHS OUT FROM MAY & JUL TO JUL & SEP | ATT-7497 | MIN001.G0000042 | 2024-03-14 | 2024-04-16 | 2024-04-23 | 2024-04-25 | 2024-05-14 | 2024-05-14 | [5 empty] | 60 | 1 & 2 | 2024 | 2 | 6 | Permit Complete | 2025-05-16
ITG-131055 | 1 | Active | Jul | Nov | BBF | NA | BBF-AT301-RT3-SEC2-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 2 | Bloomington | 1868 | 752 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-07-30 | 2024-08-16 | 2024-08-15 |  |  |  | 3733 | Joseph Smith | 2024-09-09 | 2024-09-09 | 2024-09-09 | [18 empty] | 9/9 DESIGN COMPLETED IN IQGEO - PATH CREATION FOOTAGE = 3,733'. Design needs to have HH placed to feed PSA3202 and 3203Overlap? 3/27 - MOVED FORECAST MONTHS OUT FROM MAY & JUL TO JUL & SEP | ATT-7905 | MIN001.G0000188 | 2024-08-08 | 2024-08-15 | 2024-09-24 | 2024-09-25 | [7 empty] | 61 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-10-12
ITG-110395 | 1 | Active | Jul |  | PSA | SFU | PSA-3201PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 2 | Bloomington | 382 | 383 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2023-12-07 | SCOTT | 2024-01-12 |  | 2024-02-08 | YES | 689 | 467 | 32876 | 33343 | 87.2853 | 2024-02-13 | 2024-02-26 | 2024-02-28 |  |  | 576 | PFP 10000 Girard AVE S |  | 2024-06-26 | 2024-07-12 | 2024-06-20 | 2024-08-14 | 2024-08-22 | 2024-08-22 | 32853 | Tammi Baker | 2024-04-04 | 2024-05-15 | 2024-05-29 | [5 empty] | 2024-04-26 | 3 out of 18 | [11 empty] | 8/22 CAD completed overlap issues. 8/14 CAD Revision Req'd to sync with BBF, 6/27 MNDOT coreections complete ready for permit-Kaylie 6/25 CAD returned for corrections Sus & Junior3/27 - MOVED FORECAST MONTHS OUT FROM MAY & JUL TO JUL & SEP | ATT-7514 | MIN001.G0000059 | 2024-03-08 | 2024-04-16 | 2024-04-25 | 2024-04-26 | [7 empty] | 62 | 1 | 2024 | 2 | 6 | #REF! | 2025-05-16
ITG-115404 | 1 | Active | Jul |  | PSA | MDU | PSA-3202PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 2 | Bloomington | 189 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | SEE NOTE | [8 empty] | 0 | 0 | [37 empty] | 9/6 sent email on how to proceed with this job, prvate apartment area with no R/W. 8/8 BBF job will need HH to provide fiber loop for future service 7/23- SERVE FROM BBF 4/29 Hold for BCL/MDU direction 3/27 - MOVED FORECAST MONTHS OUT FROM MAY & JUL TO JUL & SEP; HOA ? - SET HANDHOLES ALONG ARTERIAL ROADS | ATT-7515 | MIN001.G0000060 | 2024-03-14 | 2024-04-16 | 2024-05-15 | 2024-05-17 | [7 empty] | 63 | 1 | 1900 | 1 | 0 | #REF! | 2025-05-16
ITG-114996 | 1 | Active | Jul |  | PSA | MDU | PSA-3203PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 2 | Bloomington | 925 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | SEE NOTE | [8 empty] | 0 | 0 | [37 empty] | 9/6 sent email on how to proceed with this job, prvate apartment area with no R/W. 8/8 BBF job will need HH to provide fiber loop for future service 7/23- SERVE FROM BBF 4/29 Hold for BCL/MDU direction 3/27 - MOVED FORECAST MONTHS OUT FROM MAY & JUL TO JUL & SEP; HOA ? - SET HANDHOLES ALONG ARTERIAL ROADS | ATT-7591 | MIN001.G0000121 | 2024-03-14 | 2024-04-16 | 2024-05-15 | 2024-05-17 | [7 empty] | 64 | 1 | 1900 | 1 | 0 | #REF! | 2025-05-16
ITG-114997 | 1 | Active | Jul |  | PSA | SFU | PSA-3204PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 2 | Bloomington | 372 | 369 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2023-12-07 | JAEGER | 2024-01-24 |  | 2024-02-04 | YES | 0 | 2669 | 29067 | 31736 | 85.3118 | 2024-02-05 | 2024-02-14 | 2024-02-20 |  |  | 576 | PFP 1421 BLISS LN |  | 2024-05-20 | 2024-07-15 | 2024-07-15 |  |  | 2024-07-15 | 30548 | Jordan (Christian) | 2024-04-04 | 2024-05-13 | 2024-04-26 | 2024-07-11 | 2024-07-19 |  |  | 2024-07-16 | 2024-04-26 | 16 | 2024-08-28 | In Construction | 2024-08-28 | [8 empty] | City has approved, sent to const. 7/16 forwarded to Kaylie for permit amendment 7/9 CAD correction sent to Michael for const. placing. 6/25 per City revision req'd out of ROW5/8 sent Cody layout revisions permitting may need update 4/11 Another easement issue from the City 4/10 emailed Cody with design changes per the City.3/27 - MOVED FORECAST MONTHS OUT FROM MAY & JUL TO JUL & SEP | ATT-7516 | MIN001.G0000061 | 2024-03-08 | 2024-04-16 | 2024-04-30 | 2024-05-01 | see note | [5 empty] | Preapproved permits pending | 65 | 1 | 2024 | 2 | 6 | Permit Complete | 2025-05-16
ITG-131058 | 1 | NO BUILD |  |  | BBF | NA | BBF-AT301-RT3-SEC3-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 3 | Bloomington | 378 | 0 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | [7 empty] | 3450 | Joseph Smith | [21 empty] | Overlap? 3/27 - MOVED FORECAST MONTHS IN FROM JUL & SEP TO MAY & JUL | ATT-7906 | MIN001.G0000189 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Project cancel - all footage accounted for on Sec 2 and Sec 4 | 66 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-09-01
ITG-114999 | 1 | No Build - Ex Comp |  |  | PSA | SFU | PSA-3301PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 3 | Bloomington | 378 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-26 | BRIAN | 2024-04-03 | [6 empty] | 0 | 0 | [8 empty] | 2024-02-26 |  | 2024-03-05 | [26 empty] | 4/23 Moved to hold for competition in area 3/27 - MOVED FORECAST MONTHS IN FROM JUL & SEP TO MAY & JUL; 3/6 - SENT RXR CAD TO PERMITTING; 2/26 - RECEIVED RXR CROSSING FN # 854451M - SENT TO MICHAEL FOR CAD; 2/6 - SENT REQUEST TO SCOTT MEISSNER TO FIELD RXR CROSSING | ATT-7525 | MIN001.G0000066 | 2024-03-14 | 2024-04-16 | 2024-04-23 | 2024-04-23 | Stop | Stop | Stop | Stop | Stop | Stop |  | 67 | 1 | 1900 | 1 | 0 | #REF! | 2025-05-16
ITG-130634 | 1 | Active | Jun | Nov | BBF | NA | BBF-AT301-RT3-SEC4-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 4 | Bloomington | 556 | 0 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA | 9811 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-03-29 | 2024-04-15 | 2024-04-10 | 2024-07-30 | 2024-08-12 | 2024-04-04 | 5542 | Joseph Smith | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-09-09 | 2024-09-09 |  |  |  | 2024-04-17 | 1 out of 4 | [11 empty] | 9/9 IQGEO REVISIONS MADE - NEW PATH CREATION FOOTAGE = 5,542'. 7/31 MJ - Revision assigned to Sync with connecting BBFs and PSAs, 6/20 BBF Rt3 Sec 4 published in IQGEO; Path Creation footage = 5,195'. | ATT-7907 | MIN001.G0000190 | 2024-06-21 | 2024-06-24 | 2024-06-28 | 2024-07-19 | [7 empty] | 68 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-09-01
ITG-115405 | 1 | No Build - Ex Comp |  |  | PSA | SFU/MDU | PSA-3401PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 4 | Bloomington | 556 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-26 | SAMUEL | 2024-03-14 |  |  |  | 9811 | 0 | 0 | 0 | 0 | [37 empty] | 4/23 Moved to hold for competition in area, On KMZ from Gigapower on Tenielle Email 4/1 - MOVED FORECAST MONTHS OUT FROM JUN & AUG TO AUG & OCT; 3/17 - MOVED FORECAST MONTHS IN FROM JUL & SEP TO JUN & AUG | ATT-7592 | MIN001.G0000122 | 2024-03-14 | 2024-04-16 | 2024-06-24 | 2024-06-24 | Stop | Stop | Stop | Stop | Stop | Stop |  | 69 | 1 | 1900 | 1 | 0 | #REF! | 2025-05-16
ITG-131056 | 1 | Active | May | Nov | BBF | NA | BBF-AT301-RT3-SEC5-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 5 | Bloomington | 1583 | 1348 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-07-30 | 2024-08-20 | 2024-08-16 |  |  | 2024-08-15 | 5771 | Joseph Smith | 2024-09-09 | 2024-09-09 | 2024-09-09 | [18 empty] | 9/9 DESIGN COMPLETED IN IQGEO - PATH CREATION FOOTAGE = 5,771'. Overlap? 3/27 - MOVED FORECAST MONTHS IN FROM JUL & SEP TO MAY & JUL | ATT-7908 | MIN001.G0000191 | 2024-08-08 | 2024-08-14 | 2024-09-24 | 2024-09-25 | [7 empty] | 70 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-09-01
ITG-115406 | 1 | Active | May |  | PSA | SFU/MDU | PSA-3501PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 5 | Bloomington | 454 | 465 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-26 | SCOTT | 2024-02-27 |  | 2024-03-21 | YES | 0 | 1739 | 27234 | 28973 | 63.8172 | 2024-04-05 | 2024-04-10 | 2024-04-17 |  |  |  | PFP 3900 HERITAGE HILLS DR |  | 2024-04-17 | 2024-05-06 | 2024-05-06 |  |  | 5/6 v2 | 19418 | Cheryl Turk | 2024-04-17 | 2024-05-01 | 2024-04-24 |  |  |  |  | 2024-05-02 | 2024-05-17 | 1 out of 9 | [11 empty] | 5/6 sent Cheryl CAD updates 3/27 - MOVED FORECAST MONTHS IN FROM JUL & SEP TO MAY & JUL | ATT-7526 | MIN001.G0000067 | 2024-03-14 | 2024-04-01 | 2024-04-23 | 2024-04-25 | [7 empty] | 71 | 1 | 2024 | 3 | 12 | #REF! | 2025-05-16
ITG-115407 | 1 | Active | May |  | PSA | SFU | PSA-3502PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 5 | Bloomington | 589 | 587 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 | SAM | 2024-02-08 |  | 2024-02-20 | YES | 0 | 1572 | 61049 | 62621 | 106.3175 | 2024-02-21 | 2024-03-07 | 2024-03-20 |  |  | 864 | PFP 3900 W 100TH ST |  | 2024-03-14 | 2024-03-28 | 2024-04-15 | 2024-08-15 | 2024-08-16 | 2024-08-15 | 60405 | Cheryl Turk | 2024-04-01 | 2024-04-19 | 2024-04-22 | 2024-08-08 | 2024-09-11 |  |  | 2024-04-11 | 2024-04-29 | 1 out of 32 | [11 empty] | 8/8 MJ CAD Updated, Design and Layout Revision Requested 8/6 - MJ Revision Required to Sync with BBF RTE 3 Sec 5 and PSA 3503PA and add HHs and review conduit, 3/27 - MOVED FORECAST MONTHS IN FROM JUL & SEP TO MAY & JUL | ATT-7527 | MIN001.G0000068 | 2024-03-14 | 2024-04-16 | 2024-04-23 | 2024-04-25 | [7 empty] | 72 | 1 | 2024 | 2 | 8 | #REF! | 2025-05-16
ITG-115408 | 1 | Active | Jun |  | PSA | MDU | PSA-3503PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 5 | Bloomington | 387 | 296 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-06-11 | HUNTER | 2024-06-12 | 2024-06-21 | 2024-06-21 | YES | 0 | 569 | 1808 | 2377 | 6.1421 | 2024-07-03 | 2024-07-17 | 2024-07-17 |  |  | 576 | PFP 9901 HARRISON RD |  | 2024-07-25 | 2024-08-14 | 2024-08-09 |  |  |  |  | Jermaine Scott | 2024-07-30 | 2024-08-13 | 2024-08-09 | [18 empty] | 4/29 Hold for BCL/MDU direction 4/1 - REVERTED FORECASTED MONTHS BACK SINCE MDU (KAYLIE/TENILLE CONVO); 3/27 - MOVED FORECAST MONTHS IN FROM JUL & SEP TO MAY & JUL | ATT-7528 | MIN001.G0000069 | 2024-03-14 | 2024-04-16 | 2024-04-23 | 2024-04-25 | [7 empty] | 73 | 1 | 2024 | 6 | 25 | #REF! | 2024-10-25
ITG-131060 | 1 | PROJECT CANCEL |  |  | BBF | NA | BBF-AT301-RT3-SEC6-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 6 | Bloomington | 296 | 0 |  | Joseph Smith |  |  | Joseph Smith |  |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | [7 empty] | 3654 | Joseph Smith | [22 empty] | ATT-7909 | MIN001.G0000192 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Project canceled as no work was done | 74 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-09-01
ITG-119207 | 1 | NO BUILD |  |  | PSA | SFU | PSA-3601PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 6 | Bloomington | 296 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-26 | SCOTT | 2024-02-27 | NA |  |  | 5930 |  |  | 0 | 0 | [37 empty] | 4/26 On KMZ from Gigapower on Tenielle Email, Susan emailed GP for clarification as they have given this PSA as a priority 1 build 4/1 - MOVED FORECAST MONTHS OUT FROM JUN & AUG TO AUG & OCT | ATT-7529 | MIN001.G0000070 | 2024-03-14 | 2024-04-01 | 2024-04-23 | 2024-04-25 | Stop | Stop | Stop | Stop | Stop | Stop |  | 75 | 1 | 1900 | 1 | 0 | #REF! | 2024-10-25
ITG-131062 | 1 | PROJECT CANCEL |  |  | BBF | NA | BBF-AT301-RT3-SEC7-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 7 | Bloomington | 497 | 0 |  | Joseph Smith |  |  | Joseph Smith |  |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | [7 empty] | 3030 | Joseph Smith | [21 empty] | Dependent on build of PSA3701 | ATT-7910 | MIN001.G0000193 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Project canceled as no work was done | 76 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-10-12
ITG-115409 | 1 | No Build - Ex Comp |  |  | PSA | MIX | PSA-3701PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 7 | Bloomington | 497 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 | JACOB | 2024-04-09 | NA | [5 empty] | 0 | 0 | [37 empty] | 4/30 FIELDER FOUND EXISTING COMPETITION AND FIBER TO THE HOME IN THIS JOB AREA 3/17 - MOVED FORECAST MONTHS OUT FROM JUN & AUG TO JUL & SEP. | ATT-7531 | MIN001.G0000071 | 2024-03-14 | 2024-04-01 | 2024-04-23 | 2024-04-25 | Stop | Stop | Stop | Stop | Stop | Stop |  | 77 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-138001 |  | NO BUILD |  |  | PSA | SFU/MDU | PSA-3702PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 7 | Bloomington | 64 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 | [50 empty] | RENAME 3406PA TO 3702PA; 12/19 - PER TED W/ GP NO BUILD DUE TO ALREADY SERVED HOMES FROM NORD DR TO W SHAKOPEE RD & 3 STREETS GOING SOUTH FROM NORD DR. | ATT-8716 | MIN001.G0000350 | 2024-06-26 | Rejected | [8 empty] | Has been cancelled in CMPM | 78 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-131064 | 1 | PROJECT CANCEL |  |  | BBF | NA | BBF-AT301-RT3-SEC8-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 8 | Bloomington | 1772 | 0 |  | Joseph Smith |  |  | Joseph Smith |  |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | [7 empty] | 1955 | Joseph Smith | [22 empty] | ATT-7911 | MIN001.G0000194 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Project canceled as no work was done | 79 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-10-12
ITG-115420 | 1 | NO BUILD |  |  | PSA | SFU | PSA-3801PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 8 | Bloomington | 622 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 | SAM | 2024-04-01 | NA | [5 empty] | 0 | 0 | [37 empty] | 4/26 On KMZ from Gigapower on Tenielle Email, Susan emailed GP for clarification as they have given this PSA as a priority 1 build 4/1 - MOVED FORECAST MONTHS OUT FROM JUN & AUG TO AUG & OCT | ATT-7532 | MIN001.G0000072 | 2024-03-14 | 2024-04-23 | 2024-06-24 | 2024-06-24 | Stop | Stop | Stop | Stop | Stop | Stop |  | 80 | 1 | 1900 | 1 | 0 | #REF! | 2024-10-16
ITG-115422 | 1 | No Build - Ex Comp |  |  | PSA | SFU | PSA-3802PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 8 | Bloomington | 575 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 | CODY | 2024-04-09 | NA | [5 empty] | 0 | 0 | [37 empty] | FIELDER FOUND EXISTING LUMEN FTTH 4/30 | ATT-7533 | MIN001.G0000073 | 2024-03-14 | 2024-04-16 | 2024-06-24 | 2024-06-24 | Stop | Stop | Stop | Stop | Stop | Stop |  | 81 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-115421 | 1 | No Build - Ex Comp |  |  | PSA | SFU | PSA-3803PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 8 | Bloomington | 575 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 |  |  | NA | [5 empty] | 0 | 0 | [37 empty] | FIELDER FOUND EXISTING LUMEN FTTH 4/30 | ATT-7535 | MIN001.G0000074 | 2024-03-14 | 2024-04-16 | 2024-06-24 | 2024-06-24 | Stop | Stop | Stop | Stop | Stop | Stop |  | 82 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-131065 | 1 | PROJECT CANCEL |  |  | BBF | NA | BBF-AT301-RT3-SEC9-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 9 | Bloomington | 529 | 0 |  | Joseph Smith |  |  | Joseph Smith |  |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | [7 empty] | 2194 | Joseph Smith | [22 empty] | ATT-7912 | MIN001.G0000195 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Project canceled as no work was done | 83 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-115417 | 1 | No Build - Ex Comp |  |  | PSA | SFU | PSA-3901PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 9 | Bloomington | 529 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 | ERIK | 2024-04-09 | NA | [5 empty] | 0 | 0 | [37 empty] | FIELDER FOUND EXISTING LUMEN FTTH 4/30 | ATT-7536 | MIN001.G0000075 | 2024-03-14 | 2024-04-16 | 2024-06-24 | 2024-06-24 | Stop | Stop | Stop | Stop | Stop | Stop |  | 84 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-131066 | 1 | PROJECT CANCEL |  |  | BBF | NA | BBF-AT301-RT3-SEC11-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 11 | Bloomington | 894 | 0 |  | Joseph Smith |  |  | Joseph Smith |  |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | [7 empty] | 5857 | Joseph Smith | [22 empty] | ATT-7913 | MIN001.G0000196 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Project canceled as no work was done | 85 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-115419 | 1 | No Build - Ex Comp |  |  | PSA | SFU/MDU | PSA-3111PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 11 | Bloomington | 428 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 | CODY | 2024-04-09 | NA | [5 empty] | 0 | 0 | [37 empty] | 4/30 VERIFIED THERE IS EXISTING LUMEN FIBER TO THE HOME IN THIS JOB AREA | ATT-7498 | MIN001.G0000043 | 2024-03-14 | 2024-04-16 | 2024-04-23 | 2024-04-25 | Stop | Stop | Stop | Stop | Stop | Stop |  | 86 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-115418 | 2 | No Build - Ex Comp |  |  | PSA | SFU | PSA-3112PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 11 | Bloomington | 466 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 |  |  | NA | [5 empty] | 0 | 0 | [37 empty] | 4/30 VERIFIED THERE IS EXISTING LUMEN FIBER TO THE HOME IN THIS JOB AREA | ATT-7499 | MIN001.G0000044 | 2024-03-14 | 2024-04-23 | 2024-04-23 | 2024-04-25 | Stop | Stop | Stop | Stop | Stop | Stop |  | 87 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-131067 | 1 | Active | Jun | Nov | BBF | NA | BBF-AT301-RT3-SEC12-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 12 | Bloomington | 387 | 221 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-07-30 | 2024-08-16 | 2024-08-14 |  |  | 8/14 v2 | 1938 | Joseph Smith | 2024-09-11 | 2024-09-11 | 2024-09-11 | [18 empty] | 9/11 IQGEO DESIGN COMPLETED, NEW PATH CREATION FOOTAGE = 1,938'. | ATT-7914 | MIN001.G0000197 | 2024-09-05 | 2024-09-23 | [9 empty] | 88 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-115416 | 1 | Active | Jun |  | PSA | SFU | PSA-3121PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 12 | Bloomington | 387 | 221 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 | DREW | 2024-04-09 |  | 2024-04-18 | YES | 1942 | 2546 | 18072 | 20618 | 53.2765 | 2024-05-06 | 2024-05-14 | 2024-05-15 |  |  | 576 | PFP 5101 BALMORAL LN |  | 2024-05-24 | 2024-06-14 | 2024-07-01 |  |  | 2024-06-11 | 18391 | Jordan (Christian) | 2024-05-16 | 2024-06-28 | 2024-07-05 | 2024-09-25 | [17 empty] | 6/24 - Moved design DD out - Christian took PTO last week for personal matter and design still has errors to clean up 4/1 - MOVED FORECAST MONTHS IN FROM AUG & OCT TO JUN & AUG; 3/8 - SENT RXR CAD TO PERMITTING; 2/26 - RECEIVED RXR CROSSING FN # 854457D - SENT TO MICHAEL FOR CAD; 2/6 - SENT REQUEST TO SCOTT MEISSNER TO FIELD RXR CROSSING | ATT-7500 | MIN001.G0000045 | 2024-03-14 | 2024-04-16 | 2024-07-11 | 2024-07-19 | [7 empty] | 89 | 1 | 2024 | 4 | 16 | #REF! | 2025-05-16
ITG-131068 | 1 | Active | Jun | Nov | BBF | NA | BBF-AT301-RT3-SEC13-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 13 | Bloomington | 877 | 478 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-07-30 | 2024-08-09 | 2024-08-07 | 2024-08-06 | 2024-08-07 | 2024-08-07 | 2242 | Joseph Smith | 2024-09-11 | 2024-09-11 | 2024-09-11 |  |  |  |  | 2024-09-17 | 2024-09-18 | 1 out of 2 | [11 empty] | 9/17 Nate: Print review complete and sent to permiting. 9/11 IQGEO DESIGN COMPLETED, PATH CREATION FOOTAGE = 2,242'. 4/1 - MOVED FORECAST MONTHS IN FROM AUG & OCT TO JUN & AUG | ATT-7915 | MIN001.G0000198 | 2024-08-08 | 2024-08-14 | 2024-09-06 | 2024-09-23 | [7 empty] | 90 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-115412 | 1 | Active | Jun |  | PSA | SFU | PSA-3131PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 13 | Bloomington | 482 | 478 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 | DREW | 2024-03-17 |  | 2024-03-22 | YES | 4594 | 614 | 50322 | 50936 | 105.6763 | 2024-04-05 | 2024-04-22 | 2024-04-23 | 2024-08-08 | 2024-08-08 | 864 | PFP 5240 W 106TH ST |  | 2024-04-25 | 2024-05-16 | 2024-05-16 | 2024-08-08 | 2024-08-16 | 2024-05-15 | 34499 | James Lugo | 2024-04-23 | 2024-05-13 | 2024-05-02 | 2024-09-11 | 2024-09-11 |  | X | 2024-05-17 | 2024-05-29 | 1 out of 16 | [11 empty] | 5/15 sent redlines back to CAD 3/17 - MOVED FORECAST MONTHS IN FROM AUG & OCT TO JUN & AUG | ATT-7501 | MIN001.G0000046 | 2024-03-14 | 2024-04-23 | 2024-04-24 | 2024-04-25 | [7 empty] | 91 | 1 | 2024 | 3 | 12 | #REF! | 2025-05-16
ITG-115413 | 2 | No Build - Ex Comp |  |  | PSA | SFU | PSA-3132PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 13 | Bloomington | 395 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 | BRIAN | 2024-04-03 | NA | [5 empty] | 0 | 0 | [37 empty] | 4/1 - MOVED FORECAST MONTHS IN FROM AUG & OCT TO JUL & SEP. FIELDER FOUND EXISTING LUMEN FTTH 4/30 | ATT-7502 | MIN001.G0000047 | 2024-03-14 | 2024-04-16 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop |  | 92 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-131069 | 2 | Active | Aug | Nov | BBF | NA | BBF-AT301-RT3-SEC14-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 14 | Bloomington | 1164 | 1148 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-07-30 | 2024-09-20 |  | 2024-09-13 |  |  | 7656 | Joseph Smith | 2024-09-24 |  | 2024-09-25 | [18 empty] | 9/25 DESIGN COMPLETE IN IQGEO - PATH CREATION FOOTAGE = 7,656'. 9/13 missing section north per Joe request. | ATT-7916 | MIN001.G0000199 | 2024-08-08 | 2024-08-14 | 2024-09-26 | [8 empty] | 93 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-115410 | 1 | Active | Aug |  | PSA | BCL/MDU | PSA-3141PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 14 | Bloomington | 698 | 685 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-07-23 | SAM | 2024-07-24 | 2024-08-02 | 2024-08-01 | YES | 0 | 1435 | 1695 | 3130 | 4.4842 | 2024-08-07 | 2024-08-28 | 2024-09-03 |  |  | 864 | PFP 9921 NORMANDALE BLVD |  | 2024-09-05 | 2024-09-13 | 2024-09-11 |  |  | 2024-09-11 | 3167 | James Lugo | 2024-09-04 | 2024-09-11 | 2024-09-09 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7503 | MIN001.G0000048 | 2024-05-01 | 2024-05-01 | 2024-05-14 | 2024-05-14 | [7 empty] | 94 | 1 | 2024 | 8 | 31 | #REF! | 2024-10-16
ITG-115411 | 2 | NO BUILD |  |  | PSA | BCL/MDU | PSA-3142PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 14 | Bloomington | 226 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 | [8 empty] | 0 | 0 | [37 empty] | 6/21 PSA combined with with PSA3141 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7504 | MIN001.G0000049 | 2024-03-14 | 2024-04-16 | 2024-05-15 | 2024-05-17 | Stop | Stop | Stop | Stop | Stop | Stop |  | 95 | 1 | 1900 | 1 | 0 | #REF! | 2024-10-16
ITG-115414 | 2 | Active | Aug |  | PSA | SFU | PSA-3143PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 14 | Bloomington | 456 | 463 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-30 | BRIAN | 2024-04-03 | 2024-04-26 | 2024-04-26 | YES | 0 | 2205 | 38668 | 40873 | 89.6338 | 2024-05-13 | 2024-05-22 | 2024-05-22 |  |  | 864 | PFP 5901 W 102ND ST |  | 2024-05-24 | 2024-06-07 | 2024-06-06 |  |  | 6/6v2 | 38796 | James Lugo | 2024-05-22 | 2024-06-05 | 2024-05-29 | 2024-07-08 | 2024-07-08 | [16 empty] | 7/10/ Junior has reviewed | ATT-7505 | MIN001.G0000050 | 2024-03-14 | 2024-04-16 | 2024-04-30 | 2024-05-02 | [7 empty] | 96 | 1 | 2024 | 4 | 17 | #REF! | 2024-10-16
ITG-159387 | 1 | Active |  |  | PSA | SFU/MDU | PSA-3144PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 3 SEC 14 | Bloomington |  |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-02-07 | HUNTER | 2024-04-10 | 2024-04-17 | 2024-04-18 | YES | 0 | 2933 | 18308 | 21241 | #DIV/0! | 2024-05-01 | 2024-05-10 | 2024-05-10 |  |  | 432 | PFP 4825 W 95 1/2 ST |  | 2024-05-15 | 2024-05-31 | 2024-06-06 | 2024-09-04 | Pend Layout | 2024-06-06 | 18523 | Mark Copeland | 2024-05-10 | 2024-05-24 | 2024-05-26 | 2024-09-04 | [17 empty] | Bloomington RTE 4 SEC 6 is now a NO BUILD due to the existing competition in the area. PSA 4603 will become PSA 3144. | ATT-9306 | MIN001.G0000435 | [11 empty] | 97
ITG-159386 | 2 | Active |  |  | PSA |  | PSA-3145PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 14 | Bloomington |  |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-02-07 | DREW | 2024-04-10 | 2024-04-25 | 2024-04-25 | YES | 0 | 3470 | 18510 | 21980 | #DIV/0! | 2024-05-09 | 2024-05-21 | 2024-05-17 | 2024-09-04 |  | 864 | PFP 9517 ALABAMA CIR |  | 2024-05-29 | 2024-07-16 | 2024-06-12 | 2024-09-04 | Pend Layout | 2024-07-17 | 19965 | Jermaine Scott | 2024-05-17 | 2024-05-31 | 2024-07-12 | 2023-09-04 | Pend Layout | [16 empty] | PSA 4603 will become PSA 3144. | ATT-9307 | MIN001.G0000436 | [11 empty] | 98
ITG-131070 | 2 | Active | Aug | Nov | BBF | NA | BBF-AT301-RT3-SEC15-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 15 | Bloomington | 294 | 288 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-07-30 | 2024-08-16 | 2024-08-15 |  |  |  | 2242 | Joseph Smith | 2024-09-11 | 2024-09-11 | 2024-09-11 | [18 empty] | 9/11 IQGEO DESIGN COMPLETE, NEW PATH CREATION FOOTAGE = 2,242'. | ATT-7917 | MIN001.G0000200 | 2024-08-08 | 2024-08-14 | 2024-09-09 | 2024-09-23 | [7 empty] | 99 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-115415 | 2 | Active | Aug |  | PSA | BCL | PSA-3151PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 15 | Bloomington | 294 | 288 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-07-10 | JACOB | 2024-07-24 | 2024-07-29 | 2024-07-29 | YES | 0 | 6 | 3481 | 3487 | 11.8605 | 2024-08-01 | 2024-08-23 | 2024-08-23 | 2024-08-30 | 2024-09-04 | 432 | PFP 10800 NESBITT AVE S |  | 2024-08-28 | 2024-10-08 | 2024-09-04 |  |  | 2024-04-02 | 210 | Spencer Lynn | 2024-09-04 | 2024-09-18 |  | 2024-09-13 | [17 empty] | 4/29 Hold for BCL/MDU direction 3/6 - SENT RXR CAD TO PERMITTING; 2/26 - RECEIVED RXR CROSSING FN # 854258B - SENT TO MICHAEL FOR CAD; 2/6 - SENT REQUEST TO SCOTT MEISSNER TO FIELD RXR CROSSING | ATT-7506 | MIN001.G0000051 | 2024-03-14 | 2024-04-16 | 2024-05-15 | 2024-05-17 | [7 empty] | 100 | 1 | 2024 | 7 | 31 | #REF! | 2024-10-16
ITG-131071 | 2 | Active | Aug | Nov | BBF | NA | BBF-AT301-RT3-SEC16-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 16 | Bloomington | 1422 | 1118 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-07-30 | 2024-08-16 | 2024-08-14 |  |  | 2024-08-14 | 3940 | Joseph Smith | 2024-09-13 | 2024-09-13 | 2024-09-13 | [18 empty] | 9/13 IQGEO DESIGN COMPLETE, NEW PATH CREATION FOOTAGE = 3,940'. | ATT-7918 | MIN001.G0000201 | 2024-08-08 | 2024-08-14 | 2024-09-09 | 2024-09-23 | [7 empty] | 101 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-115403 | 2 | Active | Aug |  | PSA | BCL/MDU | PSA-3161PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 16 | Bloomington | 275 | 269 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-07-10 | ERIK | 2024-07-24 | 2024-07-28 | 2024-07-28 | YES | 0 | 1613 | 5347 | 6960 | 25.3091 | 2024-07-30 | 2024-08-21 | 2024-08-23 |  |  | 432 | PFP 6900 W 110TH ST |  | 2024-08-27 | 2024-10-08 | 2024-09-23 |  |  | 2024-09-20 | 6111 | Spencer Lynn | 2024-09-04 | 2024-09-18 | 2024-09-13 | 2024-09-25 | [17 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7507 | MIN001.G0000052 | 2024-03-14 | 2024-04-23 | 2024-05-15 | 2024-05-17 | [7 empty] | 102 | 1 | 2024 | 7 | 31 | #REF! | 2024-10-16
ITG-115429 | 2 | Active | Aug |  | PSA | SFU/MDU | PSA-3162PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 16 | Bloomington | 585 | 289 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-26 | CODY | 2024-04-10 | 2024-04-19 | 2024-04-19 | YES | 8500 | 1700 | 30000 | 31700 | 54.188 | 2024-05-02 | 2024-05-13 | 2024-05-09 |  |  | 864 | PFP 10556 LOUISIANA AVE S |  | 2024-05-24 | 2024-07-19 | 2024-06-05 | 2024-09-18 | 2024-09-23 | 2024-09-23 | 23752 | Jermaine Scott | 2024-05-09 | 2024-05-24 | 2024-07-12 | 2024-09-25 | 2024-07-12 |  |  | 2024-09-23 | [13 empty] | 9/23 Nate: Print has been reviewed and approved and sent to permitting. 9/18 Nate: CAD and Layout revisions needed, Sent redlines to CAD and Layout. 7/10 Junior has corrections w/ overlap of PSA 3163. | ATT-7508 | MIN001.G0000053 | 2024-03-14 | 2024-04-16 | 2024-04-30 | 2024-05-02 | [7 empty] | 103 | 1 | 2024 | 4 | 16 | #REF! | 2024-10-16
ITG-115402 | 2 | Active | Aug |  | PSA | BCL/MDU | PSA-3163PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 16 | Bloomington | 562 | 560 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-07-10 | CODY | 2024-07-25 | 2024-07-26 | 2024-07-26 | YES | 0 | 1370 | 2682 | 4052 | 7.21 | 2024-07-30 | 2024-08-21 | 2024-08-23 |  |  | 864 | PFP 10500 HAMPSHIRE AVE S |  | 2024-08-26 | 2024-10-08 | 2024-08-30 |  |  | 2024-08-29 | 3358 | Timothy Miller | 2024-09-04 | 2024-09-11 | 2024-09-06 | 2024-09-25 | [17 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7509 | MIN001.G0000054 | 2024-03-14 | 2024-04-16 | 2024-05-15 | 2024-05-17 | [7 empty] | 104 | 1 | 2024 | 7 | 30 | #REF! | 2024-10-16
ITG-131073 | 2 | Active | Aug | Nov | BBF | NA | BBF-AT301-RT3-SEC17-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 17 | Bloomington | 29 | 446 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-08-16 | 2024-09-20 | 2024-08-21 |  |  | 2024-08-21 | 2759 | Joseph Smith | 2024-09-13 | 2024-09-13 | 2024-09-13 | [18 empty] | 9/13 IQGEO DESIGN COMPLETE, NEW PATH CREATION FOOTAGE = 2,759'. 4/1 - MOVE FORECAST MONTHS FROM PERMITTING AUG & CONSTRUCTION NOV TO PERMITTING AUG & CONSTRUCTION OCT | ATT-7919 | MIN001.G0000202 | 2024-08-08 | 2024-08-14 | 2024-09-09 | 2024-09-23 | [7 empty] | 105 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-115426 | 2 | Active | Aug |  | PSA | BCL | PSA-3171PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 17 | Bloomington | 482 | 446 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-07-10 | JOSH | 2024-07-25 | 2024-08-01 | 2024-08-01 | YES | 0 | 4 | 4896 | 4900 | 10.166 | 2024-08-07 | 2024-08-21 | 2024-08-23 | 2024-08-30 | 2024-09-03 | 576 | PFP 10820 BLOOMINGTON FERRY RD |  | 2024-08-23 | 2024-09-06 | 2024-09-05 |  |  | 2024-09-04 | 4749 | Timothy Miller | 2024-09-04 | 2024-09-18 |  | 2024-09-25 | [17 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7510 | MIN001.G0000055 | 2024-03-14 | 2024-04-16 | 2024-05-15 | 2024-05-17 | [7 empty] | 106 | 1 | 2024 | 8 | 31 | #REF! | 0
ITG-131077 | 2 | PROJECT CANCEL | Aug | Nov | BBF | NA | BBF-AT301-RT3-SEC18-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 18 | Bloomington | 467 | 0 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | [7 empty] | 0 | Joseph Smith | remove? | [18 empty] | ITG-134657 |  | 9/23 Combined with Sec 19 no footage for this section. 4/1 - MOVE FORECAST MONTHS IN FROM PERMITTING AUG & CONSTRUCTION NOV TO PERMITTING AUG & CONSTRUCTION OCT | ATT-7920 | MIN001.G0000203 | 2024-08-08 | 2024-08-14 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Project canceled - no billable footage | 107 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-115425 | 2 | NO BUILD |  |  | PSA | 12 SFU/MDU | PSA-3181PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 18 | Bloomington |  |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-29 | [8 empty] | 0 | #DIV/0! | [37 empty] | 5/6 Hold for BCL/MDU direction 4/1 - MOVE FORECAST MONTHS IN FROM PERMITTING AUG & CONSTRUCTION NOV TO PERMITTING AUG & CONSTRUCTION OCT. 12 +/- SFUs and BCL | ATT-7511 | MIN001.G0000056 | 2024-03-14 | 2024-04-23 | 2024-04-30 | 2024-05-01 | Stop | Stop | Stop | Stop | Stop | Stop |  | 108 | 1 | 1900 | 1 | 0 | #REF! | 2024-10-16
ITG-131078 | 2 | Active | Aug | Nov | BBF | NA | BBF-AT301-RT3-SEC19-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 19 | Bloomington | 977 | 428 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-08-16 | 2024-09-20 | 2024-08-23 |  |  | 2024-08-23 | 1628 | Joseph Smith | 2024-09-13 | 2024-09-13 | 2024-09-13 | [18 empty] | 9/13 IQGEO DESIGN COMPLETE, NEW PATH CREATION FOOTAGE = 1,628'. 4/1 - MOVE FORECAST MONTHS IN FROM PERMITTING SEPT & CONSTRUCTION NOV TO PERMITTING AUG & CONSTRUCTION OCT | ATT-7921 | MIN001.G0000204 | 2024-08-08 | 2024-08-14 | 2024-09-23 | [8 empty] | 109 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-115424 | 2 | Active | Sep |  | PSA | SFU/MDU | PSA-3191PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 19 | Bloomington | 467 | 283 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-29 | HANNAH | 2024-04-16 | 2024-04-27 | 2024-04-27 | YES | 4452 | 90 | 30361 | 30451 | 65.2056 | 2024-07-08 | 2024-07-30 | 2024-07-29 |  |  | 576 | PFP 11160 SUMTER CIR |  | 2024-06-19 | 2024-08-23 | 2024-08-23 |  |  | 2024-08-23 | 24070 | Cheryl Turk | 2024-07-30 | 2024-08-13 | 2024-08-13 | 2024-09-25 | [17 empty] | 4/1 - MOVE FORECAST MONTHS IN FROM PERMITTING SEPT & CONSTRUCTION NOV TO PERMITTING AUG & CONSTRUCTION OCT | ATT-7512 | MIN001.G0000057 | 2024-03-14 | 2024-04-23 | 2024-04-30 | 2024-05-02 | [7 empty] | 110 | 1 | 2024 | 4 | 17 | #REF! | 2024-11-08
ITG-115423 | 2 | Active | Sep |  | PSA | SFU/MDU | PSA-3192PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 19 | Bloomington | 507 | 145 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-29 | JACOB | 2024-04-19 | 2024-04-27 | 2024-04-27 |  | 0 | 3630 | 14879 | 18509 | 36.5069 | 2024-05-16 | 2024-05-23 | 2024-05-24 |  |  | 576 | PFP 7024 KENMARE DR |  | 2024-06-04 | 2024-07-03 | 2024-07-03 | 2024-09-18 |  | 2024-08-23 | 18111 | Jordan Struck | 2024-05-24 | 2024-06-07 | 2024-05-29 | 2024-09-25 | [17 empty] | 9/18 Nate: CAD revisions needed, Sent redlines to CAD. 4/1 - MOVE FORECAST MONTHS IN FROM PERMITTING SEPT & CONSTRUCTION NOV TO PERMITTING AUG & CONSTRUCTION OCT | ATT-7513 | MIN001.G0000058 | 2024-03-14 | 2024-04-16 | 2024-04-30 | 2024-05-02 | [7 empty] | 111 | 1 | 2024 | 4 | 17 | #REF! | 2024-11-08
ITG-131079 | 2 | Active | Sep | Nov | BBF | NA | BBF-AT301-RT3-SEC21-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 21 | Bloomington | 557 | 555 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | YES |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | [7 empty] | 1383 | Joseph Smith | pend CAD | [21 empty] | ATT-7922 | MIN001.G0000205 | 2024-08-08 | 2024-08-14 | 2024-09-09 | 2024-09-20 | [7 empty] | 112 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-115430 | 2 | Active | Sep |  | PSA | SFU | PSA-3211PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 21 | Bloomington | 557 | 555 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-29 | ERIK | 2024-04-22 | 2024-05-06 | 2024-05-06 | YES | 1391 | 2218 | 41487 | 43705 | 78.465 | 2024-05-17 | 2024-06-03 | 2024-05-31 |  |  | 864 | PFP 10567 XYLON RD S |  | 2024-06-06 | 2024-07-05 | 2024-07-09 |  |  | 7/8 v2 |  | Jermaine Scott | 2024-05-31 | 2024-06-14 | 2024-06-05 | [18 empty] | 7/9 ready for CAD review | ATT-7517 | MIN001.G0000062 | 2024-03-14 | 2024-04-16 | 2024-04-30 | 2024-05-02 | [7 empty] | 113 | 1 | 2024 | 5 | 19 | #REF! | 2024-11-08
ITG-131081 | 2 | Active | Sep | Nov | BBF | NA | BBF-AT301-RT3-SEC22-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 22 | Bloomington | 1240 | 944 |  | Joseph Smith |  |  | Joseph Smith | 2023-12-20 |  |  | NA | NA | NA |  | NA | YES |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | [7 empty] | 2145 | Joseph Smith | pend CAD | [21 empty] | ATT-7923 | MIN001.G0000206 | 2024-08-08 | 2024-08-14 | 2024-09-09 | 2024-09-20 | [7 empty] | 114 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-115428 | 2 | Active | Sep |  | PSA | SFU/MDU | PSA-3221PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 22 | Bloomington | 512 | 507 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-29 | HUNTER | 2024-04-22 | 2024-05-02 | 2024-05-02 | YES | 2112 | 274 | 19798 | 20072 | 39.2031 | 2024-05-21 | 2024-05-28 | 2024-05-29 |  |  | 576 | PFP 10166 UTAH AVE S |  | 2024-06-04 | 2024-06-21 | 2024-06-26 |  |  | 2024-06-26 | 18472 | James Lugo | 2024-05-29 | 2024-06-12 | 2024-05-31 | [19 empty] | ATT-7518 | MIN001.G0000063 | 2024-02-14 | 2024-04-16 | 2024-04-30 | 2024-05-02 | [7 empty] | 115 | 1 | 2024 | 5 | 18 | #REF! | 2024-11-08
ITG-115427 | 2 | Active | Sep |  | PSA | MDU | PSA-3222PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 22 | Bloomington | 291 |  |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | SEE NOTE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | [5 empty] | N/A | N/A | [30 empty] | 7/10 - no prefield or fielding needed, all MDU PSA and we will just need to leave a coil in the POF HH that is on the BBF route. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7523 | MIN001.G0000064 | 2024-03-15 | 2024-04-16 | 2024-05-15 | 2024-05-17 | [7 empty] | 116 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-11-08
ITG-115431 | 2 | Active | Sep |  | PSA | SFU/MDU | PSA-3223PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #3 | BBF RTE 3 SEC 22 | Bloomington | 444 | 437 |  | Joseph Smith |  | 2023-11-10 | Christian Weller | 2023-12-20 |  |  | 2024-01-29 | JAEGER | 2024-04-22 | 2024-04-29 | 2024-04-29 | YES | 0 | 1861 | 29558 | 31419 | 70.7635 | 2024-05-24 | 2024-06-04 | 2024-06-05 |  |  | 576 | PFP 8172 W 103RD ST |  | 2024-06-11 | 2024-07-03 | 2024-06-26 |  |  | 6/26 v2 | 26800 | Mark Copeland | 2024-06-06 | 2024-06-25 | 2024-06-25 | [19 empty] | ATT-7524 | MIN001.G0000065 | 2024-03-15 | 2024-04-16 | 2024-04-30 | 2024-05-02 | [7 empty] | 117 | 1 | 2024 | 4 | 18 | #REF! | 2024-11-08
ITG-125993 | 1 | Active | Apr | Oct | BBF | NA | BBF-AT401-RT4-SEC1-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 1 | Bloomington | 966 | 597 |  | Joseph Smith |  |  | Joseph Smith | [8 empty] | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-06-13 | 2024-07-19 | 2024-06-05 | 2024-08-13 | 2024-08-30 | 2024-08-21 |  | Joseph Smith | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-08-05 | 2024-08-14 |  |  | 2024-06-10 | 2024-07-01 | 3 out of 8 | [11 empty] | 8/14 IQGEO Design Rev - New Path Creation Footage =12,202' 7/3 CAD corrections sent w/pending PSA's 4202 & 4101 for final overlap, BlueStar and MNDOT ready to permit.6/21 sent CAD corrections6/05 BBF Rt4 Sec 1 published in IQGEO; Path Creation footage = 14,405'. | ATT-7924 | MIN001.G0000207 | 2024-06-21 | 2024-06-25 | 2024-06-28 | 2024-06-28 | [6 empty] | Need to double check footage before submitting ms2 - joe just re-validated the footage | 118 | 1 | 1900 | 1 | 0 | #REF! | 2024-07-28
ITG-116384 | 1 | No Build - Ex Comp |  |  | PSA | BCL/MDU | PSA-4101PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 1 | Bloomington | 363 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-06-11 | HANNAH | 2024-07-26 | 2024-08-06 | EX COMP |  |  |  |  | 0 | 0 | [37 empty] | 8/5 fielder found existing aerial and UG services all through out the PSA, job to go no build. 7/3 Need field/layout to complete for overlap to BBF RT4 SEC 1. 4/29 Hold for BCL/MDU direction 4/1 - MOVED FORECAST MONTHS OUT FROM MAY & JUL TO AUG & OCT | ATT-7538 | MIN001.G0000076 | 2024-03-15 | 2024-04-16 | 2024-05-15 | 2024-05-17 | Stop | Stop | Stop | Stop | Stop | Stop |  | 119 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | 2024-12-06
ITG-116387 | 1 | Active | Apr |  | PSA | SFU/MDU | PSA-4102PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 1 | Bloomington | 603 | 597 |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-01-29 | SCOTT | 2024-01-30 |  | 2024-02-15 | YES | 0 | 2526 | 54727 | 57253 | 94.9469 | 2024-02-16 | 2024-02-29 | 2024-03-08 |  |  | 864 | PFP 9241 RUSSELL AVE S |  | 2024-03-11 | 2024-05-02 | 2024-04-11 | 2024-09-23 | 2024-09-24 | 2024-09-24 | 52302 | Eric Lynn | 2024-03-27 | 2024-04-11 | 2024-04-22 | 2024-07-26 | 2024-08-30 |  |  |  | 2024-04-17 | 1 out of 24 | [11 empty] | 9/20 City has requested additional changes 9/9 City requested corrections also needs a current engr review. 7/22/24 LAYOUT UPDATED TO ADD SCHOOL 4/22 Pending BBF tie in | ATT-7539 | MIN001.G0000077 | 2024-03-15 | 2024-04-23 | 2024-04-30 | 2024-05-01 | [7 empty] | 120 | 1 | 2024 | 2 | 7 | #REF! | 2025-05-16
ITG-136949 | 1 | Active | Aug | Nov | BBF | NA | BBF-AT401-RT4-SEC2-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 2 | Bloomington | 2214 | 67 |  | Joseph Smith |  |  | Joseph Smith | 2024-01-09 | [7 empty] | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-09-11 | 2024-09-20 | 2024-09-19 |  |  | 2024-09-19 | 5608 | Joseph Smith | [21 empty] | 4/1 - MOVED FORECAST MONTHS OUT FROM MAY & AUG TO AUG & OCT | ATT-7925 | MIN001.G0000208 | [11 empty] | 121 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-116388 | 1 | NO BUILD |  |  | PSA | SFU/MDU | PSA-4201PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 2 | Bloomington | 497 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-01-29 | JAEGER | 2024-01-31 | NA | [5 empty] | 0 | 0 | [38 empty] | ATT-7545 | MIN001.G0000082 | 2024-03-15 | 2024-04-23 | 2024-05-21 | 2024-05-22 | Stop | Stop | Stop | Stop | Stop | Stop |  | 122 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-116389 | 1 | Active | Oct |  | PSA | 6 SFU/BCL | PSA-4202PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 2 | Bloomington | 63 | 67 |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-06-11 | SAM | 2024-07-26 | 2024-07-31 | 2024-07-31 | YES | 3512 | 5 | 2384 | 2389 | 37.9206 | 2024-08-05 | 2024-08-20 | 2024-08-13 | 2024-08-27 | 2024-09-03 | 288 | PFP 8900 PENN AVE S |  | 2024-08-14 | 2024-08-27 | 2024-08-30 |  |  | 2024-08-21 | 1463 | Cheryl Turk | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-09-03 | [17 empty] | 7/3 Need field/layout to complete for overlap to BBF RT4 SEC 1. 4/1 - MOVED FORECAST MONTHS OUT FROM MAY & JUL TO AUG & OCT. 6 +/- SFUs and BCL | ATT-7546 | MIN001.G0000083 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-14 | [7 empty] | 123 | 1 | 2024 | 7 | 31 | #REF! | 2024-12-06
ITG-116390 | 1 | No Build - Ex Comp |  |  | PSA | SFU | PSA-4203PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 2 | Bloomington | 316 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-01-29 | SAM | 2024-02-08 | NA |  |  | 5815 |  |  | 0 | 0 | [37 empty] | 2/8Fielder noted aerial const throughout the PSA | ATT-7547 | MIN001.G0000084 | 2024-03-15 | 2024-04-23 | 2024-05-21 | 2024-05-22 | Stop | Stop | Stop | Stop | Stop | Stop |  | 124 | 1 | 1900 | 1 | 0 | #REF! | 2024-12-06
ITG-116391 | 1 | No Build - Ex Comp |  |  | PSA | SFU/BCL | PSA-4204PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 2 | Bloomington | 373 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-01-29 | SAM | 2024-02-08 | NA | [5 empty] | 0 | 0 | [37 empty] | 2/9 Existing fiber has been placed per Samuel/Tenille | ATT-7548 | MIN001.G0000085 | 2024-03-15 | 2024-04-23 | 2024-05-21 | 2024-05-22 | Stop | Stop | Stop | Stop | Stop | Stop |  | 125 | 1 | 1900 | 1 | 0 | #REF! | 2024-12-06
ITG-116394 | 1 | Active |  |  | PSA | BCL | PSA-4205PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 2 | Bloomington | 2 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-06-11 | JOSH | 2024-07-26 | 2024-08-12 | NO BUILD? |  |  |  |  | 0 | 0 | [37 empty] | 8/9 pending response to build this job or not, its BCLs that have fiber service already and PSA is surrounded by ex competition. 4/29 Hold for BCL/MDU direction 4/1 - MOVED FORECAST MONTHS OUT FROM MAY & AUG TO SEP & NOV | ATT-7549 | MIN001.G0000086 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-14 | [7 empty] | 126 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | 0
ITG-138003 |  | No Build - Ex Comp |  |  | PSA | SFU/MDU | PSA-4206PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 2 | Bloomington | 604 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 | [50 empty] | No Build - competition | ATT-8508 | MIN001.G0000344 | 2024-05-29 | 2024-05-29 | 2024-06-12 | 2024-06-12 | Stop | Stop | Stop | Stop | Stop | Stop |  | 127 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-116399 | 3 | Active |  |  | PSA | BCL/MDU | PSA-4207PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 2 | Bloomington | 598 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-07-22 | CODY | 2024-07-26 | 2024-08-08 | 2024-08-08 | YES | 0 | 2638 | 6774 | 9412 | 15.7391 | 2024-08-13 | 2024-09-25 | [7 empty] | 2024-10-04 | [27 empty] | 4/3 - PER ANGELA PAUSE ON BUILD; 4/1 - MOVED FORECAST MONTHS OUT FROM MAY & AUG TO SEP & NOV | ATT-7550 | MIN001.G0000087 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-14 | [7 empty] | 128 | 1 | 2024 | 8 | 32 | #REF! | 2025-06-13
ITG-116400 | 3 | Active |  |  | PSA | BCL | PSA-4208PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 2 | Bloomington | 365 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-07-22 | HOLD | [7 empty] | 0 | 0 | [37 empty] | 8/27 waiting on response to continue and field or not if this section is viable. 8/9 pending response to build this job or not, its BCLs that have fiber service already and PSA is surrounded by ex competition 5/10 Moved back to active 4/3 - PER ANGELA PAUSE ON BUILD; | ATT-7551 | MIN001.G0000088 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-14 | [7 empty] | 129 | 1 | 1900 | 1 | 0 | #REF! | 2025-06-13
ITG-136950 | 2 | Active | Jun |  | BBF | NA | BBF-AT401-RT4-SEC3-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 3 | Bloomington | 10 | 9 |  | Joseph Smith |  |  | Joseph Smith | 2024-01-09 | [7 empty] | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-08-14 | 2024-08-27 | 2024-08-30 | 2024-09-18 |  | 2024-08-21 | 2228 | Joseph Smith | 2024-08-01 | 2024-08-01 | 2024-08-14 | [18 empty] | 9/18 Nate: CAD revisions needed, Sent redlines to CAD. 8/14 - THIS SECTION HAS BEEN BUILT INTO IQGEO. BOM AND FIBER TRACE REPORT IN SHARE DRIVE. PATH CREATION FOOTAGE = 2,228'. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7926 | MIN001.G0000209 | 2024-08-16 | 2024-08-19 | 2024-09-09 | 2024-09-20 | [7 empty] | 130 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-116404 | 2 | Active |  |  | PSA | BCL | PSA-4301PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 3 | Bloomington | 10 | 9 |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-07-22 | HUNTER | 2024-07-26 | 2024-07-30 | 2024-07-30 | YES | 0 | 4735 | 8855 | 13590 | 1359 | 2024-08-01 | 2024-08-16 | 2024-08-21 | 2024-08-28 | 2024-08-28 | 288 | PFP 9700 FRANCE AVE S |  | 2024-08-22 | 2024-10-08 | 2024-09-19 |  |  | 2024-09-19 | 9087 | Jordan Struck | 2024-08-30 | 2024-09-13 | 2024-09-03 | [18 empty] | 7/23 PSA4302 and 4401 merged into this PSA 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7553 | MIN001.G0000089 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-14 | [7 empty] | 131 | 1 | 2024 | 7 | 31 | #REF! | 0
ITG-116405 | 2 | NO BUILD |  |  | PSA | BCL | PSA-4302PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 3 | Bloomington |  |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 | [11 empty] | 0 | #DIV/0! | [37 empty] | 7/22 CANCEL - MOVE INTO 4301 BOUNDARY 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7554 | MIN001.G0000090 | 2024-05-14 | 2024-05-14 | 2024-05-17 | 2024-05-17 | Stop | Stop | Stop | Stop | Stop | Stop |  | 132 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-136951 | 2 | Active | Jun |  | BBF | NA | BBF-AT401-RT4-SEC4-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 4 | Bloomington | 999 | 0 |  | Joseph Smith |  |  | Joseph Smith | 2024-01-09 | [7 empty] | NA |  | NA | NA | NA | NA |  | NA | NA |  |  | NA | NA |  | 2024-08-23 | 2024-09-23 | [5 empty] | Joseph Smith | 2024-08-22 | 2024-08-22 | [19 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7927 | MIN001.G0000210 | [11 empty] | 133 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-116407 | 2 | NO BUILD |  |  | PSA | BCL | PSA-4401PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 4 | Bloomington |  |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 | [11 empty] | 0 | #DIV/0! | [37 empty] | 7/22 CANCEL - MOVE INTO 4301 BOUNDARY 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7555 | MIN001.G0000091 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-14 | Stop | Stop | Stop | Stop | Stop | Stop |  | 134 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-116406 | 1 | NO BUILD |  |  | PSA | SFU | PSA-4402PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 4 | Bloomington | 434 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-01-29 | SAM | 2024-02-08 | NA | [5 empty] | 0 | 0 | [37 empty] | No Build per Gigapower KMZ sent in Tenielle Email | ATT-7557 | MIN001.G0000092 | 2024-03-15 | 2024-04-16 | 2024-05-21 | 2024-05-22 | Stop | Stop | Stop | Stop | Stop | Stop |  | 135 | 1 | 1900 | 1 | 0 | #REF! | 2025-07-16
ITG-138009 |  | NO BUILD |  |  | PSA |  | PSA-4403PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 4 | Bloomington | [58 empty] | No Build per Gigapower KMZ sent in Tenielle Email | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 136 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-116409 | 1 | No Build - Ex Comp |  |  | PSA | SFU/MDU | PSA-4404PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 4 | Bloomington | 510 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-02-07 | JAEGER | 2024-05-08 | 2024-05-13 | 2024-05-13 | NA | 24664 | 0 | 0 | 0 | 0 | [37 empty] | FIELDER REPORTED EXISTING LUMEN COMPETITION IN THIS JOBS AREA, BBF ROUTE WAS FIELDED 5/17. | ATT-7558 | MIN001.G0000093 | 2024-03-15 | 2024-04-16 | 2024-05-31 | 2024-06-03 | ? | [5 empty] | Fielding complete, which MS do we want to bill through? | 137 | 1 | 2024 | 5 | 20 | #REF! | 0
ITG-138012 |  | No Build - Ex Comp |  |  | PSA |  | PSA-4405PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 4 | Bloomington | 516 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 | [50 empty] | No Build - competition | ATT-8510 | MIN001.G0000346 | 2024-05-29 | 2024-06-03 | 2024-06-11 | 2024-06-11 | Stop | Stop | Stop | Stop | Stop | Stop |  | 138 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-116410 |  | NO BUILD | Jun |  | PSA | BCL | PSA-4406PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 4 | Bloomington | 52 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 | [11 empty] | 0 | 0 | [37 empty] | 4/3 - PER TED DEHN - NO BUILD - North of 494 | ATT-7559 | MIN001.G0000094 | 2024-03-15 | 2024-04-25 | 2024-05-21 | 2024-05-21 | Stop | Stop | Stop | Stop | Stop | Stop |  | 139 | 1 | 1900 | 1 | 0 | #REF! | 2028-12-31
ITG-137038 | 2 | Active | Jul |  | BBF | NA | BBF-AT401-RT4-SEC5-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 5 | Bloomington | 349 | 751 |  | Joseph Smith |  |  | Joseph Smith | 2024-01-09 | [7 empty] | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-08-23 | 2024-09-27 | [5 empty] | Joseph Smith | [21 empty] | 5/10 Moved back to active4/29 Hold for BCL/MDU direction | ATT-7929 | MIN001.G0000212 | [11 empty] | 140 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-116411 | 2 | Active |  |  | PSA | BCL | PSA-4501PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 5 | Bloomington | 5 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | SEE NOTE | [8 empty] | 0 | 0 | [37 empty] | 9/19 email sent for direction on how to continue with PSA, a few BCLS and all surrounding PSAs ar no build, email sent to team. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. SERVE FROM BBF | ATT-7560 | MIN001.G0000095 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-14 | [7 empty] | 141 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-138014 |  | NO BUILD |  |  | PSA |  | PSA-4502PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 5 | Bloomington | [58 empty] | No Build per Gigapower KMZ sent in Tenielle Email | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 142 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-138015 |  | NO BUILD |  |  | PSA |  | PSA-4503PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 5 | Bloomington | [58 empty] | No Build per Gigapower KMZ sent in Tenielle Email | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 143 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-116413 | 2 | Active |  |  | PSA | BCL | PSA-4504PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 5 | Bloomington | 2 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | SEE NOTE | [8 empty] | 0 | 0 | [37 empty] | 9/19 email sent for direction on how to continue with PSA, a few BCLS and all surrounding PSAs ar no build, email sent to team. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. SERVE FROM BBF | ATT-7561 | MIN001.G0000096 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-14 | [7 empty] | 144 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-116412 | 2 | No Build - Ex Comp |  |  | PSA | SFU | PSA-4505PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 5 | Bloomington | 23 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 | [11 empty] | 0 | 0 | [37 empty] | MARKED AS NO BUILD ON EXISTING COMPETITION KMZ | ATT-7563 | MIN001.G0000097 | 2024-03-15 | 2024-04-16 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop |  | 145 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-116415 | 3 | Active |  |  | PSA | BCL/MDU | PSA-4506PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 5 | Bloomington | 319 | 751 |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-07-22 | ERIK | 2024-07-26 | 2024-08-06 | 2024-07-30 | YES | 0 | 1063 | 7339 | 8402 | 26.3386 | 2024-08-01 | 2024-08-16 | 2024-08-21 |  |  | 864 | PFP 8201 STANLEY RD |  | 2024-08-22 | 2024-10-08 | 2024-08-28 |  |  | 2024-08-28 | 6696 | Jordan Struck | 2024-08-30 | 2024-09-13 | 2024-09-03 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7564 | MIN001.G0000098 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-14 | [7 empty] | 146 | 1 | 2024 | 7 | 31 | #REF! | 2025-06-13
ITG-136952 | 1 | NO BUILD | Jul |  | BBF | NA | BBF-AT401-RT4-SEC6-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 6 | Bloomington | 2028 | 551 |  | Joseph Smith |  |  | Joseph Smith | 2024-01-09 | [7 empty] | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-08-23 | 2024-09-13 | [5 empty] | Joseph Smith | [21 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7930 | MIN001.G0000213 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 147 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-116417 | 2 | NO BUILD |  |  | PSA | SFU | PSA-4601PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 6 | Bloomington | 533 | 198 |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-02-07 | DREW | 2024-04-10 | 2024-04-25 | 2024-04-25 | YES | 0 | 3470 | 18510 | 21980 | 41.2383 | 2024-05-09 | 2024-05-21 | 2024-05-17 |  |  | 864 | PFP 9517 ALABAMA CIR |  | 2024-05-29 | 2024-07-16 | 2024-06-12 | 2024-07-10 | 2024-07-17 | 2024-07-17 | 19965 | Jermaine Scott | 2024-05-17 | 2024-05-31 | 2024-07-12 | 2024-07-10 | 2024-07-10 | [16 empty] | 9/4/24 Meerged with PSA 4605 and moved into RTE3, Now PSA 3145. 7/10/24 LAYOUT UPDATED TO ADD 2 LU FROM PSA4602 | ATT-7565 | MIN001.G0000099 | 2024-03-15 | 2024-04-23 | 2024-05-09 | 2024-05-09 | STOP | STOP | STOP | STOP | STOP | STOP |  | 148 | 1 | 2024 | 4 | 17 | #REF! | 2025-04-15
ITG-116419 | 2 | NO BUILD |  |  | PSA | BCL | PSA-4602PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 6 | Bloomington |  |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 | [11 empty] | 0 | #DIV/0! | [37 empty] | 7/10 job to be cancelled and combined with PSA-4601. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. SERVE FROM BBF | ATT-7566 | MIN001.G0000100 | 2024-03-15 | 2024-04-23 | 2024-05-14 | 2024-05-14 | Stop | Stop | Stop | Stop | Stop | Stop |  | 149 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-116416 | 1 | NO BUILD |  |  | PSA | SFU/MDU | PSA-4603PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 6 | Bloomington | 437 | 353 |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-02-07 | HUNTER | 2024-04-10 | 2024-04-17 | 2024-04-18 | YES | 0 | 2933 | 18308 | 21241 | 48.6064 | 2024-05-01 | 2024-05-10 | 2024-05-10 |  |  | 432 | PFP 4825 W 95 1/2 ST |  | 2024-05-15 | 2024-05-31 | 2024-06-06 |  |  | 2024-06-06 | 18523 | Mark Copeland | 2024-05-10 | 2024-05-24 | 2024-05-26 | [18 empty] | 9/3/24 PSA merged with PSA4601 and moved to Rte 3, now PSA3145. 7/10 Junior has reviewed | ATT-7567 | MIN001.G0000101 | 2024-03-15 | 2024-04-01 | 2024-05-06 | 2024-05-06 | ? | [5 empty] | Design and CAD complete, which MS do we want to bill through? | 150 | 1 | 2024 | 4 | 16 | #REF! | 2024-12-06
ITG-116418 | 1 | No build - Ex Comp |  |  | PSA | SFU/MDU | PSA-4604PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 6 | Bloomington | 569 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  |  | JACOB | 2024-04-10 | NA | [5 empty] | 0 | 0 | [37 empty] | 5/21 Per Gigapower now a no build - Intrepid now has more than half the job construction completed 5/14 Per Gigapower this is an active build 4/10 FIELDER FOUND FRESH LOCATES ON THE GROUND FOR INTREPID. Fielder confirming if constuction has started by Intrepid 5/20. | ATT-7568 | MIN001.G0000102 | 2024-03-15 | 2024-04-23 | 2024-05-15 | 2024-05-17 | Stop | Stop | Stop | Stop | Stop | Stop |  | 151 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-116420 | 2 | NO BUILD |  |  | PSA | BCL | PSA-4605PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 6 | Bloomington | 2 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | N/A | [8 empty] | 0 | 0 | [37 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. SERVE FROM BBF | ATT-7569 | MIN001.G0000103 | 2024-03-15 | 2024-04-23 | 2024-05-14 | 2024-05-14 | Stop | Stop | Stop | Stop | Stop | Stop |  | 152 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-116421 | 2 | No Build - Ex Comp |  |  | PSA | SFU | PSA-4606PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 6 | Bloomington | 485 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-02-07 | BRIAN | 2024-04-10 | 2024-05-06 | NA |  |  |  |  | 0 | 0 | [37 empty] | FIELDER HAS FOUND EXISTING FIBER TO THE HOME IN THIS JOBS AREA, FIELDING WILL NOT BE COMPLETED 5/6 JR. | ATT-7583 | MIN001.G0000117 | 2024-03-15 | 2024-04-23 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop |  | 153 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | 0
ITG-136953 | 3 | Active | Aug |  | BBF | NA | BBF-AT401-RT4-SEC7-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 7 | Bloomington | 732 | 0 |  | Joseph Smith |  |  | Joseph Smith | 2024-01-09 | [7 empty] | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-08-26 | 2024-09-13 | 2024-09-06 |  |  | 2024-09-06 |  | Joseph Smith | [21 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7931 | MIN001.G0000214 | [11 empty] | 154 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-115433 | 3 | Active |  |  | PSA | BCL/MDU | PSA-4702PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 7 | Bloomington | 581 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-07-23 | JOSH | 2024-07-26 | 2024-08-09 | NO BUILD? |  |  |  |  | 0 | 0 | [37 empty] | 9/19 possible no build due to ex competition, sent email to team. 7/23 PSA4703 is now merged into this PSA 4/3 - PER ANGELA PAUSE ON BUILD; | ATT-7570 | MIN001.G0000104 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-14 | [7 empty] | 155 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | 2025-06-13
ITG-115434 | 3 | NO BUILD |  |  | PSA | SFU/MDU | PSA-4703PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 7 | Bloomington |  |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 | [11 empty] | 0 | #DIV/0! | [37 empty] | 7/23 PSA combined into PSA4702 4/3 - PER ANGELA PAUSE ON BUILD; | ATT-7571 | MIN001.G0000105 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-24 | Stop | Stop | Stop | Stop | Stop | Stop |  | 156 | 1 | 1900 | 1 | 0 | #REF! | 2025-06-13
ITG-115435 |  | NO BUILD | Sep |  | PSA | BCL | PSA-4704PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 7 | Bloomington | 65 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-02-07 | [8 empty] | 0 | 0 | [37 empty] | 4/3 - PER TED DEHN - NO BUILD - North of 494 | ATT-7572 | MIN001.G0000106 | 2024-03-15 | 2024-04-25 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 157 | 1 | 1900 | 1 | 0 | #REF! | 2028-12-31
ITG-115436 |  | NO BUILD | Sep |  | PSA | BCL | PSA-4705PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 7 | Bloomington | 20 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-02-07 | [8 empty] | 0 | 0 | [37 empty] | 4/3 - PER TED DEHN - NO BUILD - North of 494 | ATT-7573 | MIN001.G0000107 | 2024-03-15 | 2024-04-25 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 158 | 1 | 1900 | 1 | 0 | #REF! | 2028-12-31
ITG-115437 |  | NO BUILD | Aug |  | PSA | BCL | PSA-4706PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 7 | Bloomington | 61 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-02-07 | [8 empty] | 0 | 0 | [37 empty] | 4/3 - PER TED DEHN - NO BUILD - North of 494 | ATT-7574 | MIN001.G0000108 | 2024-03-15 | 2024-04-25 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 159 | 1 | 1900 | 1 | 0 | #REF! | 2028-12-31
ITG-115438 | 3 | NO BUILD |  |  | PSA | BCL | PSA-4707PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 7 | Bloomington | 5 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 | [11 empty] | 0 | 0 | [37 empty] | 4/3 - PER TED DEHN - NO BUILD; 3/6 - SENT RXR CAD TO PERMITTING; 2/26 - RECEIVED RXR CROSSING FN # 854256M - SENT TO MICHAEL FOR CAD; 2/6 - SENT REQUEST TO SCOTT MEISSNER TO FIELD RXR CROSSING | ATT-7575 | MIN001.G0000109 | 2024-03-15 | 2024-04-16 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 160 | 1 | 1900 | 1 | 0 | #REF! | 2025-06-13
ITG-136954 | 2 | Active | Aug |  | BBF | NA | BBF-AT401-RT4-SEC8-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 8 | Bloomington | 1706 | 782 |  | Joseph Smith |  |  | Joseph Smith | 2024-01-09 | [7 empty] | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-06-19 | 2024-07-12 | 2024-07-12 | 2024-08-08 | 2024-08-09 | 2024-08-09 |  | Joseph Smith | [7 empty] | 2024-09-17 | 2024-09-19 | [12 empty] | 9/17 Nate: Print has been reviewed and approved and sent to permitting. 8/9 BBF updated w/PSA overlap by Jeffrey5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7932 | MIN001.G0000215 | [11 empty] | 161 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-115439 | 2 | Active |  |  | PSA | SFU/MDU | PSA-4801PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 8 | Bloomington | 486 | 420 |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-02-08 | JAEGER | 2024-04-25 | 2024-05-06 | 2024-05-06 | YES | 9845 | 147 | 26108 | 26255 | 54.0226 | 2024-07-03 | 2024-07-19 | 2024-07-21 | 2024-08-15 | 2024-08-23 | 864 | PFP 7310 AUTUMN CHACE DR |  | 2024-07-24 | 2024-08-23 | 2024-08-19 |  |  | 2024-08-19 | 13693 | James Lugo | 2024-07-26 | 2024-08-09 | 2024-07-30 | 2024-08-23 | 2024-08-26 | [16 empty] | 8/15 Layout changes requested to match CAD, Design will need to update when CAD is complete 5/15 split PSA added PSA 4808 | ATT-7576 | MIN001.G0000110 | 2024-03-15 | 2024-04-23 | 2024-05-09 | 2024-05-09 | [7 empty] | 162 | 1 | 2024 | 5 | 19 | #REF! | 2025-04-15
ITG-115440 | 2 | Active |  |  | PSA | SFU | PSA-4802PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 8 | Bloomington | 429 | 308 |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-04-25 | SAM | 2024-04-26 | 2024-05-02 | 2024-05-02 | YES | 0 | 5 | 31995 | 32000 | 74.5921 | 2024-06-28 | 2024-07-30 | 2024-07-30 |  |  | 864 | PFP 8170 PENNSYLVANIA RD |  | 2024-07-30 | 2024-08-09 | 2024-08-09 |  |  | 2024-08-09 | 26123 | Jordan Struck | 2024-07-30 | 2024-08-13 | 2024-08-14 | [19 empty] | ATT-7577 | MIN001.G0000111 | 2024-03-15 | 2024-04-23 | 2024-05-09 | 2024-05-09 | [7 empty] | 163 | 1 | 2024 | 5 | 18 | #REF! | 2025-04-15
ITG-116366 | 2 | Active |  |  | PSA | SFU/MDU | PSA-4803PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 8 | Bloomington | 72 | 54 |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-04-26 | HANNAH | 2024-04-26 | 2024-04-29 | 2024-04-29 | YES | 0 | 45 | 4590 | 4635 | 64.375 | 2024-07-01 | 2024-07-19 | 2024-07-21 |  |  | 144 | PFP 8131 TIERNEYS WOODS CURVE |  | 2024-07-25 | 2024-08-16 | 2024-08-16 |  |  | 2024-08-16 | 4310 | Cheryl Turk | 2024-08-20 | 2024-08-30 | 2024-09-04 | [18 empty] | 5/8 Henry proposes to split the DA, Aubre to make the change. | ATT-7578 | MIN001.G0000112 | 2024-03-15 | 2024-04-16 | 2024-05-09 | 2024-05-09 | [7 empty] | 164 | 1 | 2024 | 4 | 18 | #REF! | 2024-11-27
ITG-115432 | 2 | Active |  |  | PSA | MDU | PSA-4804PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 8 | Bloomington | 512 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | SEE NOTE | [8 empty] | 0 | 0 | [37 empty] | 9/19 job is an all MDU, could combine with PSA-4803, sent email to team. 4/29 Hold for BCL/MDU direction. SERVE FROM BBF | ATT-7579 | MIN001.G0000113 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-17 | [7 empty] | 165 | 1 | 1900 | 1 | 0 | #REF! | 2025-04-15
ITG-115441 |  | PROJECT CANCEL | Aug |  | PSA | SFU | PSA-4806PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 8 | Bloomington |  |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-02-07 | [8 empty] | 0 | #DIV/0! | [37 empty] | 7/2 combining job area with Eden Prairie PSA-1201. No build - connect off or add to PSA1201-Eden Prairie rather than bore under the freeway | ATT-7580 | MIN001.G0000114 | 2024-03-15 | 2024-04-25 | 2024-06-27 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Project cancel - area merged to another psa | 166 |  | 1900 | 1 | 0 | #REF! | 2025-07-16
ITG-116367 |  | PROJECT CANCEL | Aug |  | PSA | BCL | PSA-4807PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 8 | Bloomington | 28 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-02-07 | [8 empty] | 0 | 0 | [37 empty] | 7/2 combining job area with Eden Prairie PSA-1103. 4/3 - PER TED DEHN - NO BUILD - empty buildings north of 494 | ATT-7581 | MIN001.G0000115 | 2024-03-15 | 2024-04-25 | 2024-06-27 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Project cancel - area merged to another psa | 167 |  | 1900 | 1 | 0 | #REF! | 2028-12-31
ITG-137272 |  | Active |  |  | PSA | SFU | PSA-4808PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 8 | Bloomington | 146 | 146 | [8 empty] | 2024-07-23 | JACOB | 2024-07-26 | 2024-08-05 | 2024-07-31 | YES | 0 | 570 | 16440 | 17010 |  | 2024-08-01 | 2024-08-16 | 2024-08-21 |  |  | 288 | PFP 8500 PARK KNOLL CIR |  | 2024-08-21 | 2024-09-06 | 2024-08-30 |  |  | 2024-08-30 | 13103 | Jermaine Scott | 2024-08-30 | 2024-09-13 | 2024-09-04 | [18 empty] | 5/15 split PSA 4801 added PSA 4808 | ATT-8493 | MIN001.G0000342 | 2024-05-21 | 2024-05-21 | 2024-05-31 | 2024-06-03 | [7 empty] | 168 | 1 |  |  |  | #REF! | #N/A
ITG-136955 | 2 | Active | Sep |  | BBF | NA | BBF-AT401-RT4-SEC9-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 9 | Bloomington | 312 | 300 |  | Joseph Smith |  |  | Joseph Smith | 2024-01-09 | [7 empty] | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-08-26 | 2024-09-18 | 2024-09-09 |  |  | 2024-09-04 |  | Joseph Smith | [21 empty] | 4/29 Hold for BCL/MDU direction | ATT-7933 | MIN001.G0000216 | [11 empty] | 169 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-116375 | 2 | Active |  |  | PSA | SFU | PSA-4901PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 9 | Bloomington | 312 | 300 |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-04-26 | JACOB | 2024-04-26 | 2024-05-05 | 2024-05-05 | YES | 6328 | 6 | 36360 | 36366 | 116.5577 | 2024-06-13 | 2024-07-03 | 2024-07-03 |  |  | 432 | PFP 8601 LAKEVIEW RD |  | 2024-07-09 | 2024-08-02 | 2024-07-25 |  |  | 2024-07-24 | 24187 | Eric Lynn | 2024-07-05 | 2024-07-23 | 2024-07-24 | [19 empty] | ATT-7582 | MIN001.G0000116 | 2024-03-15 | 2024-04-23 | 2024-05-09 | 2024-05-09 | [7 empty] | 170 | 1 | 2024 | 5 | 19 | #REF! | 2025-04-15
ITG-136956 | 2 | Active | Aug |  | BBF | NA | BBF-AT401-RT4-SEC11-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 11 | Bloomington | 782 | 729 |  | Joseph Smith |  |  | Joseph Smith | 2024-01-09 | [7 empty] | NA |  | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-08-26 | 2024-09-20 | [5 empty] | Joseph Smith | [21 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7934 | MIN001.G0000217 | [11 empty] | 171 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-116380 | 2 | Active |  |  | PSA | SFU | PSA-4111PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 11 | Bloomington | 246 | 239 |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-04-26 | JOSH | 2024-04-26 | 2024-05-02 | 2024-05-02 | YES | 0 | 1450 | 9962 | 11412 | 46.3902 | 2024-05-23 | 2024-06-03 | 2024-06-03 |  |  | 432 | PFP 9428 WOODBRIDGE RD |  | 2024-06-06 | 2024-06-21 | 2024-06-14 |  |  | 2024-06-14 | 12344 | Tammi Baker | 2024-06-04 | 2024-06-11 | 2024-06-06 | [19 empty] | ATT-7540 | MIN001.G0000078 | 2024-03-15 | 2024-04-16 | 2024-05-09 | 2024-05-09 | [7 empty] | 172 | 1 | 2024 | 5 | 18 | #REF! | 2024-12-06
ITG-116379 | 2 | Active |  |  | PSA | BCL | PSA-4112PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 11 | Bloomington | 13 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | SEE NOTE | [8 empty] | 0 | 0 | [37 empty] | 9/19 job is only a few BCLS, could combine with PSA-4111, sent email to team. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7541 | MIN001.G0000079 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-14 | [7 empty] | 173 | 1 | 1900 | 1 | 0 | #REF! | 2024-11-27
ITG-116382 | 2 | Active |  |  | PSA | SFU | PSA-4113PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 11 | Bloomington | 522 | 490 |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | 2024-04-26 | HANNAH | 2024-04-30 | 2024-05-24 | 2024-05-24 | YES | 2121 | 1992 | 51548 | 53540 | 102.567 | 2024-07-02 | 2024-07-19 | 2024-07-21 |  |  | 864 | PFP 9000 VENESS RD |  | 2024-07-24 | 2024-09-20 | 2024-09-25 | 2024-09-26 |  | 2024-09-25 | 43124 | Cheryl Turk | 2024-08-20 | 2024-09-20 | 2024-09-20 | [18 empty] | 9/26 Chris B. requested CAD changes | ATT-7542 | MIN001.G0000080 | 2024-05-06 | 2024-05-06 | 2024-05-09 | 2024-05-09 | [7 empty] | 174 | 1 | 2024 | 5 | 21 | #REF! | 2025-04-15
ITG-116381 | 2 | Active |  |  | PSA | BCL | PSA-4114PA-BLTNMNAT-CHARLIE | BLTNMNAT | RTE #4 | BBF RTE 4 SEC 11 | Bloomington | 1 |  |  | Merylene Hickman |  | 2023-12-22 | Cheryl Turk | 2024-01-09 |  |  | SEE NOTE | [8 empty] | 0 | 0 | [37 empty] | 9/19 job a lake and park area and may want to no build, sent email to team. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. SERVE FROM BBF | ATT-7543 | MIN001.G0000081 | 2024-03-15 | 2024-04-16 | 2024-05-14 | 2024-05-14 | [7 empty] | 175 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-132951 | 1 | Active |  |  | BBF | NA | BBF-82101-RT1-SEC1-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 1 | Eagan | 1625 | 1149 | [8 empty] | NA | NA | NA |  | NA | NA | 15627 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-05-06 | 2024-07-23 | 2024-05-31 | 2024-07-15 | 2024-07-17 | 2024-07-17 | 16225 | Joseph Smith | [9 empty] | 2 | 2024-04-24 | [10 empty] | 7/15 CAD sent to Michael for CAD revision to capture overlap 5/31 pending PSA 1105 & 1106 for possible overlaps 5/23 returned for added HH's to pull fiber | ATT-7972 | MIN001.G0000247 | [11 empty] | 176 |  | #VALUE! | #VALUE! | #VALUE! | Permit Complete | #N/A
ITG-117215 | 2 | Active | Oct |  | PSA | BCL/MDU | PSA-1101PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 1 | Eagan | 192 | 356 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-07-09 | CODY | 2024-07-09 | 2024-07-09 | 2024-07-09 | YES | 0 | 5 | 749 | 754 | 3.9271 | 2024-07-12 | 2024-08-08 | 2024-07-25 |  |  | 432 | PFP 3330 PILOT KNOB RD |  | 2024-08-05 | 2024-09-09 | 2024-09-10 |  |  | 2024-08-19 | 802 | Eric Lynn | 2024-07-26 | 2024-08-19 | 2024-08-19 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8092 | MIN001.G0000270 | 2024-05-15 | 2024-05-15 | 2024-05-21 | 2024-05-24 | [7 empty] | 177 | 1 | 2024 | 7 | 28 | #REF! | #N/A
ITG-117216 | 3 | HOLD FOR LATER |  |  | PSA | BCL | PSA-1102PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 1 | Eagan | 16 | 23 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-07-02 | JACOB | 2024-07-02 | 2024-07-04 | 2024-07-04 | YES | 0 | 216 | 3562 | 3778 | 236.125 | 2024-07-16 | 2024-08-08 | 2024-07-25 |  |  | 144 | PFP 3290 CENTRAL PARK VILLAGE DR | [30 empty] | 7/3 PSA1104 merged into this PSA. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8477 | MIN001.G0000333 | 2024-06-21 | 2024-06-25 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | LU count on Budget sheet is 11, Tracker shows 16. Per Ted - don’t go past MS1 | 178 | 1 | 2024 | 7 | 27 | #REF! | #N/A
ITG-116546 | 3 | Active |  |  | PSA | MDU | PSA-1103PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 1 | Eagan | 415 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA |  |  |  | NA | NA | [30 empty] | 7/9 no prefield or fielding needed, all MDU PSA and we will just need to leave a coil in the POF HH that is on the BBF route. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. MULTIFAMILY | ATT-8478 | MIN001.G0000334 | 2024-06-26 | 2024-07-24 | 2024-07-31 | 2024-08-15 | [7 empty] | 179 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-136824 | 3 | PROJECT CANCEL |  |  | PSA | BCL | PSA-1104PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 1 | Eagan |  |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [50 empty] | 7/24/ Canceled 7/2 combining job area with PSA-1102. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8479 | MIN001.G0000335 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled |  | 180 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-116549 | 1 | Active | Oct |  | PSA | SFU/MDU | PSA-1105PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 1 | Eagan | 235 | 111 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-11 | ERIK | 2024-04-11 | 2024-05-03 | 2024-05-03 | YES | 13649 | 676 | 15728 | 16404 | 69.8043 | 2024-05-30 | 2024-06-12 | 2024-06-11 |  |  | 432 | PFP 3196 JURDY CT S |  | 2024-06-13 | 2024-07-05 | 2024-07-02 |  |  | 2024-07-02 | 9130 | Tammi Baker | 2024-06-11 | 2024-07-01 | 2024-07-01 |  |  |  |  | 2024-07-02 | 2024-07-05 | [12 empty] | 7/2 sent back to CAD for corrections6/24 - Moved design DD out a week - NDS job took priority | ATT-8090 | MIN001.G0000268 | 2024-04-17 | 2024-05-02 | 2024-05-03 | 2024-05-03 | [7 empty] | 181 | 1 | 2024 | 5 | 18 | #REF! | #N/A
ITG-116550 | 1 | Active | Oct |  | PSA | SFU | PSA-1106PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 1 | Eagan | 552 | 453 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-23 | ERIK | 2024-04-24 | 2024-05-13 | 2024-05-13 | YES | 1978 | 103 | 67903 | 68006 | 123.1993 | 2024-05-29 | 2024-06-12 | 2024-06-17 |  |  | 864 | PFP 2890 PILOT KNOB RD |  | 2024-06-17 | 2024-08-16 | 2024-08-06 |  |  | 2024-08-06 | 43841 | Jermaine Scott | 2024-06-17 | 2024-07-01 | 2024-06-21 | [18 empty] | 7/3 Portion of PSA1108 merged into this PSA | ATT-8091 | MIN001.G0000269 | 2024-04-17 | 2024-04-18 | 2024-05-02 | 2024-05-02 | [7 empty] | 182 | 1 | 2024 | 5 | 20 | #REF! | #N/A
ITG-136825 | 3 | HOLD FOR LATER |  |  | PSA | BCL | PSA-1107PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 1 | Eagan | 207 | 206 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-07-02 | JACOB | 2024-07-02 | 2024-07-07 | 2024-07-07 | YES | 0 | 155 | 18563 | 18718 | 90.4251 | 2024-07-12 | 2024-07-30 | 2024-07-30 |  |  | 432 | PFP 1400 CORPORATE CENTER CURVE |  |  | 2024-09-03 | [27 empty] | 7/3 Portion of this PSA1108 merged into this PSA. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8480 | MIN001.G0000336 | 2024-06-24 | 2024-07-24 | 2024-07-31 | 2024-08-15 | STOP | STOP | STOP | STOP | STOP | STOP | Per Ted - don’t go past MS1 | 183 | 1 | 2024 | 7 | 28 | #REF! | #N/A
ITG-136826 | 3 | PROJECT CANCEL |  |  | PSA | BCL | PSA-1108PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 1 | Eagan | 37 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [50 empty] | 7/2 combining job area with PSA-1106 and PSA-1107. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8481 | MIN001.G0000337 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled |  | 184 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-132954 | 2 | Active |  |  | BBF | NA | BBF-82101-RT1-SEC2-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 2 | Eagan | 294 | 417 | [8 empty] | NA | NA | NA |  | NA | NA | 0 | NA | NA | NA | NA | [8 empty] | 2024-09-27 | 2024-10-30 | [5 empty] | Joseph Smith | [22 empty] | ATT-8110 | MIN001.G0000275 | Needed in IQGEO | [10 empty] | 185 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-116563 | 2 | Active |  |  | PSA | MDU | PSA-1201PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 2 | Eagan | 300 | 417 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-06-12 | HUNTER | 2024-06-18 | 2024-06-25 | 2024-06-25 | YES | 0 | 41 | 1068 | 1109 | 3.6967 | 2024-07-12 | 2024-07-22 | 2024-07-25 |  |  | 576 | PFP 3005 EAGANDALE PLACE |  | 2024-08-05 | 2024-08-28 | 2024-08-13 |  |  | 2024-08-13 | 1150 | James Lugo | 2024-07-26 | 2024-08-02 | 2024-07-30 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. MULTIFAMILY | ATT-8116 | MIN001.G0000281 | 2024-05-31 | 2024-06-04 | 2024-06-25 | 2024-06-25 | [7 empty] | 186 | 1 | 2024 | 6 | 26 | A | #N/A
ITG-132926 | 2 | NO BUILD |  |  | PSA | BCL | PSA-1202PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 2 | Eagan | 12 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-06-12 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | [37 empty] | 6/18 Combined w/ PSA 1201, 1202 is now no build/Junior 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8117 | MIN001.G0000282 | 2024-05-31 | 2024-06-04 | 2024-06-04 | 2024-06-04 | Stop | Stop | Stop | Stop | Stop | Stop |  | 187 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-132324 | 2 | Active |  |  | BBF | NA | BBF-82101-RT1-SEC3-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 3 | Eagan | 1290 | 1016 | [8 empty] | NA | NA | NA |  | NA | NA | 9127 | NA | NA | NA | NA | [9 empty] | 2024-10-30 |  |  |  |  | 12014 | Joseph Smith | [22 empty] | ATT-8097 | MIN001.G0000272 | [11 empty] | 188 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-120164 | 2 | Active |  |  | PSA | SFU/MDU | PSA-1301PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 3 | Eagan | 578 | 320 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-06-12 | HUNTER | 2024-06-18 | 2024-06-26 | 2024-06-26 | YES | 0 | 0 | 1725 | 1725 | 2.9844 | 2024-07-16 | 2024-07-23 | 2024-07-25 |  |  | 864 | PFP 3409 HIGHLAND DR |  | 2024-07-31 | 2024-08-28 | 2024-08-27 |  |  | 2024-08-20 | 1924 | James Lugo | 2024-07-26 | 2024-08-09 | 2024-07-31 | [18 empty] | MDU & PRIVATE | ATT-8118 | MIN001.G0000283 | 2024-05-31 | 2024-05-31 | 2024-06-04 | 2024-06-04 | [6 empty] | Need to correct LU count on Budget Sheet for MS2 | 189 | 1 | 2024 | 6 | 26 | #REF! | #N/A
ITG-136827 | 3 | HOLD FOR LATER |  |  | PSA | BCL | PSA-1302PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 3 | Eagan | 133 | 135 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-07-02 | JACOB | 2024-07-09 | 2024-07-13 | 2024-07-13 | YES | 0 | 323 | 1504 | 1827 | 13.7368 | 2024-07-16 | 2024-07-30 | 2024-07-30 |  |  | 288 | PFP 1472 YANKEE DOODLE RD |  |  | 2024-09-18 | [27 empty] | 6/17 Junior combined with PSA 1303. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8482 | MIN001.G0000338 | 2024-06-24 | 2024-07-24 | 2024-07-31 | 2024-08-15 | STOP | STOP | STOP | STOP | STOP | STOP | Per Ted - don’t go past MS1 | 190 | 1 | 2024 | 7 | 28 | #REF! | #N/A
ITG-136829 | 3 | PROJECT CANCEL |  |  | PSA | BCL | PSA-1303PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 3 | Eagan | 6 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [14 empty] | 2024-08-21 | [35 empty] | 6/17 Combined w/ PSA 1302, 1303 is now no build/Junior. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8483 | MIN001.G0000339 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled |  | 191 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-120165 | 2 | Active | Sep |  | PSA | SFU | PSA-1304PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 3 | Eagan | 281 | 272 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-12 | JACOB | 2024-04-12 | 2024-04-17 | 2024-04-15 | YES | 7050 | 13899 | 15162 | 29061 | 103.4199 | 2024-05-03 | 2024-08-22 | 2024-05-21 |  |  | 432 | PFP 1451 BLACKHAWK LAKE DR |  | 2024-05-29 | 2024-07-08 | 2024-07-03 |  |  | 2024-07-03 | 21103 | Christian Weller | 2024-05-24 | 2024-06-28 | 2024-07-05 | [18 empty] | 6/24 - Moved design DD out - Christian took PTO last week for personal matter and design still has errors to clean up HDB 5/13 - LAYOUT ECD MOVED FROM 5/10 TO 5/14 - DESIGNER OOO | ATT-8096 | MIN001.G0000271 | 2024-05-02 | 2024-05-02 | 2024-05-31 | 2024-06-03 | [7 empty] | 192 | 1 | 2024 | 4 | 16 | #REF! | #N/A
ITG-120166 | 2 | Active | Sep |  | PSA | SFU | PSA-1305PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 3 | Eagan | 299 | 289 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-12 | JACOB | 2024-04-17 | 2024-04-22 | 2024-04-19 | YES | 2077 | 12987 | 14891 | 27878 | 93.2375 | 2024-04-24 | 2024-05-08 | 2024-05-08 | 2024-09-10 | 2024-09-10 | 432 | PFP 3613 ASHBURY RD |  | 2024-07-01 | 2024-07-05 | 2024-05-28 | 2024-07-25 | 2024-09-10 | 2024-05-28 | 20376 | Jordan Struck | 2024-05-08 | 2024-05-23 | 2024-05-14 | 2024-09-16 |  |  |  | 2024-06-02 | 2024-06-11 | 1 out of 2 | [11 empty] | 7/3 PSA1306 and PSA1037 merged into this PSA | ATT-8098 | MIN001.G0000273 | 2024-05-02 | 2024-05-02 | 2024-05-31 | 2024-06-03 | [7 empty] | 193 | 1 | 2024 | 4 | 16 | #REF! | #N/A
ITG-136830 | 3 | PROJECT CANCEL |  |  | PSA | BCL | PSA-1306PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 3 | Eagan |  |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [50 empty] | 7/2 combining job area with PSA-1305. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8484 | MIN001.G0000340 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled |  | 194 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136832 | 3 | PROJECT CANCEL |  |  | PSA | BCL | PSA-1307PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 3 | Eagan |  |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [50 empty] | 7/2 combining job area with PSA-1305. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8485 | MIN001.G0000341 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled |  | 195 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-132956 | 1 | Active |  |  | BBF | NA | BBF-82101-RT1-SEC4-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 4 | Eagan | 1797 | 1323 | [8 empty] | NA | NA | NA |  | NA | NA | 11554 | NA | NA | NA | NA | [8 empty] | 2024-07-02 | 2024-08-23 | 2024-08-26 | 2024-09-11 | ECD 9/30 | 2024-08-19 | 12154 | Joseph Smith | [21 empty] | 9/11 corrections needed on both MNDOT and CAD print. 8/14 MJ - CAD date revised to ensure all overlapping MNDOT work is completed, we need to ensure Sections are assigned altogther so the engineering can take place at the same time 6/4 show PSA-1404 on this BBF permit. | ATT-8111 | MIN001.G0000276 | [11 empty] | 196 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-120163 | 3 | Active |  |  | PSA | SFU/MDU | PSA-1401PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 4 | Eagan | 254 | 357 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-07-09 | CODY | 2024-07-09 | 2024-07-14 | 2024-07-14 | YES | 0 | 47 | 3059 | 3106 |  | 2024-07-24 | 2024-08-05 | 2024-08-07 |  |  | 432 | PFP 1560 QUARRY RD |  | 2024-08-20 | 2024-10-02 | 2024-08-26 |  |  | 2024-08-26 | 2159 | Jermaine Scott | 2024-08-09 | 2024-08-23 | 2024-08-13 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8469 | MIN001.G0000325 | 2024-05-31 | 2024-06-04 | 2024-06-04 | 2024-06-04 | [7 empty] | 197 | 1 | 2024 | 7 | 29 | #REF! | #N/A
ITG-118087 | 2 | Active | Sep |  | PSA | MIX | PSA-1402PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 4 | Eagan | 500 | 241 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-12 | JAEGER | 2024-04-12 | 2024-04-18 | 2024-04-17 | YES | 10044 | 10 | 13217 | 13227 | 26.454 | 2024-05-03 | 2024-05-10 | 2024-05-13 |  |  | 864 | 3395 YANKEE DOODLE LN |  | 2024-06-17 | 2024-06-19 | 2024-06-19 | 2024-09-25 | ECD 9/30 | 2024-06-19 | 6800 | James Lugo | 2024-05-13 | 2024-05-27 | 2024-05-14 |  |  |  |  | 2024-06-18 | 2024-06-19 | [12 empty] | 6/13 Returned to CAD for missing BBF, Excel pipeline is outside of our placement kaylie to check if anything is required. 6/12 Forwrd to Kaylie to permit 6/11 CAD sent back for corrections, MNDOT is good to permit. | ATT-8119 | MIN001.G0000284 | 2024-05-02 | 2024-05-02 | 2024-05-31 | 2024-06-03 | [7 empty] | 198 | 1 | 2024 | 4 | 16 | #REF! | #N/A
ITG-132925 | 2 | Active | Sep |  | PSA | BCL | PSA-1403PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 4 | Eagan | 52 | 58 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-06-12 | HUNTER | 2024-06-12 | 2024-06-24 | 2024-06-24 | YES | 0 | 159 | 7886 | 8045 | 154.7115 | 2024-07-12 | 2024-08-09 | 2024-07-17 |  |  | 144 | PFP 3207 SIBLEY MEMORIAL HWY |  | 2024-07-23 | 2024-08-23 | 2024-08-19 | 2024-09-25 | ECD 9/30 | 2024-08-19 | 6271 | Cheryl Turk | 2024-07-18 | 2024-08-01 | 2024-07-31 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8120 | MIN001.G0000285 | 2024-05-31 | 2024-06-04 | 2024-06-04 | 2024-06-04 | [7 empty] | 199 | 1 | 2024 | 6 | 26 | #REF! | #N/A
ITG-118088 | 1 | Active | Sep |  | PSA | MDU | PSA-1404PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 4 | Eagan | 297 | 217 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-05-21 | CODY | 2024-05-23 | 2024-06-03 | 2024-06-03 | YES | 1510 | 36 | 1017 | 1053 | 3.5455 | 2024-06-10 | 2024-06-17 | 2024-06-12 |  |  | 432 | PFP 3155 COACHMAN RD |  | 2024-06-17 | 2024-07-19 | 2024-07-02 |  |  | 2024-07-02 | 1553 | Jermaine Scott | 2024-06-12 | 2024-06-19 | 2024-06-12 |  |  |  |  | 2024-07-02 | 2024-07-02 | [12 empty] | 6/4 combine this PSA on the same permit as BBF RTE 1 SEC 4. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-8121 | MIN001.G0000286 | 2024-04-17 | 2024-04-18 | 2024-05-15 | 2024-05-15 | [7 empty] | 200 | 1 | 2024 | 6 | 23 | #REF! | #N/A
ITG-120169 | 1 | Active | Sep |  | PSA | SFU/MDU | PSA-1405PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 4 | Eagan | 338 | 80 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-05-21 | CODY | 2024-05-23 | 2024-06-04 | 2024-06-04 | YES | 0 | 65 | 3398 | 3463 | 10.2456 | 2024-06-04 | 2024-06-17 | 2024-06-11 |  |  | 432 | PFP 1593 FOUR OAKS RD |  | 2024-06-13 | 2024-07-19 | 2024-07-03 |  |  | 2024-07-03 | 3689 | Tammi Baker | 2024-06-11 | 2024-07-30 | 2024-07-31 | [18 empty] | 6/24 - Moved design DD out a week - NDS job took priority 80+/- SFUs (4-PLEX with individual addresses), the rest are MDU | ATT-8122 | MIN001.G0000287 | 2024-04-17 | 2024-04-18 | 2024-05-15 | 2024-05-16 | [7 empty] | 201 | 1 | 2024 | 6 | 23 | #REF! | #N/A
ITG-136834 | 3 | Active |  |  | PSA | BCL/MDU | PSA-1406PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 4 | Eagan | 369 | 370 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-07-09 | CODY | 2024-07-09 | 2024-07-14 | 2024-07-14 | YES | 0 | 53 | 1777 | 1830 |  | 2024-07-24 | 2024-07-30 | 2024-07-30 |  |  | 432 | PFP 3255 COACHMAN RD |  | 2024-08-20 | 2024-10-02 | 2024-08-22 |  |  | 2024-08-21 | 1835 | Cheryl Turk | 2024-07-30 | 2024-08-06 | 2024-08-06 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. MULTIFAMILY | ATT-8470 | MIN001.G0000326 | 2024-06-27 | 2024-07-19 | 2024-07-22 | 2024-07-24 | [7 empty] | 202 | 1 | 2024 | 7 | 29 | #REF! | #N/A
ITG-132957 | 2 | Active |  |  | BBF | NA | BBF-82101-RT1-SEC5-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan | 3465 | 2084 | [8 empty] | NA | NA | NA |  | NA | NA | 20913 | NA | NA | NA | NA | [8 empty] | 2024-08-30 | 2024-10-04 | [5 empty] | Joseph Smith | [22 empty] | ATT-8112 | MIN001.G0000277 | Needed in IQGEO | [10 empty] | 203 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-133171 | 2 | Active | Sep |  | PSA | BCL | PSA-1501PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan | 104 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-07-15 | EX COMP | NA | NA | NA | NA | [42 empty] | 7/23 fielder found that the area already has fiber services. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8140 | MIN001.G0000288 | 2024-05-31 | 2024-06-04 | 2024-06-04 | 2024-06-04 | [7 empty] | 204 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-121053 | 2 | Active | Sep |  | PSA | MDU | PSA-1502PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan | 255 | 186 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-07-09 | HUNTER | 2024-07-09 | 2024-07-15 | 2024-07-12 | YES | 0 | 740 | 3783 | 4523 | 17.7373 | 2024-07-16 | 2024-07-30 | 2024-07-30 |  |  | 432 | PFP 3601 BURGUNDY DR |  | 2024-08-09 | 2024-09-18 | 2024-08-26 |  |  | 2024-08-23 | 4558 | James Lugo | 2024-08-05 | 2024-08-09 | 2024-08-08 | [18 empty] | MDU | ATT-8602 | MIN001.G0000348 | 5/31/2024 | 2024-06-04 | 2024-06-04 | 2024-06-24 | [7 empty] | 205 | 1 | 2024 | 7 | 28 | #REF! | #N/A
ITG-121054 | 2 | Active |  |  | PSA | SFU | PSA-1503PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan | 199 | 121 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-23 | CODY | 2024-04-24 | 2024-05-13 | 2024-05-13 | YES | 7216 | 0 | 10872 | 10872 | 54.6332 | 2024-06-24 | 2024-07-09 | 2024-07-08 |  |  | 288 | PFP 3745 BLACKHAWK RD |  | 2024-07-09 | 2024-09-27 | [5 empty] | Cheryl Turk | 2024-07-17 | 2024-07-31 | 2024-07-30 | [19 empty] | ATT-8307 | MIN001.G0000298 | 2024-05-06 | 2024-05-06 | 2024-05-31 | 2024-06-03 | [7 empty] | 206 | 1 | 2024 | 5 | 20 | #REF! | #N/A
ITG-121055 | 2 | No Build - Ex Comp |  |  | PSA | SFU | PSA-1504PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan | 589 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-23 | DREW | 2024-04-24 | 2024-05-13 | 2024-05-13 | NA | 3266 | 0 | 0 | 0 | 0 | [37 empty] | 5/22 Competition confirmed5/21 GP to verify competition in the field today. FIELDER REPORTED EXISTING LUMEN COMPETITION IN THIS JOBS AREA, BBF ROUTE WAS FIELDED 5/17. | ATT-8171 | MIN001.G0000291 | 2024-05-06 | 2024-05-06 | 2024-06-27 | 2024-07-24 | ? | [5 empty] | Fielding complete, which MS do we want to bill through? | 207 | 1 | 2024 | 5 | 20 | #REF! | #N/A
ITG-121056 | 2 | Active |  |  | PSA | SFU/BCL | PSA-1506PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan | 477 | 408 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-23 | HUNTER | 2024-04-25 | 2024-05-08 | 2024-05-08 | YES | 2808 | 359 | 17397 | 17756 | 37.2243 | 2024-06-07 | 2024-06-26 | 2024-06-26 |  |  | 576 | 800 Carnelian LN | 2024-06-26 | 2024-06-26 | 2024-07-12 | 2024-07-08 |  |  | 2024-07-08 | 14359 | Jordan Struck | 2024-06-26 | 2024-07-03 | 2024-06-28 | [19 empty] | ATT-8288 | MIN001.G0000292 | 2024-05-06 | 2024-05-06 | 2024-05-31 | 2024-06-03 | [7 empty] | 208 | 1 | 2024 | 5 | 19 | #REF! | #N/A
ITG-121058 | 2 | Active |  |  | PSA | MDU | PSA-1507PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan | 397 | 365 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-07-09 | HANNAH | 2024-07-23 | 2024-08-09 | 2024-08-09 | YES | 0 | 943 | 4974 | 5917 | 14.9043 | 2024-08-12 | 2024-08-28 | 2024-09-04 |  |  | 864 | PFP 1895 DIFFLEY RD |  | 2024-09-06 | 2024-09-13 | 2024-09-16 |  |  | 2024-09-16 | 6168 | James Lugo | 2024-09-04 | 2024-09-18 | 2024-09-10 | [18 empty] | MDU | ATT-8451 | MIN001.G0000307 | 2024-05-31 | 2024-05-31 | 2024-06-04 | 2024-06-04 | [7 empty] | 209 | 1 | 2024 | 8 | 32 | #REF! | #N/A
ITG-133172 | 2 | Active |  |  | PSA | SFU/MDU | PSA-1508PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan | 373 | 321 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-06-12 | NA | NA | NA | NA | NA | 0 | 0 | 0 |  |  | 2024-08-28 | 2024-09-12 | 2024-09-05 |  |  | 432 | PFP 1832 SOUTHPOINTE TER |  | 2024-09-16 | 2024-10-04 | 2024-09-16 |  |  | 2024-09-16 | 5 | Spencer Lynn | 2024-09-10 | 2024-09-20 | 2024-09-20 | [18 empty] | 6/13 fielding not needed, routes fielded on PSA-1513 and PSA-1507. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8452 | MIN001.G0000308 | 2024-05-31 | 2024-06-04 | 2024-06-04 | 2024-06-04 | [7 empty] | 210 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-133313 | 2 | Active |  |  | PSA | MDU | PSA-1510PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan | 402 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-06-21 | NA | NA | NA | NA | NA | 0 | 0 | 0 | [39 empty] | 6/27 PSA1511 and PSA1512 combined into this PAS 6/13 fielding not needed, routes fielded on PSA-1513 with BBF assignment. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. MULTIFAMILY | ATT-8453 | MIN001.G0000309 | 2024-05-31 | 2024-06-04 | 2024-06-04 | 2024-06-04 | [7 empty] | 211 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-133315 | 2 | NO BUILD |  |  | PSA | BCL/MDU | PSA-1511PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan |  |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [50 empty] | 6/25 job to be cancelled, job area combined with PSA-1510. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. MULTIFAMILY | ATT-8454 | MIN001.G0000310 | 5/31/2024 | 2024-06-04 | 2024-06-04 | 2024-06-04 | Stop | Stop | Stop | Stop | Stop | Stop |  | 212 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-137080 | 3 | PROJECT CANCEL |  |  | PSA | BCL/MDU | PSA-1512PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan |  |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [50 empty] | 6/25 job to be cancelled, job area combined with PSA-1510. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8468 | MIN001.G0000324 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled |  | 213 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-133162 | 2 | Active |  |  | PSA | SFU | PSA-1509PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan | 401 | 401 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-16 | HUNTER | 2024-04-16 | 2024-04-26 | 2024-04-26 | YES | 1104 | 270 | 26274 | 26544 | 66.1945 | 2024-05-02 | 2024-05-16 | 2024-05-20 |  |  | 576 | PFP 4249 BLACKHAWK RD |  | 2024-05-22 | 2024-07-05 | 2024-07-04 |  |  | 2024-07-03 | 22720 | Cheryl Turk | 2024-05-20 | 2024-06-03 | 2024-05-28 | [19 empty] | ATT-8289 | MIN001.G0000293 | 2024-05-06 | 2024-05-06 | 2024-05-31 | 2024-06-03 | [7 empty] | 214 | 1 | 2024 | 4 | 17 | #REF! | #N/A
ITG-133186 | 2 | Active |  |  | PSA | SFU/BCL | PSA-1513PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 5 | Eagan | 294 | 282 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-16 | JAEGER | 2024-04-16 | 2024-04-23 | 2024-04-23 | YES | 6519 | 95 | 15778 | 15873 | 53.9898 | 2024-05-17 | 2024-05-28 | 2024-05-29 |  |  | 432 | PFP 2010 CLIFF RD |  | 2024-06-04 | 2024-06-21 | 2024-06-21 |  |  | 2024-06-21 | 14082 | Jordan Struck | 2024-05-29 | 2024-06-12 | 2024-05-31 |  |  |  |  | 2024-06-28 | 2024-07-02 | [12 empty] | 6/17 Returned to CAD/Junior for corrections. | ATT-8290 | MIN001.G0000294 | 2024-05-06 | 2024-05-06 | 2024-05-31 | 2024-06-03 | [7 empty] | 215 | 1 | 2024 | 4 | 17 | #REF! | #N/A
ITG-132983 | 2 | Active |  |  | BBF | NA | BBF-82101-RT1-SEC6-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 6 | Eagan | 2945 | 1306 | [8 empty] | NA | NA | NA |  | NA | NA | 7258 | NA | NA | NA | NA | [8 empty] | 2024-06-24 | 2024-09-27 | [5 empty] | Joseph Smith | [22 empty] | ATT-8113 | MIN001.G0000278 | Needed in IQGEO | [10 empty] | 216 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-137083 | 3 | Active |  |  | PSA | BCL/MDU | PSA-1601PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 6 | Eagan | 207 | 208 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-07-09 | CODY | 2024-07-09 | 2024-07-15 | 2024-07-14 | YES | 0 | 84 | 1362 | 1446 | 6.9855 | 2024-07-19 | 2024-07-31 | 2024-07-30 |  |  | 288 | PFP 1959 SILVER BELL RD |  | 2024-08-12 | 2024-09-19 | 2024-09-05 |  |  | 9/5 v2 | 1178 | James Lugo | 2024-08-06 | 2024-08-13 | 2024-08-08 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8472 | MIN001.G0000328 | 2024-06-27 | 2024-07-24 | 2024-08-01 | 2024-08-01 | [7 empty] | 217 | 1 | 2024 | 7 | 29 | #REF! | #N/A
ITG-133317 | 2 | Active |  |  | PSA | SFU/MDU | PSA-1602PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 6 | Eagan | 514 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-06-21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | [38 empty] | 7/9 fielding not needed, routes were fielded on PSA-1601. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. MULTIFAMILY | ATT-8341 | MIN001.G0000304 | 2024-05-31 | 2024-06-04 | 2024-06-04 | 2024-06-04 | [7 empty] | 218 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-133337 | 2 | Active |  |  | PSA | SFU/MDU | PSA-1603PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 6 | Eagan | 539 | 603 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-06-21 | SAM | 2024-07-02 | 2024-07-08 | 2024-07-08 | YES | 0 | 3009 | 6305 | 9314 | 17.2801 | 2024-07-19 | 2024-08-01 | 2024-07-31 |  |  | 864 | PFP 3801 BALLANTRAE RD |  | 2024-08-07 | 2024-09-13 | 2024-09-09 |  |  | 2024-09-09 | 8491 | Jermaine Scott | 2024-08-07 | 2024-08-21 | 2024-08-12 | [18 empty] | MULTIFAMILY- Part BLC part small MDU | ATT-8343 | MIN001.G0000305 | 2024-05-15 | 2024-05-15 | 2024-05-21 | 2024-05-24 | [7 empty] | 219 | 1 | 2024 | 7 | 28 | #REF! | #N/A
ITG-137085 | 3 | HOLD FOR LATER |  |  | PSA | MDU | PSA-1604PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 6 | Eagan | 369 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-06-21 | HUNTER | 2024-07-02 | 2024-07-08 | 2024-07-08 | YES | 0 | 99 | 3029 | 3128 | 8.477 | 2024-07-15 | 2024-08-01 | [35 empty] | 8/1 SW section split off to create PSA1609 6/27 PSA1701 combined into this PSA 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8473 | MIN001.G0000329 | 2024-06-27 | 2024-07-24 | 2024-08-01 | 2024-08-01 | Stop | Stop | Stop | Stop | Stop | Stop | Budget Sheet shows 335, Tracker is 369 Per Ted - don’t go past MS1 | 220 | 1 | 2024 | 7 | 28 | #REF! | #N/A
ITG-137088 | 3 | HOLD FOR LATER |  |  | PSA | BCL/MDU | PSA-1605PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 6 | Eagan | 472 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | [39 empty] | 7/9 fielding not needed, routes fielded with the BBF on PSA-1608. 6/27 PSA1606 combined into thise PSA 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. MULTIFAMILY | ATT-8474 | MIN001.G0000330 | 2024-06-27 | 2024-07-24 | 2024-08-01 | 2024-08-01 | Stop | Stop | Stop | Stop | Stop | Stop | Budget Sheet shows 461, Tracker shows 472. Per Ted - don’t go past MS1 | 221 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-137089 | 3 | PROJECT CANCEL |  |  | PSA | SFU | PSA-1606PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 6 | Eagan |  |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [14 empty] | 2024-08-13 | [35 empty] | 6/25 job to be cancelled, job area combined with PSA-1605. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-8475 | MIN001.G0000331 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled |  | 222 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-137090 | 3 | Active |  |  | PSA | MDU | PSA-1607PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 6 | Eagan | 353 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | [39 empty] | 7/9 no prefield or fielding needed, all MDU PSA and we will just need to leave a coil in the POF HH that is on the BBF route. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. MULTIFAMILY | ATT-8476 | MIN001.G0000332 | 2024-06-27 | 2024-08-15 | 2024-08-22 | 2024-08-23 | [7 empty] | 223 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-133187 | 2 | Active |  |  | PSA | SFU | PSA-1608PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 6 | Eagan | 497 | 495 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-16 | ERIK | 2024-04-16 | 2024-05-04 | 2024-05-04 | YES | 7258 | 0 | 52261 | 52261 | 105.1529 | 2024-06-26 | 2024-08-13 | 2024-08-21 |  |  | 864 | PFP 4347 JASPER DR |  | 2024-08-26 | 2024-09-13 | 2024-09-11 |  |  | 2024-09-10 | 33074 | Eric Lynn | 2024-08-27 | 2024-09-10 | 2024-09-10 | [18 empty] | 8/15, CAD was assigned early prior to Layout, and Layout was delayed, so have to push CAD date, MULTIFAMILY | ATT-8344 | MIN001.G0000306 | 2024-05-15 | 2024-05-15 | 2024-05-31 | 2024-06-03 | [7 empty] | 224 | 1 | 2024 | 5 | 18 | #REF! | #N/A
ITG-151862 | 3 | HOLD FOR LATER |  |  | PSA |  | PSA-1609PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 6 | Eagan | 479 | [6 empty] | 2024-08-02 | [50 empty] | PSA was previously SW section of PSA1604 | ATT-9445 | MIN001.G0000565 | need to associate |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 225
ITG-132984 | 2 | Active |  |  | BBF | NA | BBF-82101-RT1-SEC7-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 7 | Eagan | 998 | 724 | [8 empty] | NA | NA | NA |  | NA | NA | 10181 | NA | NA | NA | NA | [15 empty] | Joseph Smith | [22 empty] | ATT-8114 | MIN001.G0000279 | Needed in IQGEO | [10 empty] | 226 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-133339 | 2 | NO BUILD |  |  | PSA | SFU/MDU | PSA-1701PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 7 | Eagan |  |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [14 empty] | 2024-08-13 | [35 empty] | 6/25 job to be cancelled, job area combined with PSA-1604. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. MULTIFAMILY | ATT-8455 | MIN001.G0000311 | 2024-05-31 | 2024-06-04 | 2024-06-04 | 2024-06-04 | Stop | Stop | Stop | Stop | Stop | Stop | billed 165 LU on this job - those were actually merged into PSA1604 | 227 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-133259 | 2 | Active |  |  | PSA | SFU/BCL | PSA-1702PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 7 | Eagan | 379 | 379 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-17 | BRIAN | 2024-04-18 | 2024-05-10 | 2024-05-10 | YES | 10181 | 250 | 28993 | 29243 | 77.1583 | 2024-06-24 | 2024-07-09 | 2024-07-08 |  |  | 576 | PFP 4040 NICOLS RD |  | 2024-07-09 | 2024-08-16 | 2024-08-27 |  |  | 2024-08-27 | 25098 | Tammi Baker | 2024-07-11 | 2024-08-16 | 2024-08-16 | [18 empty] | 6/27 PSA1703 combined into this PSA | ATT-8291 | MIN001.G0000295 | 2024-05-06 | 2024-05-06 | 2024-05-31 | 2024-06-04 | [7 empty] | 228 | 1 | 2024 | 5 | 19 | #REF! | #N/A
ITG-137091 | 3 | PROJECT CANCEL |  |  | PSA | BCL | PSA-1703PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 7 | Eagan |  |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [50 empty] | 6/25 job to be cancelled, job area combined with PSA-1702. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8471 | MIN001.G0000327 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled |  | 229 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-133349 | 2 | Active |  |  | PSA | SFU | PSA-1704PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 7 | Eagan | 98 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-06-25 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | [38 empty] | 6/25 fielding not needed, routes follow along the BBF route. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. MULTIFAMILY | ATT-8456 | MIN001.G0000312 | 2024-05-31 | 2024-06-03 | 2024-06-04 | 2024-06-04 | [7 empty] | 230 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-136762 | 2 | Active |  |  | PSA | BCL/MDU | PSA-1705PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 7 | Eagan | 166 | 166 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-06-25 | JACOB | 2024-06-25 | 2024-06-27 | 2024-06-27 | YES | 0 | 480 | 3883 | 4363 | 26.2831 | 2024-07-15 | 2024-07-22 | 2024-07-25 |  |  | 288 | PFP 4450 ERIN DR |  | 2024-08-05 | 2024-08-23 | 2024-08-22 |  |  | 2024-07-25 | 3873 | James Lugo | 2024-07-26 | 2024-08-09 | 2024-07-31 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8457 | MIN001.G0000313 | 2024-05-31 | 2024-06-03 | 2024-06-04 | 2024-06-04 | [7 empty] | 231 | 1 | 2024 | 6 | 26 | #REF! | #N/A
ITG-133260 | 2 | Active |  |  | PSA | SFU/BCL | PSA-1706PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 7 | Eagan | 179 | 179 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-17 | JOSH | 2024-04-18 | 2024-04-25 | 2024-04-25 | YES |  | 413 | 7410 | 7823 | 43.7039 | 2024-05-17 | 2024-05-24 | 2024-05-24 |  |  | 288 | PFP 4495 SCOTT TRAIL |  | 2024-05-31 | 2024-06-14 | 2024-06-12 |  | 2024-06-12 | 2024-06-12 | 6695 | Mark Copeland | 2024-05-28 | 2024-06-11 | 2024-06-03 |  |  |  |  | 2024-06-12 | 2024-06-13 | 1 out of 2 |  | In Construction | 2024-07-26 | [8 empty] | 7/25 To const for county placement 6/12 forwarded to permitting 6/11correction to CAD | ATT-8292 | MIN001.G0000296 | 2024-05-06 | 2024-05-06 | 2024-05-13 | 2024-05-13 | [7 empty] | 232 | 1 | 2024 | 4 | 17 | #REF! | #N/A
ITG-132985 | 2 | Active |  |  | BBF | NA | BBF-82101-RT1-SEC8-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 8 | Eagan | 1850 | 882 | [8 empty] | NA | NA | NA |  | NA | NA | 15324 | NA | NA | NA | NA | [15 empty] | Joseph Smith | [21 empty] | 8/27 Current proposed BBF route crosses an overpass, need to find a new route to get to SEC 8 PSAs, awaiting email response. | ATT-8115 | MIN001.G0000280 | Needed in IQGEO | [10 empty] | 233 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-133346 | 2 | Active |  |  | PSA | SFU/MDU | PSA-1801PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 8 | Eagan | 251 | 244 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-07-09 | SAM | 2024-07-09 | 2024-07-15 | 2024-07-15 | YES | 0 | 2279 | 2724 | 5003 | 19.9323 | 2024-07-23 | 2024-08-01 | 2024-07-31 |  |  | 432 | PFP 2125 SILVER BELL RD |  | 2024-08-12 | 2024-10-01 | 2024-08-22 |  |  |  | 4164 | Jermaine Scott | 2024-08-07 | 2024-08-21 | 2024-08-12 | [18 empty] | 16+/- SFUs with MDU and BCL | ATT-8340 | MIN001.G0000303 | 5/31/2024 | 2024-06-03 | 2024-06-04 | 2024-06-04 | [7 empty] | 234 | 1 | 2024 | 7 | 29 | #REF! | #N/A
ITG-137092 | 3 | NO BUILD |  |  | PSA | BCL/MDU/PR | PSA-1802PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #4 | BBF RTE 4 SEC 8 | Eagan | 572 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-07-22 | HUNTER | 2024-07-25 | 2024-08-05 | 2024-08-05 | YES | 0 | 1379 | 6112 | 7491 | 13.0962 | 2024-08-07 | 2024-08-28 | [35 empty] | 9/3 was previously Eagan 1802, now Burnsville PSA4804 6/27 PSA1803 and PSA1804 combined into this. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8467 | MIN001.G0000323 | 2024-06-27 | 2024-07-24 | 2024-08-01 | 2024-08-01 | STOP | STOP | STOP | STOP | STOP | STOP | Budget sheet shows 14 LU, Tracker shows 445. Current Min- MIN001.G0000323/ ATT-8467 will need canceled, jobs was previously Eagan1802. New GP Project number needed | 235 | 1 | 2024 | 8 | 32 | #REF! | #N/A
ITG-133350 | 2 | NO BUILD |  |  | PSA | MDU/PR | PSA-1803PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 8 | Eagan |  |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [50 empty] | 6/26 job to be cancelled, job area combined with PSA-1802. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-8338 | MIN001.G0000302 | 2024-05-31 | 2024-06-03 | 2024-06-04 | 2024-06-04 | Stop | Stop | Stop | Stop | Stop | Stop |  | 236 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-136763 | 2 | NO BUILD |  |  | PSA | BCL/MDU | PSA-1804PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 8 | Eagan |  |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [50 empty] | 6/26 job to be cancelled, job area combined with PSA-1802. 5/10 Moved back to active4/29 Hold for BCL/MDU direction. COMMERCIAL - School | ATT-8335 | MIN001.G0000299 | 2024-05-15 | 2024-05-15 | 2024-05-31 | 2024-06-04 | Stop | Stop | Stop | Stop | Stop | Stop |  | 237 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-133269 | 2 | NO BUILD |  |  | PSA | SFU | PSA-1805PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 8 | Eagan | 426 | 257 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-18 | DREW | 2024-04-18 | 2024-05-06 | 2024-05-06 | YES | 15324 | 2 | 16698 | 16700 | 39.2019 | 2024-05-20 | 2024-05-28 | 2024-05-31 |  |  | 576 | PFP 2230 CLARK ST |  | 2024-06-04 |  | 2024-07-01 |  |  |  |  | Jordan Struck | 2024-05-31 | 2024-06-07 | 2024-06-05 | [18 empty] | 9/4/24 Merged with PSA1805 and moved to Burnsville PSA4704. 8/15 Pending Major MNDOT Reroute decision | ATT-8293 | MIN001.G0000297 | 2024-05-06 | 2024-05-06 | 2024-05-31 | 2024-06-04 | STOP | STOP | STOP | STOP | STOP | STOP |  | 238 | 1 | 2024 | 5 | 19 | #REF! | #N/A
ITG-136764 | 2 | NO BUILD |  |  | PSA | MDU | PSA-1806PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 8 | Eagan | 265 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-06-25 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | [38 empty] | 9/4/24 Merged with PSA1805 and moved to Burnsville PSA4704. 6/26 fielding not needed, routes follow along the BBF route. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. MULTIFAMILY | ATT-8336 | MIN001.G0000300 | 2024-05-15 | 2024-05-15 | 2024-05-31 | 2024-06-04 | STOP | STOP | STOP | STOP | STOP | STOP |  | 239 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-133270 | 2 | NO BUILD |  |  | PSA | SFU/BCL | PSA-1807PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 8 | Eagan | 463 | 381 |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 |  |  | 2024-04-18 | SAM | 2024-04-18 | 2024-04-25 | 2024-04-25 |  |  |  |  | 0 | 0 | 2024-06-11 | 2024-06-26 | 2024-06-26 |  |  | 576 | PFP 2223 JAMES ST | 2024-06-27 | 2024-06-28 | 2024-07-19 | 2024-07-11 |  |  | 2024-07-11 | 29027 | James Lugo | 2024-06-28 | 2024-07-09 | 2024-07-03 | [18 empty] | 9/4 PSA is now Burnsville PSA4705. 6/27/2024 sent redline layout to CAD, needs BBF updates , COMMERCIAL | ATT-8337 | MIN001.G0000301 | 2024-05-15 | 2024-05-15 | 2024-05-31 | 2024-06-04 | STOP | STOP | STOP | STOP | STOP | STOP |  | 240 | 1 | 2024 | 4 | 17 | #REF! | #N/A
ITG-138016 |  | NO BUILD |  |  | PSA | VACANT | PSA-1808PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #1 | BBF RTE 1 SEC 8 | Eagan | 1 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | [50 empty] | VACANT LOT | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 241 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-131136 | 1 | Active | Apr | Jul | BBF | NA | BBF-82201-RT2-SEC1-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 1 | Eagan | 2383 | 2383 |  | Aubre Thompson | [6 empty] | NA | NA | NA |  | NA | NA | 2588 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-04-23 | 2024-05-06 | 2024-04-17 |  | 2024-07-08 | 2024-07-08 | 7324 | Joseph Smith | 2024-05-13 | 2024-05-13 | 2024-05-14 |  |  |  |  | 2024-07-08 | 2024-05-03 | 1 | 2024-05-07 | In Construction | 2024-05-21 |  | 2024-07-01 | [6 empty] | 9/11 Zak-Complete 7/5 Added POF for PSA 2104 & 2105. 6/28 additional HH permit approved w/Dakota County6/6 constr not started, Junior has correction 5/14 BBF Rt2 Sec 1 published in IQGEO; Path Creation footage = 7,324'. 5/2 Sent Kaylie revised job to permit 4/30 Junior identified overlap w/BBF Rte2 w/CAD. | ATT-7975 | MIN001.G0000249 | 2024-06-21 | 2024-06-25 | 2024-06-28 | 2024-07-19 | 2024-08-27 | 2024-09-24 | [5 empty] | 242 | 1 & 2 | #VALUE! | #VALUE! | #VALUE! | Permit Complete | #N/A
ITG-118043 | 1 | Active | Jun | Sep | PSA | SFU | PSA-2101PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 1 | Eagan | 471 | 475 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-02-15 | SAM | 2024-02-19 |  | 2024-02-27 | YES | 2588 | 1652 | 44104 | 45756 | 97.1465 | 2024-04-05 | 2024-04-16 | 2024-04-19 |  |  | 576 | PFP 3603 SPRINGWOOD CT |  | 2024-07-01 | 2024-07-12 | 2024-07-12 |  |  | 2024-07-12 | 33360 | Mark Copeland | 2024-04-12 | 2024-05-16 | 2024-05-26 | 2024-07-11 | 2024-07-11 |  |  | 2024-07-12 | 2024-05-21 | 3 | 2024-07-31 | In Construction | 2024-07-12 |  | 2024-07-01 | [6 empty] | 7/25 fiber layout sent to const.7/12/Final review sent to Kaylie for permit amendment7/9 sent CAD corrections due date of 7/12, costruction calling in locates 4/19 design changes sent to Mark 4/10 Moved to 3603 Springwood Ct. -CAD 4/2 needs PFP relocated from intersection | ATT-7887 | MIN001.G0000172 | 2024-04-10 | 2024-04-16 | 2024-04-23 | 2024-06-27 | 2024-08-02 | 2024-08-02 | [5 empty] | 243 | 1 & 2 | 2024 | 2 | 9 | Permit Complete | 2024-08-16
ITG-132320 | 1 | Active | Apr | Nov | PSA | MDU | PSA-2102PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 1 | Eagan | 258 | 296 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-05-22 | DREW | 2024-05-24 | 2024-05-31 | 2024-05-31 | YES | 0 | 472 | 2040 | 2512 | 0 | 2024-06-19 | 2024-07-03 | 2024-07-03 | 2024-09-27 |  | 432 | PFP 3590 BLUE JAY WAY |  | 2024-07-09 | 2024-07-17 | 2024-07-18 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2252 | James Lugo | 2024-07-11 | 2024-07-25 | 2024-07-12 | 2024-07-18 | 2024-07-18 | [16 empty] | 9/27 Sent CAD/layout revision to remove PFP & fiber, leaving loop in BBF HH. 7/10 Construction wants this job. 5/10 Moved back to active 4/29 Hold for BCL/MDU. Apartments | ATT-7892 | MIN001.G0000176 | 2024-04-04 | 2024-04-16 | 2024-04-23 | 2024-04-25 | [7 empty] | 244 | 1 | 2024 | 5 | 22 | #REF! | 2024-08-26
ITG-118045 | 1 | Active | Apr | Aug | PSA | SFU/MDU | PSA-2103PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 1 | Eagan | 533 | 520 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-02-15 | JAEGER | 2024-02-19 |  | 2024-02-24 | YES | 0 | 1692 | 20681 | 22373 | 41.9756 | 2024-04-05 | 2024-04-15 | 2024-04-15 |  |  | 864 | PFP 1195 SPOONBILL CIRCLE |  | 2024-04-12 | 2024-07-09 | 2024-07-09 |  |  | 2024-07-09 | 16622 | Tammi Baker | 2024-04-01 | 2024-05-15 | 2024-06-03 | 2024-07-16 | 2024-07-16 |  |  | 2024-07-10 | 2024-05-02 | 2 | 2024-07-11 | In Construction | 2024-06-10 |  | 2024-08-01 | [6 empty] | 7/11 permit amendment approved, notified const.7/9 revision sent to Kaylie & const., need permit ammended. 7/2 sent rev request to the team to build out to 33 twnhm's, const is on site 5/1 email'd Kaylie to begin permitting/ 'PERMIT COPY' 4/11 design revision sent to Tammi | ATT-7888 | MIN001.G0000173 | 2024-04-11 | 2024-04-16 | 2024-04-23 | 2024-04-25 | 2024-06-25 | 2024-06-25 | [5 empty] | 245 | 1 & 2 | 2024 | 2 | 8 | Permit Complete | 2024-07-19
ITG-132316 | 1 | Active | Jun | Aug | PSA | MDU | PSA-2104PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 1 | Eagan | 326 | 325 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-05-22 | DREW | 2024-05-24 | 2024-05-31 | 2024-05-31 | YES | 0 | 480 | 804 | 1284 | 0 | 2024-06-20 | 2024-07-03 | 2024-07-03 |  |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | Cheryl Turk | 2024-07-09 | 2024-07-31 | 2024-07-23 |  |  |  |  | N/A | N/A | N/A | N/A | In Construction | 2024-07-16 | [8 empty] | 7/9 sent to Chris for IQGEO due 7/13, no permitting is required. 7/5 sent change to Henry, CAD & Chris 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-7973 | MIN001.G0000248 | 2024-04-11 | 2024-04-16 | 2024-04-23 | 2024-04-25 | 2024-08-26 | 2024-08-26 | [5 empty] | 246 | 1 & 2 | 2024 | 5 | 22 | Permit Complete | 2024-08-26
ITG-132319 | 1 | Active | Jun | Aug | PSA | MDU | PSA-2105PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 1 | Eagan | 251 | 250 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-05-22 | DREW | 2024-05-24 | 2024-05-31 | 2024-05-31 | YES | 0 | 384 | 398 | 782 | 0 | 2024-06-17 | 2024-07-03 | 2024-07-03 |  |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | Cheryl Turk | 2024-07-09 | 2024-07-31 | 2024-07-23 |  |  |  |  | N/A | N/A | N/A | N/A | In Construction | 2024-07-16 | [8 empty] | 7/9 sent to Chris for IQGEO due 7/13. No permitting is required. 7/5 sent change to Henry, CAD & Chris 5/10 Moved back to active 4/29 Hold for BCL/MDU. Apartments | ATT-7976 | MIN001.G0000250 | 2024-04-11 | 2024-04-16 | 2024-04-23 | 2024-04-25 | 2024-08-26 | 2024-08-26 | [5 empty] | 247 | 1 & 2 | 2024 | 5 | 22 | Permit Complete | 2024-08-26
ITG-132341 | 3 | Active |  | Dec | PSA | BCL/MDU | PSA-2106PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 1 | Eagan | 443 | 546 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-06-26 | JACOB | 2024-06-26 | 2024-06-27 | 2024-06-27 | YES | 0 | 656 | 4058 | 4714 | 10.6411 | 2024-07-16 | 2024-07-29 | 2024-07-29 |  |  | 864 | PFP 1121 TOWN CENTRE DR |  | 2024-08-26 | 2024-08-30 | 2024-08-27 |  |  | 2024-08-27 | 3899 | Cheryl Turk | 2024-08-05 | 2024-08-19 | 2024-08-19 | [18 empty] | 8/26 Assigned to new CAD drafter, 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-8030 | MIN001.G0000252 | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-24 | [7 empty] | 248 | 1 | 2024 | 6 | 26 | #REF! | #N/A
ITG-132342 | 3 | Active |  |  | PSA | BCL | PSA-2107PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 1 | Eagan | 61 | 99 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-06-26 | HUNTER | 2024-06-26 | 2024-06-30 | 2024-06-30 | YES | 0 | 4105 | 4780 | 8885 | 145.6557 | 2024-07-11 | 2024-08-05 | 2024-07-29 |  |  | 144 | PFP 1276 TOWN CENTRE DR |  | 2024-08-05 | 2024-09-10 | 2024-09-12 |  |  | 2024-09-11 | 5687 | Cheryl Turk | 2024-08-06 | 2024-08-19 | 2024-08-19 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8029 | MIN001.G0000251 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-24 | [7 empty] | 249 | 1 | 2024 | 6 | 27 | #REF! | #N/A
ITG-131150 | 1 | Active | Apr | Jul | BBF | NA | BBF-82201-RT2-SEC2-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 2 | Eagan | 1854 | 1563 | [8 empty] | NA | NA | NA |  | NA | NA | 12629 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-05-02 | 2024-05-07 | 2024-05-19 | 2024-08-15 | 2024-08-20 | 2024-08-20 | 10767 | Joseph Smith | 2024-05-13 | 2024-05-15 | 2024-05-16 |  |  |  |  | 2024-07-17 | 2024-05-07 | 3 | 2024-05-23 | In Construction | 2024-08-21 |  | 2024-08-21 | [6 empty] | 9/11 Zak-Complete 8/23 revized spl copy per Zak, included Joe. 8/20 sent revised copy to const. only notes added to explain added fiber to PSA 2203 to pick up school8/7 Fiber plaement/splic print provided to const.7/17 spoke with Matt and job was built to 5/3 version w/minor changes 5/16 BBF Rt2 Sec 2 published in IQGEO; Path Creation footage = 10,767'. 5/6 CAD revision complete ready to permit. 4/29 emailed Michael for CAD schedule. Overlaps with PSA 2201,2202, 2203 and 2204 | ATT-8033 | MIN001.G0000255 | 2024-05-28 | 2024-05-29 | 2024-06-11 | 2024-06-11 | 2024-08-27 | 2024-08-28 |  |  |  |  | Need to double check footage before submitting ms2 - joe just re-validated the footage | 250 | 1 & 2 | #VALUE! | #VALUE! | #VALUE! | Permit Complete | #N/A
ITG-118090 | 1 | Active | Apr | Aug | PSA | SFU/MDU | PSA-2201PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 2 | Eagan | 481 | 476 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-02-15 | SAM | 2024-03-05 |  | 2024-03-17 | YES | 4345 | 1172 | 37753 | 38925 | 80.9252 | 2024-04-05 | 2024-04-15 | 2024-04-17 | 2024-08-08 | 2024-08-12 | 864 | PFP 3870 PILOT KNOB RD |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | 2024-08-12 | 2024-08-13 | 2024-06-26 | 27396 | James Lugo | 2024-04-17 | 2024-05-01 | 2024-04-26 | 2024-08-13 | 2024-08-16 | 2024-07-05 |  | 2024-07-16 | 2024-05-01 | 2 |  | In Construction | 2024-06-24 | [8 empty] | 8/6 - MJ Junior messaged that this PSA is absorbing additional LUs and CAD/Layout/Design need updates 7/25 fiber layout sent to const.7/16 sent revision to Kaylie & Chris for amendment/design update (6/26 issue)6/24 const started w/o handoff, revision required on sht 39 & 40 permit amendment needed5/28 Magellan x-ing permitted on the BBF. 5/1 email'd Kaylie to begin permitting/ 'PERMIT COPY' 4/29 CAD sent to James-This job overlaps with BBF-82201-RT2-SEC2-EAGNMN82-CHARLIE on Pilot Knob Rd to Berry Ridge, sent email to Michael | ATT-7890 | MIN001.G0000174 | 2024-04-11 | 2024-04-16 | 2024-04-23 | 2024-04-25 | 2024-05-30 | 2024-05-30 | [5 empty] | 251 | 1 & 2 | 2024 | 3 | 12 | #REF! | 2024-07-19
ITG-116547 | 1 | Active | Apr | Oct | PSA | SFU | PSA-2202PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 2 | Eagan | 344 | 227 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-02-15 | JAEGER | 2024-03-05 |  | 2024-03-13 | YES | 2509 | 510 | 23966 | 24476 | 71.1512 | 2024-04-05 | 2024-04-11 | 2024-04-12 |  |  | 576 | PFP 3817 KINGSWOOD TRL |  | 2024-05-13 | 2024-05-15 | 2024-05-19 | 2024-08-22 | 2024-08-27 | 2024-08-27 | 17863 | Jordan Struck | 2024-04-12 | 2024-04-26 | 2024-04-19 | 2024-09-10 | 2024-09-18 | 2024-09-19 |  | 2024-08-21 | 2024-05-22 | 2 | 2024-07-26 | In Construction | 2024-08-21 |  | 2024-09-20 | [6 empty] | 8/28 sent to Kaylie to send to the city. 8/22 City requested revision sht 8. 8/19 sent CAD corrections to Michael. Permit will need to be amended.7/10 pending city 4/29 overlaps w/BBF sent email to Michael 4/18 sent final CAD | ATT-8037 | MIN001.G0000259 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-25 | 2024-08-27 | 2024-08-28 | [5 empty] | 252 | 1 & 2 | 2024 | 3 | 11 | Permit Complete | 2024-08-16
ITG-126045 | 1 | Active | Apr | Oct | PSA | SFU/MDU | PSA-2203PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 2 | Eagan | 382 | 370 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-02-15 | JAEGER | 2024-02-29 |  | 2024-03-06 | YES | 3050 | 444 | 24364 | 24808 | 64.9424 | 2024-04-05 | 2024-04-25 | 2024-04-26 | 2024-08-28 | 2024-09-03 | 864 | PFP 3771 DENMARK TRL W |  | 2024-05-13 | 2024-05-15 | 2024-05-19 | 2024-08-28 | 2024-08-28 | 8/28 v2 | 19360 | Jordan Struck | 2024-04-26 | 2024-05-10 | 2024-04-30 | 2024-09-03 | 2024-09-05 |  |  | 2024-08-21 | 2024-05-23 | 1 out of 2 |  | In Construction | 2024-09-23 | [8 empty] | 9/24 sent 8/28 issue to constr. 9/11 County approved pending city 8/28 layout correction to Henry, sent CAD to Kaylie for permit review. 8/26Corrections to CAD/Layout per city request. 8/21 sent to const, no additional permitting req'd.8/21 Layout missing the end of new 48f, CAD has sheet 10 messed up7/25 fiber layout sent to const. pending City perm4/29 overlaps w/BBF 4/24/24 - LAYOUT REVISION NEEDED TO FIX FP'S - COMPL 4/26 | ATT-7935 | MIN001.G0000218 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-25 | [7 empty] | 253 | 1 | 2024 | 3 | 10 | #REF! | 2024-08-16
ITG-125283 | 1 | Active | May | Oct | PSA | SFU | PSA-2204PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 2 | Eagan | 598 | 455 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-02-23 | SAM | 2024-02-23 |  | 2024-03-05 | YES | 2725 | 1437 | 37876 | 39313 | 65.7408 | 2024-04-05 | 2024-04-22 | 2024-04-22 | 2024-08-23 | 2024-08-28 | 864 | 1058 Savannah Rd |  | 2024-05-15 | 2024-07-12 | 2024-07-12 | 2024-09-11 | 2024-09-16 | 2024-09-16 | 31500 | Cheryl Turk | 2024-04-22 | 2024-05-13 | 2024-05-09 | 2024-09-04 | 2024-09-13 | 2024-09-13 |  | 2024-09-16 | 2024-05-23 | 2 out of 3 |  |  |  |  | 2024-09-20 | [6 empty] | 9/16 approved CAD sent to Kaylie to expedite permit 9/11 sent revision request to Michael /Chris9/9 sent Matt a copy of print. 8/9 PSA Boundary change updates needed for CAD/Layout/Design 7/23 permit amendment sent to city 7/18 revision approved Nate notified Kaylie to amend permit7/12 Sent to CAD for revisions Nate 7/10 pending city & M permits5.6 Curtis provided layout update 5/3 pending layout revision 4/29 overlaps w/BBF | ATT-7936 | MIN001.G0000219 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-25 | [7 empty] | 254 | 1 | 2024 | 3 | 10 | #REF! | 2024-08-16
ITG-136813 | 3 | Active |  |  | PSA | BCL | PSA-2205PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 2 | Eagan | 9 | 9 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-06-26 | ERIK | 2024-06-27 | 2024-07-06 | 2024-07-06 |  | 0 | 700 | 643 | 1343 | 149.2222 | 2024-07-15 | 2024-08-13 | 2024-07-29 |  |  | 144 | PFP 3625 PILOT KNOB RD |  | 2024-08-07 | 2024-09-10 | 2024-08-20 |  |  | 2024-08-20 | 1395 | James Lugo | 2024-08-06 | 2024-08-13 | 2024-08-08 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8465 | MIN001.G0000321 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-24 | [7 empty] | 255 | 1 | 2024 | 7 | 27 | #REF! | #N/A
ITG-136814 | 3 | No Build |  |  | PSA | BCL | PSA-2206PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 2 | Eagan | 26 | 26 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-06-26 | ERIK | 2024-06-27 | 2024-07-06 | 2024-07-06 |  | 0 | 955 | 1358 | 2313 | 88.9615 | 2024-07-17 | 2024-08-02 | 2024-08-05 |  |  | 144 | PFP 1380 DUCKWOOD DR |  | 2024-08-09 | 2024-09-12 | 2024-08-20 |  |  | 2024-08-20 | 2254 | James Lugo | 2024-08-07 | 2024-08-14 | 2024-08-09 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8466 | MIN001.G0000322 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-24 | ? | [5 empty] | Design and CAD complete, which MS do we want to bill through? | 256 | 1 | 2024 | 7 | 27 | #REF! | #N/A
ITG-131152 | 1 | Active | June | Aug | BBF | NA | BBF-82201-RT2-SEC3-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan | 3678 | 3154 | [8 empty] | NA | NA | NA |  | NA | NA | 16519 | NA | NA | NA | NA | [8 empty] | 2024-07-01 | 2024-07-05 | 2024-07-24 | 2024-08-09 | 2024-08-12 | 2024-08-12 | 13128 | Joseph Smith | 2024-05-20 | 2024-05-22 | 2024-05-22 | 2024-08-12 | 2024-08-27 | 2024-08-28 |  | 2024-07-10 | 2024-06-07 | 3 out of 4 |  | In Construction | 2024-07-10 |  | 2024-08-21 | [6 empty] | 9/11 Zak-Path creation in process 8/28 REVISIONS COMPLETED, PATH CREATION FOOTAGE =13,128'. 8/27 no corrections required for City, notified Kaylie8/12 submitted to Kaylie for permit amendment added HH to sht 12. 7/10 pending city , pipeline & Nat gas 5/22 BBF Rt2 Sec 3 published in IQGEO; Path Creation footage = 13,128'. | ATT-8032 | MIN001.G0000254 | 2024-06-21 | 2024-06-25 | 2024-06-28 | 2024-06-28 | [7 empty] | 257 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-130216 | 1 | Active | May |  | PSA | SFU | PSA-2301PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan | 467 | 437 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-06 | CODY | 2024-03-26 |  | 2024-04-11 | YES | 2796 | 302 | 42602 | 42904 |  | 2024-04-18 | 2024-05-02 | 2024-04-30 | 2024-08-30 | 2024-09-03 | 864 | PFP 1865 PLAZA DR |  | 2024-05-02 | 2024-06-03 | 2024-06-03 | 2024-09-16 | 2024-09-18 | 2024-09-16 | 39547 | Jermaine Scott | 2024-04-30 | 2024-05-20 | 2024-05-08 | 2024-09-03 | 2024-09-06 |  |  | 2024-06-03 | 2024-06-04 |  |  | In Construction | 2024-07-08 | [8 empty] | 9/16 sent back to CAD for corrections. 9/9 corrections sent to CAD 8/30 sent city corrections to CAD/Henry 6/4 Remove shts 42-49 due to competion 5/31 Sent CAD corrections to Michael/Junior | ATT-7937 | MIN001.G0000220 | 4/10/2024 | 2024-04-16 | 2024-04-23 | 2024-04-25 | [7 empty] | 258 | 1 | 2024 | 4 | 15 | #REF! | 2024-09-27
ITG-130182 | 1 | Active | June |  | PSA | SFU | PSA-2302PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan | 508 | 449 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-06 | DREW | 2024-03-25 |  | 2024-04-09 | YES | 0 | 438 | 26226 | 26664 |  | 2024-04-16 | 2024-05-10 | 2024-05-08 |  |  |  | PFP 1705 HICKORY HILL DR |  | 2024-05-09 | 2024-05-24 | 2024-05-22 | 2024-09-13 | 2024-09-19 | 2024-09-19 | 22347 | Cheryl Turk | 2024-04-26 | 2024-05-15 | 2024-06-12 | 2024-07-26 | 2024-08-02 |  |  | 2024-07-26 | 2024-06-04 | 1 out of 2 |  | In Construction | 2024-07-26 | [8 empty] | 9/13 Nate: Redlines Layout redlines sent to CAD and Layout. 7/26 Nate: CAD made redline corrections sent new CAD dated 7/26 to Kaylie to amend current permit. 7/26 NEED TO SEND REVISION TO CONST AND AMEND permit 7/25 To const for county placement7/26 sent to CAD for corrections.pending city 5/8 sent layout revision to Cheryl. PFP RELOC 5/3, MAJOR LAYOUT REV | ATT-7938 | MIN001.G0000221 | 2024-04-10 | 2024-04-16 | 2024-04-23 | 2024-04-25 | [7 empty] | 259 | 1 | 2024 | 4 | 15 | #REF! | 2024-09-27
ITG-129608 | 1 | Active | May | Dec | PSA | MIX | PSA-2303PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan | 649 | 614 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-06 | SAM | 2024-03-22 |  | 2024-04-08 | YES | 3834 | 5 | 31412 | 31417 |  | 2024-04-16 | 2024-04-29 | 2024-04-29 |  |  | 864 | PFP 1670 MALLARD DR |  | 2024-07-01 | 2024-07-05 | 2024-06-09 | 2024-09-12 | 2024-09-26 | 2024-09-26 | 20998 | Cody Newbill | 2024-04-29 | 2024-05-13 | 2024-05-10 | 2024-09-26 |  |  | X | 2024-09-26 | 2024-05-30 | 3 out of 4 | [11 empty] | 9/26 Nate: Print has been reviewed and approved and sent to permitting. 9/12 Nate: Cad sent back to CAD team for revision. 5/8 Layout revisions sent to Cody 4/29 sent layout to Cody. PUSH LAYOUT DATE TO 4/29 - HDB | ATT-7940 | MIN001.G0000223 | 2024-04-10 | 2024-04-16 | 2024-04-23 | 2024-04-25 | [7 empty] | 260 | 1 | 2024 | 4 | 15 | #REF! | 2024-08-26
ITG-129451 | 1 | Active | May |  | PSA | SFU/MDU | PSA-2304PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan | 322 | 195 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-06 | DREW | 2024-03-20 |  | 2024-03-29 | YES | 3246 | 162 | 22821 | 22983 | 71.3758 | 2024-04-05 | 2024-04-24 | 2024-04-24 |  |  | 432 | PFP 4350 JOHNNY CAKE RD |  | 2024-05-10 | 2024-05-24 | 2024-05-21 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 12982 | Jordan Struck | 2024-04-25 | 2024-05-09 | 2024-04-26 | 2024-07-18 | 2024-08-02 |  |  | 2024-07-18 | 2024-05-31 | 1 out of 2 | [11 empty] | 7/24 Resubmitted to city 7/18 Nate notified Kaylie permit needs to be amended. Nate 7/15 Returned to CAD and Design for corrections. Nate 7/10 pending city & M 5/22 Reviewed pend'g Junior review 5/6 Sent Jordan layout revisions. | ATT-7941 | MIN001.G0000224 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-25 | [7 empty] | 261 | 1 | 2024 | 3 | 13 | #REF! | 2024-09-20
ITG-129367 | 1 | Active | May |  | PSA | SFU | PSA-2305PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan | 450 | 282 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-06 | SAM | 2024-03-19 |  | 2024-03-23 | YES | 890 | 405 | 15419 | 15824 | 35.1644 | 2024-04-05 | 2024-04-24 | 2024-04-24 |  |  | 576 | PFP 1556 FIR PT |  | 2024-06-03 | 2024-06-04 | 2024-06-04 | 2024-07-15 | 2024-07-16 | 2024-06-04 | 14067 | James Lugo | 2024-04-25 | 2024-05-13 | 2024-04-29 | 2024-07-18 | 2024-07-18 |  | X | 2024-07-17 | 2024-06-19 | 2 out of 3 | [11 empty] | Nate 7/17 CAD corrections have been made forwareded Final CAD to Kaylie an dPermitting Nate 7/15 Returned to CAD, Design, and Permitting for corrections. Nate 7/10 pending City & 2 M 6/11 to Kaylie for permit 5/31 Returned redlines to CAD and incl. Junior. 5/16 2 Magellan x-ings to permit | ATT-7942 | MIN001.G0000225 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-25 | [7 empty] | 262 | 1 | 2024 | 3 | 12 | #REF! | 2024-09-20
ITG-127636 | 1 | Active | May |  | PSA | SFU | PSA-2306PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan | 604 | 512 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-06 | JAEGER | 2024-03-08 |  | 2024-04-04 | YES | 3686 | 1148 | 45377 | 46525 | 77.0281 | 2024-05-08 | 2024-05-21 | 2024-05-22 |  |  | 864 | PFP 4244 SEQUOIA DR |  | 2024-05-20 | 2024-07-09 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 41578 | Jermaine Scott | 2024-05-22 | 2024-06-05 | 2024-07-12 |  |  |  |  | 2024-07-12 | 2024-07-18 | 1 out of 2 |  | In Construction | 2024-07-26 | [8 empty] | 7/25 To const for county placement7/9 Layout revision due to Junior adding area of PSA2310 to PSA . CAD and IQGEO revision required | ATT-7943 | MIN001.G0000226 | 2024-04-12 | 2024-04-16 | 2024-04-23 | 2024-04-25 | [7 empty] | 263 | 1 | 2024 | 4 | 14 | #REF! | 2024-09-20
ITG-128043 | 1 | Active | Jun |  | PSA | SFU | PSA-2307PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan | 607 | 480 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-06 | HUNTER | 2024-03-12 |  | 2024-03-27 | YES | 2067 | 215 | 42091 | 42306 | 69.6969 | 2024-04-24 | 2024-05-13 | 2024-05-14 |  |  | 864 | PFP 4168 WENZEL AVE |  | 2024-05-14 | 2024-07-03 | 2024-07-01 |  |  |  | 34508 | Jordan (Cody) | 2024-05-14 | 2024-05-28 | 2024-05-28 | 2024-07-11 | 2024-08-01 |  |  | 2024-07-01 | 2024-07-05 | 2 out of 3 |  | In Construction | 2024-07-26 | [8 empty] | 7/25 To const for county placement7/9 layout revised for Juniors addition of portion of PSA2310 to the PSA, cad & IQGEO revision required 6/17 combined with PSA 2309 per Junior 5/29 review'd w/many corrections forwarded to Junior for her review | ATT-7944 | MIN001.G0000227 | 2024-04-12 | 2024-04-16 | 2024-04-24 | 2024-04-25 | [7 empty] | 264 | 1 | 2024 | 3 | 13 | #REF! | 2024-08-26
ITG-139765 | 3 | Active |  |  | PSA | BCL | PSA-2308PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan | 7 |  |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-06-26 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | [38 empty] | 6/27 fielding not needed, majority of F1 lateral route was fielded on PSA-2304. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8031 | MIN001.G0000253 | 2024-05-20 | 2024-05-20 | 2024-05-21 | 2024-05-24 | [7 empty] | 265 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-132321 | 1 | NO BUILD |  |  | PSA | BCL | PSA-2309PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan |  |  |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-05-22 | [47 empty] | 6/17 combined with PSA 2307, PSA 2309 has been eliminated. 5/24 LATERAL WAS FIELDED ALREADY ON PSA-2307PA. 5/22 PREFIELD COMP - HDB PLANNED LATERAL AND PFP 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-7948 | MIN001.G0000231 | 2024-04-12 | 2024-04-16 | 2024-05-15 | 2024-05-16 | Stop | Stop | Stop | Stop | Stop | Stop |  | 266 | 1 | 1900 | 1 | 0 | #REF! | 0
ITG-136815 | 3 | NO BUILD |  |  | PSA | BCL | PSA-2310PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan |  |  |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-06-26 | [47 empty] | 7/8 job to be canceled, combining job area with PSA-2306 and PSA-2307. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8464 | MIN001.G0000320 | 2024-05-20 | 2024-05-20 | 2024-05-29 | 2024-06-04 | Stop | Stop | Stop | Stop | Stop | Stop |  | 267 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-132322 | 1 | Active | Jun |  | PSA | MDU | PSA-2311PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan | 48 | 0 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-05-22 | DREW | 2024-05-24 | 2024-05-31 | 2024-05-31 | YES | 0 | 4156 | 0 | 4156 | 0 | 2024-06-17 | 2024-06-24 | 2024-06-24 |  |  | 144 | PFP 990 KENSINGTON TRL | 2024-06-24 | 2024-06-28 | 2024-07-26 | 2024-07-16 |  |  | 2024-07-05 | 4171 | Jordan Struck | 2024-06-24 | 2024-07-01 | 2024-06-25 | [18 empty] | 5/22 PREFIELD COMP - HDB PLANNED LATERAL AND PFP 5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-8034 | MIN001.G0000256 | 2024-04-12 | 2024-04-16 | 2024-05-15 | 2024-05-16 | [7 empty] | 268 | 1 | 2024 | 5 | 22 | #REF! | 0
ITG-132323 | 2 | Active | Jun | Dec | PSA | BCL/MDU | PSA-2312PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 3 | Eagan | 186 | 185 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-06-26 | JOSH | 2024-06-27 | 2024-07-10 | 2024-07-10 | YES | 0 | 1750 | 4350 | 6100 | 32.7957 | 2024-07-10 | 2024-08-02 | 2024-08-05 |  |  | 288 | PFP 4180 LEXINGTON AVE S |  | 2024-08-07 | 2024-09-05 | 2024-08-22 | 2024-09-12 |  | 2024-08-05 | 5463 | Jordan Struck | 2024-08-09 | 2024-08-23 | 2024-08-15 | [18 empty] | 9/12 Nate: Cad sent back to CAD team for revision. Comm/Apts | ATT-8035 | MIN001.G0000257 | 2024-04-16 | 2024-04-16 | 2024-05-31 | 2024-06-03 | [7 empty] | 269 | 1 | 2024 | 7 | 28 | #REF! | 2024-09-13
ITG-131154 | 1 | Active | May | Aug | BBF | NA | BBF-82201-RT2-SEC4-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 4 | Eagan | 669 | 443 | [8 empty] | NA | NA | NA |  | NA | NA | 5290 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-06-26 | 2024-07-10 | 2024-07-10 | 2024-07-16 | 2024-07-17 | 2024-07-17 | 9040 | Joseph Smith | 2024-05-20 | 2024-05-24 | 2024-05-22 |  | 2024-09-26 |  |  | 2024-07-16 | 2024-08-15 | 1 | 2024-08-20 | In Construction | 2024-08-21 |  | 2024-08-28 | [6 empty] | 9/26 - REVISIONS COMPLETE IN IQGEO - NEW PATH CREATION FOOTAGE = 9,040'. 9/11 Zak-Path creation in process 7/24 resubmitted to the city 7/16 Pending revision for Juniors correction, Jeff to complete 7/17. 5/23 pending CAD revision w/Junior updates 5/22 BBF Rt2 Sec 4 published in IQGEO; Path Creation footage = 8,754'. 5/13 Junior sent out detailed direction to CAD with PSA overlaps | ATT-7947 | MIN001.G0000230 | 2024-05-23 | 2024-05-23 | 2024-08-02 | 2024-08-05 | 2024-09-11 | 2024-09-20 | [5 empty] | 270 | 1 & 2 | #VALUE! | #VALUE! | #VALUE! | Permit Complete | #N/A
ITG-130636 | 1 | Active | Jun |  | PSA | SFU | PSA-2401PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 4 | Eagan | 396 | 228 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-06 | Brian | 2024-04-03 |  | 2024-04-11 | YES | 0 | 1165 | 20602 | 21767 |  | 2024-04-30 | 2024-05-09 | 2024-05-08 |  |  | 288 | PFP 4601 FAIRWAY HILLS DR |  | 2024-05-15 | 2024-06-26 | 2024-06-26 |  | 2024-07-17 | 2024-07-17 | 18013 | James Lugo | 2024-05-08 | 2024-05-23 | 2024-07-09 |  |  |  |  | 2024-07-12 | 2024-07-02 | 2 out of 3 |  | In Construction | 2024-07-10 | [8 empty] | 7/10 pending City & Nat G 6/26 CAD corrections completed forwarded to Kaylie for permitting | ATT-7945 | MIN001.G0000228 | 4/12/2024 | 2024-04-16 | 2024-04-24 | 2024-04-25 | [7 empty] | 271 | 1 | 2024 | 4 | 15 | #REF! | 2024-09-13
ITG-131166 | 1 | Active | Jun |  | PSA | SFU | PSA-2402PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 4 | Eagan | 273 | 215 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-06 | Brian | 2024-04-03 |  | 2024-04-22 | YES | 5290 | 675 | 17949 | 18624 |  | 2024-05-01 | 2024-05-07 | 2024-05-07 |  |  | 432 | PFP 1367 WILDERNESS RUN DR |  | 2024-05-29 | 2024-06-21 | 2024-06-21 |  |  | 2024-06-21 | 16583 | Cheryl Turk | 2024-05-07 | 2024-06-03 | 2024-05-22 |  |  |  |  | 2024-06-25 | 2024-06-26 | [12 empty] | 6/25 Nate emailed Kaylie ready to permit/CAD corrections completed. | ATT-7946 | MIN001.G0000229 | 2024-04-12 | 2024-04-16 | 2024-04-24 | 2024-04-25 | [7 empty] | 272 | 1 | 2024 | 4 | 17 | #REF! | 2024-09-13
ITG-131157 | 1 | Active | May | Nov | BBF | NA | BBF-82201-RT2-SEC5-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 5 | Eagan | 943 | 857 | [8 empty] | NA | NA | NA |  | NA | NA | 17677 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-05-15 | 2024-06-21 | 2024-07-05 | 2024-07-16 | 2024-07-17 | 2024-07-05 | 7814 | Joseph Smith | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-07-17 | 2024-09-27 |  |  | 2024-07-17 | 2024-07-17 | 1 | 2024-07-18 | In Construction | 2024-09-18 |  | 2024-09-20 | [6 empty] | 9/27 ADDITIONAL IQGEO REVISIONS COMPLETED, NEW PATH CREATION FOOTAGE = 7,814'. 8/28 IQGEO REVISIONS COMPLETED, NEW PATH CREATION FOOTGAE = 8/,060'. 7/16 SUS sent to CAD for a few minor corrections. 7/10 City has requsted changes per Kaylie, Junior reviewed 5/27 BBF Rt2 Sec 5 published in IQGEO; Path Creation footage =7,917'. 5/13 Junior sent out detailed direction to CAD with PSA overlaps | ATT-7949 | MIN001.G0000232 | 2024-06-21 | 2024-06-24 | 2024-08-02 | 2024-08-05 | 2024-09-23 | 2024-09-25 | [5 empty] | 273 | 1 & 2 | #VALUE! | #VALUE! | #VALUE! | Permit Complete | #N/A
ITG-131167 | 1 | Active | Jun |  | PSA | SFU | PSA-2501PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 5 | Eagan | 481 | 464 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-06 | SAM | 2024-04-05 | 2024-04-19 | 2024-04-19 | YES | 12536 | 2010 | 52233 | 54243 | 112.7713 | 2024-05-09 | 2024-05-21 | 2024-05-24 |  |  | 864 | PFP 670 ATLANTIC HILL DR |  | 2024-05-28 | 2024-06-21 | 2024-07-01 | 2024-08-29 | 2024-09-10 | 2024-09-10 | 44987 | Cheryl Turk | 2024-05-24 | 2024-06-07 | 2024-06-06 |  |  |  |  | 2024-07-16 | 2024-07-19 | 1 out of 3 |  | In Construction | 2024-07-26 | [8 empty] | 8/29 MJ MNDOT requested revisions, 7/25 To const for county placementNate 7/16 CAD revisions have been made and sent to permitting 7/10 CAD needs fixes | ATT-7950 | MIN001.G0000233 | 2024-04-12 | 2024-04-16 | 2024-04-24 | 2024-04-25 | [7 empty] | 274 | 1 | 2024 | 4 | 16 | #REF! | 2024-09-13
ITG-131168 | 1 | Active | Jun |  | PSA | SFU | PSA-2502PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 5 | Eagan | 462 | 393 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-06 | CODY | 2024-04-12 | 2024-04-30 | 2024-04-30 | YES | 5141 | 42587 | 0 | 42587 | 92.1797 | 2024-05-09 | 2024-05-17 | 2024-05-17 |  |  | 576 | PFP 786 N HAY LAKE RD |  | 2024-05-22 | 2024-07-05 | 2024-07-09 |  |  | 2024-07-05 | 33856 | James Lugo | 2024-05-17 | 2024-05-31 | 2024-05-22 | [19 empty] | ATT-7951 | MIN001.G0000234 | 2024-04-12 | 2024-04-16 | 2024-04-24 | 2024-04-25 | [7 empty] | 275 | 1 | 2024 | 4 | 18 | #REF! | 2024-09-13
ITG-131159 | 1 | Active | Jun | Nov | BBF | NA | BBF-82201-RT2-SEC6-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 6 | Eagan | 1982 | 2050 | [8 empty] | NA | NA | NA |  | NA | NA | 9831 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-05-24 | 2024-06-14 | 2024-06-12 | 2024-06-21 | 2024-06-21 | 2024-06-21 | 6211 | Joseph Smith | 2024-05-27 | 2024-05-27 | 2024-05-27 |  |  |  |  | 2024-07-23 | 2024-05-08 |  |  | In Construction | 2024-08-19 |  | 2024-09-11 | [6 empty] | 9/11 Zak-Locates called in. Nate 7/23 CAD approved and sent to permitting. NATE 7/22. 5/27 BBF Rt2 Sec 6 published in IQGEO; Path Creation footage =6,211'. | ATT-7952 | MIN001.G0000235 | 2024-06-21 | 2024-06-25 | 2024-06-28 | 2024-06-28 | [7 empty] | 276 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-130315 | 1 | Active | Jun |  | PSA | SFU | PSA-2601PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 6 | Eagan | 410 | 525 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-26 | JACOB | 2024-03-26 |  | 2024-04-07 | YES | 7412 | 26916 | 27404 | 54320 |  | 2024-04-19 | 2024-05-03 | 2024-05-02 |  |  | 864 | PFP 535 AIDAN CV |  | 2024-05-07 | 2024-05-24 | 2024-06-03 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 41285 | Christian Weller | 2024-05-02 | 2024-05-29 | 2024-06-05 |  |  |  |  | 2024-07-01 | 2024-07-09 | 1 out of 2 |  | In Construction | 2024-07-26 | [8 empty] | 7/25 To const for county placement6/25 returned to Cad for several missed corrections 6/17 returned to CAD/Junior 6/12-Nate 5/6 sent Christian PFP detail from fielder. | ATT-7953 | MIN001.G0000236 | 2024-04-12 | 2024-04-16 | 2024-04-24 | 2024-04-25 | [7 empty] | 277 | 1 | 2024 | 4 | 15 | #REF! | 2024-09-13
ITG-130317 | 1 | Active | Jun |  | PSA | SFU | PSA-2602PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 6 | Eagan | 497 | 495 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-26 | ERIK | 2024-03-26 |  | 2024-04-11 | YES | 0 | 2498 | 55610 | 58108 |  | 2024-04-19 | 2024-05-03 | 2024-05-03 |  |  | 864 | PFP 748 SADDLEWOOD DR |  | 2024-05-07 | 2024-05-24 | 2024-05-26 | 2024-07-16 | 2024-07-18 | 2024-05-26 | 43887 | James Lugo | 2024-05-03 | 2024-05-20 | 2024-05-07 | 2024-07-18 | 2024-08-01 |  |  | 2024-07-18 | 2024-06-07 | 1 out of 2 |  | In Construction | 2024-07-26 | [8 empty] | 7/25 To const for county placement7/24 resubmitted to the city Nate 7/18 Redline corrections made sent to Kaylie and permmitting to amend permit. Nate 7/16 Returned to CAD, Design, and Permitting for corrections. Nate 7/10 pending city | ATT-7954 | MIN001.G0000237 | 2024-04-12 | 2024-04-16 | 2024-04-24 | 2024-04-25 | [7 empty] | 278 | 1 | 2024 | 4 | 15 | #REF! | 2024-09-13
ITG-130373 | 1 | Active | Jun | Dec | PSA | SFU | PSA-2603PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 6 | Eagan | 475 | 469 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-27 | HUNTER | 2024-03-27 |  | 2024-04-12 | YES | 0 | 50 | 45548 | 45598 |  | 2024-04-24 | 2024-05-06 | 2024-05-06 |  |  | 864 | PFP 714 BRENTWOOD LN |  | 2024-05-17 | 2024-05-31 | 2024-06-20 | 2024-09-11 |  | 2024-06-19 | 45098 | Eric Lynn | 2024-05-06 | 2024-06-05 | 2024-07-08 | 2024-09-25 |  |  |  | 2024-06-20 | 2024-06-25 | [12 empty] | 9/11 Nate: CAD revision requested to bring up to current standards. 6/17 CAD req revision, sent to Junior for input. 6/10 - IQG pending update from gigapower about BBF job conflicting with PSA causing errors | ATT-7955 | MIN001.G0000238 | 2024-04-12 | 2024-04-16 | 2024-04-24 | 2024-04-25 | [7 empty] | 279 | 1 | 2024 | 4 | 15 | #REF! | 2024-09-13
ITG-130322 | 1 | Active | Jul |  | PSA | SFU | PSA-2604PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 6 | Eagan | 581 | 561 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-26 | JOSH | 2024-03-26 | 2024-04-20 | 2024-04-20 | YES | 2419 | 3773 | 48991 | 52764 | 90.8158 | 2024-05-08 | 2024-05-17 | 2024-05-15 |  |  | 864 | PFP 864 NORTHVIEW PARK RD |  | 2024-05-22 | 2024-07-16 | 2024-07-16 |  |  | 2024-07-15 | 44453 | Jordan Struck | 2024-05-15 | 2024-05-29 | 2024-05-21 | 2024-07-18 | 2024-08-05 | [16 empty] | PSA2606 being merged into this PSA | ATT-7956 | MIN001.G0000239 | 2024-04-12 | 2024-04-16 | 2024-04-24 | 2024-04-25 | [7 empty] | 280 | 1 | 2024 | 4 | 16 | #REF! | #N/A
ITG-136816 | 3 | HOLD FOR LATER |  |  | PSA | BCL | PSA-2605PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 6 | Eagan | 20 |  |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 | [50 empty] | 5/31 OH HOLD per Ted email .5/10 Moved back to active 4/29 Hold for BCL/MDU direction | ATT-8459 | MIN001.G0000315 | 2024-05-20 | 2024-05-20 | 2024-05-31 | 2024-05-31 | Stop | Stop | Stop | Stop | Stop | Stop |  | 281 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-136818 | 3 | NO BUILD |  |  | PSA | BCL | PSA-2606PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 6 | Eagan |  |  |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-06-26 | [47 empty] | 6/28 job to be canceled, combining with PSA-2604. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8460 | MIN001.G0000316 | 2024-05-31 | 2024-06-03 | 2024-06-11 | 2024-06-11 | Stop | Stop | Stop | Stop | Stop | Stop |  | 282 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-131160 | 1 | Active | Apr | Nov | BBF | NA | BBF-82201-RT2-SEC7-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 7 | Eagan | 1509 | 807 | [8 empty] | NA | NA | NA |  | NA | NA | 9752 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-05-17 | 2024-07-08 | 2024-05-29 | 2024-09-10 | 2024-09-12 | 2024-09-12 | 9853 | Joseph Smith | 2024-05-13 | 2024-05-17 | 2024-05-17 | 2024-09-12 |  |  |  | 2024-09-18 | 2024-07-08 | 2 out of 4 |  | In Construction | 2024-09-18 | [8 empty] | 9/10 CAD revision sent, requested Kaylie to check on permit, no IQGEO correction needed. 8/19 - IQGEO REVISIONS MADE NEW PATH CREATION FOOTAGE = 9,746'. 7/24 updated utilities for MNDOT 7/10 pending MNDOT & RR can build to RR pending 2 pipelines 5/29 CAD updates and MNDOT maps added ready for permit 5/28 emailed Joe with the CAD corrections 5/17 BBF Rt2 Sec 7 published in IQGEO; Path Creation footage = 9,803'. | ATT-7959 | MIN001.G0000242 | 2024-05-21 | 2024-05-21 | 2024-06-24 | 2024-06-25 | [7 empty] | 283 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-131169 | 1 | Active | Jul |  | PSA | SFU | PSA-2701PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 7 | Eagan | 450 | 332 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-26 | JAEGER | 2024-04-05 |  | 2024-04-11 | YES | 5769 | 115 | 31997 | 32112 |  | 2024-04-19 | 2024-05-03 | 2024-04-29 |  |  | 864 | PFP 682 HILLSIDE DR |  | 2024-04-30 | 2024-05-24 | 2024-07-03 | 2024-09-16 | 2024-09-23 | 2024-09-23 | 31084 | Jordan Struck | 2024-04-30 | 2024-05-23 | 2024-05-02 | 2024-09-25 |  |  |  | 2024-09-13 | 2024-07-09 | 1 out of 3 | [11 empty] | 9/13 Nate: Redline corrections have been made CAD has been sent to permitting. 6/17 returned to CAD/Junior for revisions | ATT-7960 | MIN001.G0000243 | 2024-04-12 | 2024-04-16 | 2024-04-24 | 2024-04-25 | [7 empty] | 284 | 1 | 2024 | 4 | 15 | #REF! | #N/A
ITG-136820 | 3 | HOLD FOR LATER |  |  | PSA | BCL | PSA-2702PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 7 | Eagan | 10 |  |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-07-01 | CODY | 2024-07-02 | 2024-07-09 | 2024-07-09 | YES | 0 | 236 | 3604 | 3840 | 384 | 2024-07-17 | 2024-08-02 | [35 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8461 | MIN001.G0000317 | 2024-05-20 | 2024-05-31 | 2024-06-27 | 2024-07-24 | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted - don’t go past MS1 | 285 | 1 | 2024 | 7 | 28 | #REF! | #N/A
ITG-136821 | 3 | HOLD FOR LATER |  |  | PSA | BCL | PSA-2703PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 7 | Eagan | 19 |  |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 | [50 empty] | 5/30 Hold for now per Ted mostly in MNDOT ROW 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8462 | MIN001.G0000318 | 2024-05-30 | 2024-05-30 | 2024-06-11 | 2024-06-11 | Stop | Stop | Stop | Stop | Stop | Stop |  | 286 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-136822 | 3 | HOLD FOR LATER |  |  | PSA | BCL | PSA-2704PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 7 | Eagan | 31 | 31 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-07-01 | ERIK | 2024-07-02 | 2024-07-07 | 2024-07-07 | YES | 0 | 282 | 5286 | 5568 | 179.6129 | 2024-07-12 | 2024-07-26 | 2024-07-16 |  |  | 144 | PFP 3388 MIKE COLLINS DR |  | 2024-07-23 | 2024-09-03 | [5 empty] | Jordan Struck | 2024-07-18 | 2024-07-25 | 2024-07-24 | [18 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8463 | MIN001.G0000319 | 2024-05-20 | 2024-05-31 | 2024-06-27 | 2024-07-24 | ? | [5 empty] | Design complete, which MS do we want to bill through? Per TED -don't go past MS1 | 287 | 1 | 2024 | 7 | 28 | #REF! | #N/A
ITG-122664 | 1 | Active | Jul |  | PSA | SFU/MDU | PSA-2705PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 7 | Eagan | 522 | 222 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-02-08 | JAEGER | 2024-02-12 |  | 2024-02-20 | YES | 3983 | 198 | 27696 | 27894 | 53.4368 | 2024-04-05 | 2024-04-22 | 2024-04-25 |  |  | 864 | PFP 851 WESCOTT SQ |  | 2024-07-01 | 2024-07-05 | 2024-04-24 | 2024-09-05 | 2024-09-11 | 2024-09-11 | 17418 | Jermaine Scott | 2024-04-24 | 2024-05-09 | 2024-05-02 | 2024-09-05 | 2024-09-10 |  |  | 2024-09-11 | 2024-05-10 | 2 out of 3 | [11 empty] | 9/16 Permit sent to the city, county isn't required done on the BBF. 9/11 Nate: Redline corrections complete CAD has been sent to permitting for submittal. 9/5 Nate: CAD print redlined and sent back to CAD for revision. 5/1 email'd Kaylie to begin permitting/ 'PERMIT COPY' 4/30 Forwarded final CAD to Jermaine | ATT-7961 | MIN001.G0000244 | 2024-04-12 | 2024-04-16 | 2024-04-24 | 2024-04-25 | [7 empty] | 288 | 1 | 2024 | 2 | 8 | #REF! | #N/A
ITG-132857 | 2 | Active | Jul | Nov | PSA | MDU | PSA-2706PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 7 | Eagan | 477 | 222 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-05-16 | BRIAN | 2024-05-17 | 2024-06-14 | 2024-06-14 | YES | 0 | 0 | 715 | 715 | 1.499 | 2024-06-05 | 2024-06-07 | 2024-06-07 |  |  | 288 | PFP 3420 GOLFVIEW DR |  | 2024-06-11 | 2024-07-03 | 2024-07-04 | 2024-09-27 |  | 2024-07-04 | 620 | Cheryl Turk | 2024-06-07 | 2024-06-14 | 2024-06-11 | 2024-09-10 | 2024-09-20 |  |  | 2024-07-08 | 2024-07-09 | 1 outof 2 | [11 empty] | 9/10 PSA cancelled, permit cancelled, future fiber added to the BBF RTE2 SEC7 for Nov turnup. 7/2 Returned to CAD for Corrections, Junior has reviewed.6/7 - LAYOUT COMPLETED ON SIMPLE PROJECT WITHOUT FIELDING PER CAD REQUEST.5/16 sent Junior/Henry a request for fielding easy TU with PSA 2705 | ATT-8070 | MIN001.G0000260 | 2024-04-16 | 2024-04-16 | 2024-05-31 | 2024-06-03 | [7 empty] | 289 | 1 | 2024 | 6 | 24 | #REF! | #N/A
ITG-131162 | 2 | Active | Jun | Nov | BBF | NA | BBF-82201-RT2-SEC8-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 8 | Eagan | 770 | 691 | [8 empty] | NA | NA | NA |  | NA | NA | 13347 | NA | NA | NA | NA | [8 empty] | 2024-08-05 | 2024-08-23 | 2024-08-28 | 2024-09-04 | 2024-09-09 | 2024-09-05 | 6783 | Joseph Smith | 2024-09-02 | 2024-09-02 | 2024-09-02 |  |  |  |  | 2024-09-16 |  | 1 out of 3 | [11 empty] | 9/16 Nate: CAD looks good I have moved this over to permitting. 9/2 IQGEO DESIGN COMPLETE. PATH CREATION FOOTAGE = 7,690'. | ATT-7962 | MIN001.G0000245 | 2024-09-11 | [10 empty] | 290 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-131170 | 2 | NO BUILD |  |  | PSA | 14 SFU/BCL | PSA-2801PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 8 | Eagan |  | 27 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-26 | SAM | 2024-04-03 |  | 2024-04-08 | YES | 3310 | 5 | 9391 | 9396 | #DIV/0! | [37 empty] | 7/1 PSA Merging into PSA2802. Commercial. 14 +/- SFU and BCL | ATT-7963 | MIN001.G0000246 | 2024-04-16 | 2024-04-16 | 2024-05-31 | 2024-06-03 | Stop | Stop | Stop | Stop | Stop | Stop |  | 291 | 1 | 2024 | 4 | 15 | #REF! | #N/A
ITG-132874 | 2 | Active | Jul |  | PSA | BCL | PSA-2802PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 8 | Eagan | 128 | 119 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-06-18 | JACOB | 2024-06-18 | 2024-06-20 | 2024-06-20 | YES | 0 | 8 | 15208 | 15216 | 118.875 | 2024-06-26 | 2024-07-15 | 2024-07-17 |  |  | 432 | PFP 660 LONE OAK RD |  | 2024-07-23 | 2024-08-21 | 2024-08-08 | 2024-09-23 | 2024-09-24 | 2024-09-24 | 16810 | James Lugo | 2024-08-09 | 2024-08-16 | 2024-08-12 | 2024-09-26 |  |  | X | 2024-09-26 | [13 empty] | 9/26 Nate: Print has been reviewed and approved and sent to permitting. Nate: CAD and Layout revisions needed, Sent redlines to CAD and Layout. 7/1 PSA2801 mergedinto this PSA5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8071 | MIN001.G0000261 | 2024-04-16 | 2024-04-16 | 2024-05-31 | 2024-06-03 | [7 empty] | 292 | 1 | 2024 | 6 | 25 | #REF! | #N/A
ITG-121716 | 3 | Active |  |  | PSA | BCL | PSA-2803PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 8 | Eagan | 183 | 171 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-02-23 | JAEGER | 2024-02-23 |  | 2024-03-01 | YES | 10037 | 159 | 31625 | 31784 | 173.6831 | 2024-03-04 | 2024-03-19 | 2024-04-08 |  |  | 576 | PFP 3025 LUNAR LN |  | 2024-06-03 | 2024-06-13 | 2024-06-13 | 2024-08-26 | 2024-09-23 | 9/20 v2 | 12618 | Jermaine Scott | 2024-05-14 | 2024-05-28 | 2024-05-16 | 2024-09-11 | 2024-09-11 |  | X | 2024-09-23 | 2024-09-24 | 1 out of 2 | [11 empty] | 9/23 Nate: Print has been reviewed and approved and sent to permitting. 8/14 Revision to CAD to sync with BBF 3/7 - SENT RXR CAD SENT TO PERMITTING 3/4/24 - RXR 696380G CAD REQUESTED. 4/3 - PER DON - HOLD ON DESIGN - POSSIBLE NO BUILD DUE TO BCL 5/28 Pulled back from permitting for review of BCL design by Junior/Henry. Ted has agreed to move forward w/job. 5/29 City has requested section to be removed from the job forwarded to Junior/Henry. | ATT-8458 | MIN001.G0000314 | 2024-04-16 | 2024-04-16 | 2024-06-27 | 2024-07-19 | [7 empty] | 293 | 1 | 2024 | 3 | 9 | #REF! | #N/A
ITG-132909 | 2 | NO BUILD |  |  | PSA | BCL | PSA-2804PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 8 | Eagan | 42 |  |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 | [50 empty] | 6/21 PSA has been combined into PSA2904 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL 6/18 - ABSORBED 2904PA IN EAGAN | ATT-8074 | MIN001.G0000262 | 2024-04-16 | 2024-04-16 | 2024-05-31 | 2024-06-03 | Stop | Stop | Stop | Stop | Stop | Stop |  | 294 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-132910 | 2 | Active | Jul | Nov | PSA | BCL/MDU | PSA-2805PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 8 | Eagan | 420 | 374 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-06-18 | HANNAH | 2024-06-20 | 2024-07-12 | 2024-07-12 | YES | 0 | 198 | 11219 | 11417 | 27.1833 | 2024-07-19 | 2024-08-05 | 2024-08-07 |  |  | 576 | PFP 3305 LEXINGTON AVE S |  | 2024-08-12 | 2024-09-18 | 2024-08-22 |  |  | 2024-08-22 | 11348 | Jermaine Scott | 2024-08-29 | 2024-09-12 | 2024-08-30 | [18 empty] | 7/1 job area is to be renamed PSA-2804, the POF HH location was moved and this job is now in section 8 rather than in section 9. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8079 | MIN001.G0000267 | 2024-04-16 | 2024-04-16 | 2024-05-31 | 2024-06-03 | [7 empty] | 295 | 1 | 2024 | 7 | 28 | #REF! | #N/A
ITG-145806 | 2 | HOLD FOR LATER |  |  | PSA | BCL | PSA-2806PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 8 | Eagan | 162 | 159 | [8 empty] | 2024-06-28 | CODY | 2024-06-28 | 2024-07-09 | 2024-07-09 | YES | 0 | 639 | 11756 | 12395 |  | 2024-07-16 | 2024-07-31 | 2024-07-31 |  |  | 288 | PFP 2945 COMMERS DR | [30 empty] | 7/1 now consists PSA2901 and PSA2902 as the BBF route was moved to section 8. | ATT-8881 | MIN001.G0000410 | 2024-07-29 | 2024-07-30 | 2024-08-08 | 2024-08-08 | Stop | Stop | Stop | Stop | Stop | Stop | LU count on budget sheet is 126 instead of 162 Per Ted - don’t go past MS1 | 296 | 1
ITG-131164 | 1 | Active | Aug | Nov | BBF | NA | BBF-82201-RT2-SEC9-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 9 | Eagan | 281 | 168 | [8 empty] | NA | NA | NA |  | NA | NA | 0 | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA |  | 2024-08-05 | 2024-08-16 | 2024-08-22 |  | 2024-08-22 | 2024-08-16 | 5578 | Joseph Smith | 2024-09-02 | 2024-09-02 | 2024-09-02 |  |  |  |  | 2024-09-17 | 2024-09-18 | 1 | 2024-09-18 | [10 empty] | 9/17 Nate: Print has been reviewed and approved and sent to permitting. 9/1 IQGEO DESIGN COMPLETED. PATH CREATION FOOTAGE = 5,578'. | ATT-7957 | MIN001.G0000240 | 2024-09-24 | 2024-09-25 | [9 empty] | 297 |  | #VALUE! | #VALUE! | #VALUE! | Permit Complete | #N/A
ITG-132912 | 2 | NO BUILD |  |  | PSA | BCL | PSA-2901PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 9 | Eagan |  |  |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-06-28 | [47 empty] | 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8076 | MIN001.G0000264 | 2024-04-16 | 2024-04-16 | 2024-05-31 | 2024-06-03 | Stop | Stop | Stop | Stop | Stop | Stop |  | 298 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-132913 | 2 | NO BUILD |  |  | PSA | BCL | PSA-2902PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 9 | Eagan |  |  |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | cancel | [47 empty] | 5/31 OH HOLD per Ted's email 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-8077 | MIN001.G0000265 | 2024-04-16 | 2024-04-16 | 2024-05-31 | 2024-05-31 | Stop | Stop | Stop | Stop | Stop | Stop |  | 299 | 1 | 1900 | 1 | 0 | #REF! | #N/A
ITG-126043 | 1 | Active | Jul |  | PSA | SFU | PSA-2903PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 9 | Eagan | 109 | 109 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-03-06 | HUNTER | 2024-03-08 |  | 2024-03-13 | YES |  | 117 | 9407 | 9524 | 87.3761 | 2024-04-05 | 2024-04-19 | 2024-04-22 |  |  |  | PFP 2876 Lexington Ave S. |  | 2024-07-01 | 2024-07-12 | 2024-04-26 | 2024-06-28 | 2024-07-26 | 2024-07-25 | 7102 | Jordan Struck | 2024-04-22 | 2024-05-06 | 2024-04-24 | 2024-09-11 |  |  |  |  | 2024-05-22 | 1 out of 2 | [11 empty] | 6/28 CAD revision for overlap of BBF & PSA per Junior | ATT-7958 | MIN001.G0000241 | 2024-04-12 | 2024-04-30 | 2024-05-06 | 2024-05-07 | [7 empty] | 300 | 1 | 2024 | 3 | 11 | #REF! | #N/A
ITG-132914 | 2 | Active | Jul |  | PSA | BCL | PSA-2904PA-EAGNMN82-CHARLIE | EAGNMN82 | RTE #2 | BBF RTE 2 SEC 9 | Eagan | 62 | 59 |  | Tammi Baker |  | 2024-01-04 | Christian Weller | 2024-01-19 |  |  | 2024-06-28 | CODY | 2024-06-28 | 2024-07-09 | 2024-07-09 | YES | 0 | 186 | 1141 | 1327 | 21.4032 | 2024-07-16 | 2024-08-06 | 2024-08-07 |  |  | 288 | PFP 2859 LEXINGTON AVE S |  | 2024-08-12 | 2024-09-27 | 2024-09-27 |  |  | 2024-09-27 | 1772 | Jermaine Scott | 2024-08-09 | 2024-08-23 | 2024-08-14 | 2024-09-11 | 2024-09-13 |  | X | [14 empty] | 6/21 PSA2804 has been combine dinto this PSA | ATT-8078 | MIN001.G0000266 | 2024-04-16 | 2024-04-16 | 2024-05-31 | 2024-06-03 | [7 empty] | 301 | 1 | 2024 | 7 | 28 | #REF! | #N/A
ITG-135834 | 1 | Active | Jul |  | BBF |  | BBF-PI101-RT1-SEC1-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 1 | Eden Prairie | 1216 |  |  | Joseph Smith | [25 empty] | 2024-05-31 | 2024-08-15 | 2024-08-08 | 2024-08-09 | 2024-09-12 | 2024-09-12 |  | Joseph Smith | 2024-09-25 | [6 empty] | 2024-09-19 | [13 empty] | 9/19 Nate: Print has been reviewed and approved and sent to permitting. 8/8 MJ - MNDOT And Route 3 tie in assigned to CAD, we should still make 8/15 DD still, 8/6 MJ - Moving to East side of Shady Oak to avoid future Trail on West Side, adjusted due date to account for rework | [13 empty] | 302 |  |  |  |  | #REF! | #N/A
ITG-134578 | 3 | HOLD FOR LATER |  |  | PSA | BCL/SFU | PSA-1101PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 1 | Eden Prairie | 608 |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-07-02 | JAEGER | 2024-07-08 | 2024-07-12 | 2024-07-11 | YES | 7949 | 61 | 18450 | 18511 | 30.4457 | 2024-07-17 | 2024-08-06 | [7 empty] | 2024-09-12 | [27 empty] | 7/30 Do not proceed per Ted , Don to verifyPSA1102 merged into this PSA | ATT-8882 | MIN001.G0000411 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-09-20 | ? | [5 empty] | Per Ted - PSA-1101 is all BCL's. Do not proceed past MS1 unless instructed to do so by Gigapower | 303 |  | 2024 | 7 | 28 | #REF! | #N/A
ITG-134588 | 3 | NO BUILD |  |  | PSA | BCL/MDU | PSA-1102PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 1 | Eden Prairie |  |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller | [51 empty] | PSA is merging into PSA1101 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 304 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134589 | 3 | HOLD FOR LATER |  |  | PSA | SFU/MDU/BCL | PSA-1103PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 1 | Eden Prairie | 608 |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-07-02 | HANNAH | 2024-07-08 | 2024-07-23 | [5 empty] | 0 | 0 | [37 empty] | 7/30 Do not proceed per Ted, Don to verify Bloomington PSA4807 merged into this PSA | ATT-8883 | MIN001.G0000412 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-09-20 | Stop | Stop | Stop | Stop | Stop | Stop |  | 305 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134591 | 3 | NO BUILD |  |  | PSA | SFU/BCL | PSA-1105PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 1 | Eden Prairie |  |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller | [51 empty] | 7/1 PSA has been combined into PSA3109 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 306 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136795 | 3 | NO BUILD |  |  | PSA | MDU | PSA-1106PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 1 | Eden Prairie |  |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller | [51 empty] | 7/2 COMBINED WITH 1104, JOB CANCEL.5/10 Moved back to active 4/29 Hold for BCL/MDU direction | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 307 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135838 | 1 | Active |  |  | BBF |  | BBF-PI101-RT1-SEC2-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 2 | Eden Prairie | 1434 |  |  | Joseph Smith | [25 empty] | 2024-07-23 | 2024-08-05 | 2024-08-05 | 2024-08-27 |  | 2024-08-05 | [37 empty] | 308 |  |  |  |  | #REF! | #N/A
ITG-134599 | 4 | HOLD FOR LATER |  |  | PSA | BCL | PSA-1201PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 2 | Eden Prairie | 119 | 114 |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-07-16 | SAM | 2024-07-18 | 2024-07-22 | 2024-07-22 | YES | 0 | 5 | 9390 | 9395 |  | 2024-07-25 | 2024-08-06 | 2024-08-09 |  |  | 288 | PFP 11200 W 78TH ST |  | 2024-08-21 | 2024-10-03 | [5 empty] | Cheryl Turk | 2024-08-12 | 2024-08-26 | 2024-08-23 | [18 empty] | Bloomington PSA4806 merged into this PSA | ATT8855 | MIN001.G0000413 | 2024-09-05 | 2024-09-24 |  |  | ? | [5 empty] | Design complete, which MS do we want to bill through? | 309 |  | 2024 | 7 | 30 | #REF! | #N/A
ITG-136766 | 1 | Active |  |  | PSA | SFU/MDU | PSA-1202PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 2 | Eden Prairie | 628 | 488 |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-05-22 | SAM | 2024-05-24 | 2024-06-05 | 2024-06-05 | YES | 0 | 1821 | 2810 | 4631 | 7.3742 | 2024-06-12 | 2024-06-21 | 2024-06-24 |  |  | 576 | PFP 8415 ANNAPOLIS WAY | 2024-06-24 | 2024-06-24 | 2024-08-01 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-26 | 3196 | Jermaine Scott | 2024-06-24 | 2024-07-01 | 2024-06-25 | 2024-08-06 | 2024-08-13 |  |  | 2024-08-05 | [13 empty] | 8/5 Nate Revision approved and sent to permiting for amendment and resubmittal. 7/26 Michael Revised to address Eden Variances, ready for final review 7/25 City HH requirement correction 7/24 ready for review5/10 Moved back to active 4/29 Hold for BCL/MDU direction Original Drafter Skyde Subcontractor | ATT-8811 | MIN001.G0000353 | 2024-07-18 | 2024-07-30 | 2024-08-15 | 2024-08-15 | [7 empty] | 310 | 1 | 2024 | 6 | 23 | #REF! | #N/A
ITG-134600 | 2 | Active |  |  | PSA | MIX | PSA-1203PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 2 | Eden Prairie | 687 | 687 |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-07-16 | CODY | 2024-07-18 | 2024-07-30 | 2024-07-30 | YES | 0 | 160 | 4496 | 4656 | 6.7773 | 2024-08-01 | 2024-08-19 | 2024-08-23 |  |  | 864 | PFP 8580 GWENETH LANE |  | 2024-08-27 | 2024-10-10 | 2024-09-12 |  |  | 2024-09-12 | 2905 | James Lugo | 2024-09-03 | 2024-09-17 | 2024-09-04 | [19 empty] | ATT8886 | MIN001.G0000414 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-09-20 | [7 empty] | 311 |  | 2024 | 7 | 31 | #REF! | #N/A
ITG-135841 | 1 | Active |  |  | BBF |  | BBF-PI101-RT1-SEC3-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 3 | Eden Prairie | 1055 |  |  | Joseph Smith | [7 empty] | JOSH | 2024-05-10 | 2024-05-19 | 2024-05-19 |  | 21000 | 0 | 0 | 0 | 0 | [8 empty] | 2024-07-23 | 2024-10-04 | [41 empty] | 312 |  |  |  |  | #REF! | #N/A
ITG-134602 | 1 | Active |  |  | PSA | School | PSA-1301PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 3 | Eden Prairie | 1 |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-07-16 | NA | NA | NA | NA | NA | NA | NA | [40 empty] | 7/18 Fielding not needed, route was fielded on BBF SEC 3. JOB AREA IS ONLY A SCHOOL, NO SFUs | ATT-8887 | MIN001.G0000415 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-08-15 | [7 empty] | 313 | 1 | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-134604 | 1 | No Build - Ex Comp |  |  | PSA | SFU | PSA-1302PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 3 | Eden Prairie | 182 |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-05-03 | SAM | 2024-05-03 | 2024-05-20 | [44 empty] | CONSTUCTION JUST COMPLETED BY EXISTING COMPETITION 5/10. | ATT-8813 | MIN001.G0000355 | 2024-07-18 | 2024-07-30 | 2024-09-09 | 2024-09-16 | Stop | Stop | Stop | Stop | Stop | Stop |  | 314 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134605 | 2 | Active |  |  | PSA | BCL | PSA-1303PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 3 | Eden Prairie | 53 | 44 |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-07-16 | CODY | 2024-07-18 | 2024-07-29 | 2024-07-29 | YES | 0 | 2167 | 1780 | 3947 | 74.4717 | 2024-07-30 | 2024-08-15 | 2024-08-23 |  |  | 288 | PFP 12700 ANDERSON LAKES PKWY |  | 2024-08-26 | 2024-10-03 | 2024-09-03 |  |  | 2024-09-03 | 3982 | Spencer Lynn | 2024-09-04 | 2024-09-20 | 2024-09-20 | [19 empty] | ATT-8888 | MIN001.G0000416 | 2024-07-18 | 2024-07-30 | 2024-08-15 | 2024-08-15 | [7 empty] | 315 | 1 | 2024 | 7 | 31 | #REF! | #N/A
ITG-134606 | 1 | No Build - Ex Comp |  |  | PSA | SFU | PSA-1304PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 3 | Eden Prairie | 378 | 252 |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  | 2024-05-06 | 2024-05-06 | 2024-05-08 | CODY | 2024-05-10 | 2024-05-19 | 2024-05-19 | YES | 0 | 2965 | 26499 | 29464 | 77.9471 | 2024-06-07 | 2024-06-14 | 2024-06-17 |  |  | 288 | PFP 12101 SUNNYBROOK RD |  | 2024-06-17 | 2024-07-17 | 2024-07-11 | 2024-07-25 | 2024-07-31 | 2024-07-31 | 22085 | Jordan Struck | 2024-06-28 | 2024-07-02 | 2024-06-23 | 2024-08-02 | 2024-08-12 |  |  | 2024-08-06 | [13 empty] | 8/9 fielder went back out and confirmed there is existing competition with FTTH in this entire PSA area. 8/6 Nate Revision approved and sent to permiting for amendment and resubmittal. 7/25 City HH requirement correction PSA1802 merging into this PSA. | ATT-8889 | MIN001.G0000417 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-09-20 | ? |  | Stop | Stop | Stop | Stop | Design and CAD complete, which MS do we want to bill through? | 316 |  | 2024 | 5 | 21 | #REF! | #N/A
ITG-134607 | 1 | Active |  |  | PSA | SFU/BCL | PSA-1305PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 3 | Eden Prairie | 441 | 293 |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  | 2024-05-06 | 2024-05-06 | 2024-05-08 | JAEGER | 2024-05-10 | 2024-05-16 | 2024-05-16 | YES | 0 | 1069 | 18025 | 19094 | 43.2971 | 2024-05-31 | 2024-06-10 | 2024-06-05 |  |  | 432 | PFP 9303 COLD STREAM LN |  | 2024-06-06 | 2024-07-01 | 2024-07-01 | 2024-09-17 | 2024-09-19 | 2024-09-19 | 18567 | James Lugo | 2024-06-06 | 2024-06-13 | 2024-06-07 | 2024-08-02 | 2024-08-08 |  |  | 2024-08-02 | 2024-08-02 | [12 empty] | 9/18 MJ, This has the purgatory creek crossing, CAD updates needed to show special requirements such as 100 year flood zone,8/9 fielder went back out and confirmed there is existing competition with FTTH in the northern half of the PSA area. 8/2 PSA1307 has been merged into this PSA. 8/1 final review forwarded to Kaylie for permitting 7/29 Nate Redlines corrected and sent over to Kaylie and Permitting for submittal. 7/25 Nate: Second Revision needed sent back to CAD for corrections. 7/25 City HH requirement correction 7/1 pending Junior review of corrections6/28 sent back to CAD for corrections w/Juniors. | ATT-8890 | MIN001.G0000418 | 2024-07-18 | 2024-07-30 | 2024-09-09 | 2024-09-16 | [6 empty] | Need to account for new Living unit count on MS1 submittal, PSA was merged into this one. | 317 |  | 2024 | 5 | 20 | #REF! | #N/A
ITG-134608 | 2 | PROJECT CANCEL |  |  | PSA | MDU | PSA-1306PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 3 | Eden Prairie |  |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-07-16 | NA | NA | NA | NA | NA | NA | NA | [40 empty] | 8/2 This PSA has been merged into PSA1901. 7/18 Fielding not needed, route was fielded on BBF SEC 3 and PSA-1901. | ATT-8891 | MIN001.G0000419 | 2024-07-18 | 2024-07-30 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Project cancel - area merged to another psa | 318 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-134609 | 2 | PROJECT CANCEL |  |  | PSA | SFU/BCL | PSA-1307PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 3 | Eden Prairie |  |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-07-16 | ERIK | 2024-07-18 | 2024-07-21 | 2024-07-21 | YES | 0 | 4128 | 1103 | 5231 |  | 2024-07-26 | 2024-08-07 | [7 empty] | 2024-10-03 | [27 empty] | 8/2 This PSA merged into 1305. | ATT-8892 | MIN001.G0000420 | 2024-07-18 | 2024-07-30 | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Canceled | Project cancel - area merged to another psa | 319 |  | 2024 | 7 | 30 | #REF! | #N/A
ITG-135843 | 1 | Active |  |  | BBF |  | BBF-PI101-RT1-SEC4-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 4 | Eden Prairie | 1691 |  |  | Joseph Smith | [25 empty] | 2024-07-23 | 2024-08-09 | 2024-08-06 |  |  | 2024-08-06 | [37 empty] | 320 |  |  |  |  | #REF! | #N/A
ITG-134610 | 1 | No Build - Ex Comp |  |  | PSA | SFU/MDU | PSA-1401PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 4 | Eden Prairie | 414 |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-05-03 | JAEGER | 2024-05-03 | NA | [44 empty] | CONSTUCTION JUST COMPLETED BY EXISTING COMPETITION 5/10. | ATT-8814 | MIN001.G0000356 | 2024-07-18 | 2024-08-15 | 2024-09-10 | 2024-09-16 | Stop | Stop | Stop | Stop | Stop | Stop |  | 321 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134611 | 2 | Active |  |  | PSA | MDU/BCL | PSA-1402PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 4 | Eden Prairie | 633 | 615 |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-07-16 | JOSH | 2024-07-18 | 2024-08-01 | 2024-07-30 | YES | 0 | 1300 | 3100 | 4400 | 6.951 | 2024-08-01 | 2024-08-19 | 2024-08-23 |  |  | 864 | PFP 11225 WESTWIND DR |  | 2024-08-27 | 2024-10-10 | 2024-09-03 |  |  | 2024-09-03 | 3602 | Jermaine Scott | 2024-09-04 | 2024-09-11 | 2024-09-06 | [19 empty] | ATT-8893 | MIN001.G0000421 | 2024-07-18 | 2024-07-30 | 2024-08-22 | 2024-08-23 | [7 empty] | 322 | 1 | 2024 | 7 | 31 | #REF! | #N/A
ITG-134612 | 1 | No Build - Ex Comp |  |  | PSA | MDU/SFU | PSA-1403PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 4 | Eden Prairie | 644 |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-05-03 | HUNTER | 2024-05-03 | NA | [44 empty] | CONSTUCTION JUST COMPLETED BY EXISTING COMPETITION 5/10. | ATT-8815 | MIN001.G0000357 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-09-20 | Stop | Stop | Stop | Stop | Stop | Stop |  | 323 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135844 | 1 | No Build - Ex Comp |  |  | BBF |  | BBF-PI101-RT1-SEC5-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 5 | Eden Prairie | 442 |  |  | Joseph Smith | [26 empty] | NA | [27 empty] | 7/25 Backbone route and permit not needed for section 5, the PSAs went no build. | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 324 |  |  |  |  | #REF! | #N/A
ITG-134613 | 1 | No Build - Ex Comp |  |  | PSA | SFU/ 5 BCL | PSA-1501PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 5 | Eden Prairie | 442 |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  | 2024-05-06 | 2024-05-06 | 2024-05-06 |  |  | NA | [44 empty] | CONSTUCTION IN PROGRESS BY INTREPID EXISTING COMPETITION 5/10. | ATT-8816 | MIN001.G0000358 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-09-20 | Stop | Stop | Stop | Stop | Stop | Stop |  | 325 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135845 | 1 | NO BUILD |  |  | BBF |  | BBF-PI101-RT1-SEC6-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 6 | Eden Prairie | 686 |  |  | Joseph Smith | [26 empty] | NA | [27 empty] | 7/25 Backbone route and permit not needed for section 6, the PSAs went no build. | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 326 |  |  |  |  | #REF! | #N/A
ITG-134614 | 1 | No Build - Ex Comp |  |  | PSA | SFU | PSA-1601PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 6 | Eden Prairie | 677 |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  | 2024-05-06 | 2024-05-06 | NA |  |  | NA | [44 empty] | CONSTUCTION HAS NOT YET STARTED, PROPOSED WHITE LINES AND BLUE STAKE FRESH ON THE GROUND 5/10 | ATT-8817 | MIN001.G0000359 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-09-20 | Stop | Stop | Stop | Stop | Stop | Stop |  | 327 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134615 | 2 | HOLD FOR LATER |  |  | PSA | SFU/BCL | PSA-1602PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 6 | Eden Prairie | 9 |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | cancel? | [47 empty] | 7/25 trying to see if we can absorb this job into PSA-1701, pending response from layout team. | ATT-8894 | MIN001.G0000422 | 2024-09-05 | 2024-09-23 |  |  | Stop | Stop | Stop | Stop | Stop | Stop | 9/5 Per Ted "ok to resubmit" Per Ted - PSA-1602PA-EDPRMNPI-CHARLIE - All business, MNDOT ROW, difficult build. Cancelled PSA | 328 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135846 | 1 | NO BUILD |  |  | BBF |  | BBF-PI101-RT1-SEC7-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 7 | Eden Prairie | 606 |  |  | Joseph Smith | [25 empty] | 2024-08-06 | 2024-08-23 | 2024-08-22 |  |  | 2024-08-19 | [23 empty] | No build due to creek and existing comp | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 329 |  |  |  |  | #REF! | #N/A
ITG-134621 | 1 | No Build - Ex Comp |  |  | PSA | SFU | PSA-1701PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 7 | Eden Prairie | 606 |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  | 2024-05-06 | 2024-05-06 | 2024-05-09 | DREW | 2024-05-10 | 2024-05-28 | 2024-05-28 | YES | 0 | 2632 | 33846 | 36478 | 60.1947 | 2024-06-10 | 2024-06-28 | 2024-06-28 |  |  | 864 | PFP 10320 FRANLO RD | 2024-07-01 | 2024-07-03 | 2024-08-23 | [27 empty] | 8/14 MJ - 1602 was proposed to be combined and that decision is still pending approval, 8/9 fielder went back out and confirmed there is existing competition with FTTH in this entire PSA area. 7/15 - moved ECD out due to conduit corrections needed on other jobs | ATT-8895 | MIN001.G0000423 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-08-19 | ? | [5 empty] | Field and Layout complete, which MS do we want to bill through? | 330 | 1 | 2024 | 5 | 22 | #REF! | #N/A
ITG-135847 | 1 | NO BUILD |  |  | BBF |  | BBF-PI101-RT1-SEC8-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 8 | Eden Prairie | 431 |  |  | Joseph Smith | [25 empty] | 2024-08-08 | 2024-08-16 | 2024-08-12 |  |  | 2024-08-12 | [23 empty] | No build due to creek and existing comp | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 331 |  |  |  |  | #REF! | #N/A
ITG-134617 | 1 | No Build - Ex Comp |  |  | PSA | SFU | PSA-1801PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 8 | Eden Prairie | 431 | 293 |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  | 2024-05-06 | 2024-05-06 | 2024-05-08 | JOSH | 2024-05-08 | 2024-05-30 | 2024-05-30 | YES | 6129 | 962 | 31165 | 32127 | 74.5406 | 2024-06-11 | 2024-06-24 | 2024-06-21 |  |  | 576 | PFP 11081 BLOSSOM RD | 2024-06-24 | 2024-06-26 | 2024-07-12 | 2024-07-10 |  |  | 2214-11-06 | 24294 | James Lugo | 2024-06-24 | 2024-07-03 | 2024-06-28 |  |  |  | X | [14 empty] | 8/9 fielder went back out and confirmed there is existing competition with FTTH in this entire PSA area. 8/2 portion of this PSA with 73 LU merged into PSA1901. 7/25 City HH requirement correction 7/10 was marked up layout used? | ATT-8896 | MIN001.G0000424 | 2024-07-18 | 2024-07-30 | 2024-08-22 | 2024-08-23 | ? | [5 empty] | Design and CAD complete, which MS do we want to bill through? | 332 | 1 | 2024 | 5 | 22 | #REF! | #N/A
ITG-134622 | 2 | NO BUILD |  |  | PSA | BCL | PSA-1802PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 8 | Eden Prairie |  |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller | [51 empty] | merged into PSA1304 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 333 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135849 | 1 | Active |  |  | BBF |  | BBF-PI101-RT1-SEC9-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 9 | Eden Prairie | 1191 |  |  | Joseph Smith | [25 empty] | 2024-08-08 | 2024-08-16 | 2024-08-14 |  |  | 2024-08-15 | [37 empty] | 334 |  |  |  |  | #REF! | #N/A
ITG-134623 | 3 | Active | Aug | Nov | PSA | SFU | PSA-1901PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 9 | Eden Prairie | 241 | 345 |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  | 2024-05-06 | 2024-05-06 | 2024-05-08 | JACOB | 2024-05-08 | 2024-05-12 | 2024-05-12 | YES | 2086 | 6 | 24544 | 24550 | 101.8672 | 2024-05-29 | 2024-06-13 | 2024-06-05 |  |  | 432 | PFP 9890 HOMEWARD HILLS RD |  | 2024-06-11 | 2024-07-09 | 2024-07-09 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 17044 | Jermaine Scott | 2024-06-06 | 2024-06-14 | 2024-07-12 | 2024-07-29 | 2024-08-16 |  |  | 2024-07-29 | 2024-07-31 | 1 out of 2 |  | In Construction | 2024-08-23 | [8 empty] | 8/23 sent the job to const for Hennipen County portion permit approved.8/2 PSA 1306 and a portion of PSA1801 have been merged into this PSA. 7/29 Nate: Redline corrections made and snet to Kaylie and the Permitting team. 7/29 Nate: Reviewed CAD had minor corrections on the HH placements between P/L returned to CAD. 7/25 City HH requirement correction 7/8 sent corrections to Tyler | ATT-8898 | MIN001.G0000425 | 2024-07-18 | 2024-07-30 | 2024-08-22 | 2024-08-23 | [6 empty] | Need to account for new Living unit count on MS1 submittal, PSA was merged into this one. | 335 | 1 | 2024 | 5 | 20 | #REF! | #N/A
ITG-134624 | 1 | Active |  |  | PSA | SFU | PSA-1902PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 9 | Eden Prairie | 452 | 432 |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  | 2024-05-06 | 2024-05-06 | 2024-05-08 | SAM | 2024-05-08 | 2024-05-16 | 2024-05-16 | YES | 1626 | 767 | 36348 | 37115 | 82.1128 | 2024-06-03 | 2024-06-17 | 2024-06-17 |  |  | 576 | PFP 12101 JASPER LN |  | 2024-06-18 | 2024-07-18 | 2024-07-10 | 2024-07-25 | 2024-07-30 | 2024-07-30 | 32532 | James Lugo | 2024-06-18 | 2024-07-02 | 2024-06-20 | 2024-07-11 | 2024-07-15 |  |  | 2024-07-30 | 2024-08-01 | [12 empty] | 7/25 City HH requirement correction 7/16 Forwarded to Kaylie for permitting. 7/11 returned corrections to CAD | ATT-8899 | MIN001.G0000426 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-08-19 | [7 empty] | 336 | 1 | 2024 | 5 | 20 | #REF! | #N/A
ITG-135744 | 1 | Active | Sep | Dec | PSA | SFU | PSA-1903PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 9 | Eden Prairie | 498 | 439 |  | Aubre Thompson |  | 2024-05-06 |  |  | 2024-05-06 | 2024-05-06 | 2024-05-08 | HUNTER | 2024-05-08 | 2024-05-22 | 2024-05-22 | YES | 0 | 4206 | 46313 | 50519 | 101.4438 | 2024-05-31 | 2024-06-12 | 2024-06-12 |  |  | 864 | PFP 10415 HOMEWARD HILLS RD |  | 2024-06-17 | 2024-07-09 | 2024-07-09 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 43718 | James Lugo | 2024-06-12 | 2024-06-20 | 2024-06-20 | 2024-07-12 | 2024-07-12 |  |  | 2024-07-30 | 2024-08-01 | [12 empty] | 7/30 Appreved design, forwarded to Kaylie for permitting 7/29 Nate: Reviewed CAD had minor corrections on the HH placements between P/L returned to CAD. 7/25 City HH requirement correction 7/3 LAYOUT UPDATED 7/2 CAD corrections sent to CAD 7/1 Layout corrections sent to Layout | ATT-8900 | MIN001.G0000427 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-08-19 | [7 empty] | 337 | 1 |  |  |  | #REF! | #N/A
ITG-148811 | 1 | Active |  |  | BBF |  | BBF-PI101-RT1-SEC11-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 11 | Eden Prairie | [29 empty] | 2024-07-19 | 2024-07-30 | 2024-07-26 | 2024-09-25 |  | 2024-09-11 | [9 empty] | 2024-09-19 |  | 1 out of 4 | [11 empty] | 9/25 MNDOT requested corrections of CAD 9/19 Nate: Print has been reviewed and approved and sent to permitting. 8/15 Revision Req'd it to reroute to better MNDOT crossing location, 8/6 MJ - Moving to East side of Shady Oak to avoid future Trail on West Side | [13 empty] | 338 |  |  |  |  | #REF! | #N/A
ITG-134590 | 3 | HOLD FOR LATER |  |  | PSA | BCL/MDU | PSA-1111PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 11 | Eden Prairie | 520 | 519 |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-07-02 | HUNTER | 2024-07-08 | 2024-07-09 | 2024-07-09 | YES | 0 | 40 | 4471 | 4511 | 8.675 | 2024-07-19 | 2024-08-07 | 2024-08-09 |  |  | 864 | PFP 6385 OLD SHADY OAK RD |  | 2024-08-14 | 2024-09-19 | [5 empty] | James Lugo | 2024-08-20 | 2024-08-28 | 2024-08-22 | [18 empty] | Job cancelled in CMPM by Ted, on hold for further instruction. Previously PSA1104 | ATT-8831 | MIN001.G0000360 | 2024-09-05 | 2024-09-23 |  |  | Stop | Stop | Stop | Stop | Stop | Stop | 9/5 Per Ted - ok to resubmit. Moved job back to active. Has been cancelled in CMPM | 339
ITG-148812 |  | Active |  |  | BBF |  | BBF-PI101-RT1-SEC12-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 12 | Eden Prairie | [29 empty] | 2024-07-17 | 2024-07-24 | 2024-07-23 | 2024-08-01 | 2024-08-02 | 2024-08-02 | [9 empty] | 2024-08-26 | 2024-09-06 | 1 out of 3 | [11 empty] | 8/26 Nate CAD print reviewed for MNDOT changes and corrections made, resubmitted to Permitting for amendedment. 8/1 MJ MNDOT recjection to correct 7/26 returned to CAD for revision, due 7/29. | [13 empty] | 340
ITG-134595 | 1 | Active |  |  | PSA | SFU/BCL | PSA-1112PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 11 | Eden Prairie | 251 | 268 |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | 2024-04-24 | CODY | 2024-05-02 | 2024-05-21 | 2024-05-20 | [6 empty] | 2024-05-23 | 2024-06-04 | 2024-06-05 |  |  | 576 | PFP 6475 ROWLAND RD |  | 2024-06-07 | 2024-07-05 | 2024-07-02 | 2024-08-28 | 2024-08-29 | 2024-07-02 | 36636 | Jordan Struck | 2024-06-06 | 2024-06-13 | 2024-06-11 | 2024-09-04 | 2024-09-12 |  |  | 2024-08-30 |  | 1 out of 2 | [11 empty] | 8/30 Nate: Redline corrections have been made I have move this over to permitting. 8/28 NATE: REDLINES SENT TO CAD FOR MINOR REVISIONS.7/25 City HH requirement correction 7/12 need to change PSA number to be PSA-1112, previously PSA1107. | ATT-8832 | MIN001.G0000361 | 2024-07-18 | 2024-07-30 | 2024-08-22 | 2024-08-23 | [7 empty] | 341 | 1 | 2024 | 5 | 21
ITG-148813 |  | Active |  |  | BBF |  | BBF-PI101-RT1-SEC13-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 13 | Eden Prairie | [29 empty] | 2024-07-17 | 2024-07-19 | 2024-07-19 | 2024-09-11 | 2024-09-11 | 2024-09-11 | [9 empty] | 2024-08-08 | 2024-08-08 | [12 empty] | 8/8 approved and forwarded to Kaylie for permit 8/6 MJ - Moving to East side of Shady Oak , 7/26 sent to Kaylie for permitting 7/25 HH add requested w/Joshua | [13 empty] | 342
ITG-134597 | 1 | Active |  |  | PSA | SFU/BCL | PSA-1113PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #1 | BBF RTE 1 SEC 11 | Eden Prairie | 31 |  |  | Joseph Smith |  | 2024-01-03 | Christian Weller |  |  |  | N/A | [47 empty] | JOB AREA IS A SCHOOL AND 27 SFU THAT ARE FAR FROM BUILD AREA AND ON MNDOT. 7/12 need to change PSA number to be PSA-1113, previously PSA1108. | ATT-8833 | MIN001.G0000362 | 2024-07-29 | 2024-08-15 | 2024-09-10 | 2024-09-16 | [7 empty] | 343 |  | 1900 | 1 | 0
ITG-135853 | 2 | Active |  |  | BBF |  | BBF-PI201-RT2-SEC1-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 1 | Eden Prairie | 1165 |  |  | Eric Lynn |  | 2024-01-15 | Eric Lynn | [22 empty] | 2024-09-03 | 2024-10-10 | 2024-09-09 |  |  | 2024-09-09 | [37 empty] | 344 |  | 1900 | 1 | 0 | #REF! | #N/A
6778 | 2 | Active |  |  | PSA | SFU/MDU | PSA-2101PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 1 | Eden Prairie | 592 | 588 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  |  |  | 2024-07-10 | CODY | 2024-07-12 | 2024-07-17 | 2024-07-17 | YES | 0 | 310 | 9397 | 9707 | 16.397 | 2024-07-23 | 2024-08-07 | 2024-08-11 |  |  | 864 | PFP 12365 SINGLETREE LN |  | 2024-08-20 | 2024-10-01 | 2024-09-26 |  |  | 2024-09-26 | 9280 | Jordan Struck | 2024-08-13 | 2024-08-27 | 2024-08-19 | [18 empty] | PSA previously named 2104 | ATT-8954 | MIN001.G0000429 | 2024-07-31 | Rejected | [8 empty] | Has been cancelled in CMPM | 345 |  | 2024 | 7 | 29 | #REF! | #N/A
ITG-147256 |  | HOLD FOR LATER |  |  | PSA | BCL/MDU | PSA-2102PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 1 | Eden Prairie | 573 | 590 | [8 empty] | 2024-07-16 | JOSH | 2024-07-18 | 2024-07-25 | 2024-07-25 | YES | 1910 | 2220 | 955 | 3175 | 5.541 | 2024-07-24 | 2024-08-23 | 2024-08-23 |  |  | 864 | PFP 12400 CASTLEMOOR DR |  | 2024-08-23 | 2024-10-10 | [27 empty] | Job cancelled by Ted in CMPM, on hold until further notice. PSA previously named 2103 | ATT-8955 | MIN001.G0000430 | 2024-07-31 | Rejected/Cancelled | [8 empty] | Has been cancelled in CMPM | 346 | [5 empty] | #N/A
ITG-135854 | 1 | Active |  |  | BBF |  | BBF-PI201-RT2-SEC2-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 2 | Eden Prairie | 1564 |  |  | Joseph Smith | [25 empty] | 2024-09-04 | 2024-10-10 | [41 empty] | 347 |  |  |  |  | #REF! | #N/A
ITG-134652 | 2 | Active |  |  | PSA | SFU/BCL/MDU | PSA-2201PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 2 | Eden Prairie | 559 | 528 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  |  |  | 2024-07-10 | HUNTER | 2024-07-12 | 2024-07-15 | 2024-07-15 | YES | 0 | 1583 | 2423 | 4006 |  | 2024-07-24 | 2024-08-08 | 2024-08-12 |  |  | 864 | PFP 13000 DAHLIA CIR |  | 2024-08-19 | 2024-10-01 | 2024-08-23 |  |  | 2024-08-23 | 2349 | Jermaine Scott | 2024-08-20 | 2024-09-03 | 2024-08-28 | [19 empty] | ATT-8864 | MIN001.G0000393 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-09-20 | [7 empty] | 348 |  | 2024 | 7 | 29 | #REF! | #N/A
ITG-134653 | 1 | Active |  |  | PSA | BCL/MDU | PSA-2202PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 2 | Eden Prairie | 511 | 477 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  |  |  | 2024-07-10 | HUNTER | 2024-07-12 | 2024-07-16 | 2024-07-16 | YES | 3164 | 1719 | 1696 | 3415 |  | 2024-07-25 | 2024-08-14 | 2024-08-22 |  |  | 864 | PFP 8980 MASSIE CURVE |  | 2024-08-26 | 2024-10-01 | 2024-09-05 |  |  | 2024-08-28 | 2133 | Jermaine Scott | 2024-09-04 | 2024-09-11 | 2024-09-06 | [19 empty] | ATT-8865 | MIN001.G0000394 | 2024-07-19 | 2024-09-23 | [9 empty] | 349 |  | 2024 | 7 | 29 | #REF! | #N/A
ITG-147258 |  | Active |  |  | PSA | BCL/MDU | PSA-2203PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 2 | Eden Prairie | 494 | 495 | [8 empty] | 2024-07-16 | JAEGER | 2024-07-18 | 2024-07-19 | 2024-07-19 | YES | 0 | 561 | 2203 | 2764 |  | 2024-07-25 | 2024-08-09 | 2024-08-12 |  |  | 864 | PFP 8675 MARIGOLD CIR |  | 2024-08-20 | 2024-10-02 | 2024-08-23 |  |  | 2024-08-23 | 2419 | Spencer Lynn | 2024-08-20 | 2024-09-03 | 2024-08-22 | [19 empty] | ATT-8866 | MIN001.G0000395 | 2024-07-19 | 2024-08-15 | 2024-09-10 | 2024-09-20 | [7 empty] | 350 | [5 empty] | #N/A
ITG-135859 | 4 | Active |  |  | BBF |  | BBF-PI201-RT2-SEC3-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 3 | Eden Prairie | 92 |  |  | Joseph Smith | [7 empty] | CODY | 2024-08-27 | 2024-09-05 | 2024-09-04 | NA | 3667 | 0 | 0 | 0 | 0 | [8 empty] | 2024-09-16 | 2024-10-29 | 2024-09-19 |  |  | 2024-09-19 | [23 empty] | SEC 3 BBF route is needed to get to SEC 5 | [13 empty] | 351 |  |  |  |  | #REF! | #N/A
ITG-134654 | 4 | NO BUILD |  |  | PSA | BCL | PSA-2301PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 3 | Eden Prairie |  |  |  | Eric Lynn |  | 2024-01-15 | Eric Lynn | [51 empty] | PSA has been combined into PSA2302 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 352 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134655 | 4 | HOLD FOR LATER |  |  | PSA | Airport/BCL | PSA-2302PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 3 | Eden Prairie | 92 | 144 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  |  |  | 2024-06-26 | JACOB | 2024-07-09 | 2024-07-15 | 2024-07-13 | YES | 0 | 73 | 6303 | 6376 | 69.3043 | 2024-07-19 | 2024-08-08 | 2024-08-12 |  |  | 288 | PFP 13300 PIONEER TRL |  | 2024-08-13 | 2024-09-24 | [27 empty] | PSA now contains what used to be PSA2301 | ATT-8867 | MIN001.G0000396 | 2024-07-19 | Rejected/Cancelled | [8 empty] | Has been cancelled in CMPM | 353 |  | 2024 | 7 | 28 | #REF! | #N/A
ITG-135861 | 1 | Active |  |  | BBF |  | BBF-PI201-RT2-SEC4-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 4 | Eden Prairie | 1597 |  |  | Joseph Smith | [25 empty] | 2024-09-04 | 2024-10-10 | 2024-09-09 |  |  | 2024-09-11 | [37 empty] | 354 |  |  |  |  | #REF! | #N/A
ITG-134657 | 1 | Active |  |  | PSA | SFU | PSA-2401PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 4 | Eden Prairie | 624 | 488 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  | 2024-05-10 | 2024-05-13 | 2024-05-17 | BRIAN | 2024-05-17 | 2024-06-21 | 2024-06-21 | YES | 0 | 1562 | 24409 | 25971 | 41.6202 | 2024-07-23 | 2024-08-14 | 2024-08-22 |  |  | 864 | PFP 8752 KNOLLWOOD DR |  | 2024-08-26 | 2024-09-27 | 2024-09-23 |  |  | 2024-09-12 | 25471 | Jermaine Scott | 2024-09-04 | 2024-09-18 | 2024-09-16 | [19 empty] | ATT-8868 | MIN001.G0000397 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-08-19 | [7 empty] | 355 | 1 | 2024 | 6 | 25 | #REF! | #N/A
ITG-134663 | 1 | Active |  |  | PSA | SFU | PSA-2402PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 4 | Eden Prairie | 638 | 622 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  | 2024-05-10 | 2024-05-13 | 2024-05-17 | HANNAH | 2024-05-17 | 2024-06-17 | 2024-06-17 | YES | 0 | 1453 | 42000 | 43453 | 68.1082 | 2024-07-08 | 2024-08-14 | 2024-08-23 |  |  | 864 | PFP 14693 VILLAGE WOODS DRIVE |  | 2024-08-23 | 2024-09-13 | 2024-09-16 |  |  | 2024-09-13 | 37019 | James Lugo | 2024-08-29 | 2024-09-12 | 2024-09-02 | [19 empty] | ATT-8869 | MIN001.G0000398 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-08-19 | [7 empty] | 356 | 1 | 2024 | 6 | 25 | #REF! | #N/A
ITG-134685 | 1 | Active |  |  | PSA | SFU | PSA-2403PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 4 | Eden Prairie | 335 | 267 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  | 2024-05-10 | 2024-05-13 | 2024-05-17 | HUNTER | 2024-05-17 | 2024-06-03 | 2024-06-03 | YES | 5557 | 1231 | 28578 | 29809 | 88.9821 | 2024-06-12 | 2024-06-28 | 2024-06-28 |  |  | 576 | PFP 14704 LANGDON PL | 2024-06-28 | 2024-07-17 | 2024-09-27 | [5 empty] | Jordan Struck | 2024-06-28 | 2024-07-08 | 2024-07-06 | [19 empty] | ATT-8870 | MIN001.G0000399 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-08-19 | [7 empty] | 357 | 1 | 2024 | 6 | 23 | #REF! | #N/A
ITG-134650 | 4 | HOLD FOR LATER |  |  | PSA | MDU | PSA-2404PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 1 | Eden Prairie | 649 | 485 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  |  |  | 2024-06-26 | JAEGER | 2024-06-28 | 2024-07-01 | 2024-07-01 | YES | 0 | 2534 | 3819 | 6353 | 9.7889 | 2024-07-03 | 2024-07-19 | 2024-07-19 |  |  | 864 | PFP 13570 CARMODY DR |  | 2024-07-29 | 2024-08-29 | 2024-08-12 |  |  | 2024-08-12 | 3776 | Jermaine Scott | 2024-07-23 | 2024-07-30 | 2024-07-24 | [18 empty] | 7/1 renamed PSA to be 2404 rather than 2102 b/c the BBF route and POF locations were moved to section 4. | ATT-8871 | MIN001.G0000400 |  |  |  |  | ? | [5 empty] | Design complete, which MS do we want to bill through? | 358 |  | 2024 | 7 | 27 | #REF! | #N/A
ITG-134649 | 4 | HOLD FOR LATER |  |  | PSA | BCL/MDU | PSA-2405PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 1 | Eden Prairie | 553 | 724 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  |  |  | 2024-06-26 | JAEGER | 2024-07-01 | 2024-07-09 | 2024-07-09 | YES | 0 | 1721 | 16331 | 18052 | 32.6438 | 2024-07-16 | 2024-08-07 | 2024-08-13 |  |  | 864 | PFP 1307 ERWIN COURT |  | 2024-08-16 | 2024-09-24 | [27 empty] | 7/1 PSA 2101 split at Priairie Center Drive, section to east is now PSA2405. 5/10/2024 BCL - Mall area is no build. Remove from PSA boundry. New boundry to include the SFU's/MDU's | ATT-8872 | MIN001.G0000401 | 2024-07-19 | Rejected/Cancelled | [8 empty] | Has been cancelled in CMPM | 359 |  | 2024 | 7 | 28 | #REF! | #N/A
ITG-135863 | 1 | Active |  |  | BBF |  | BBF-PI201-RT2-SEC5-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 5 | Eden Prairie | 309 |  |  | Joseph Smith | [25 empty] | 2024-08-30 | 2024-10-24 | 2024-09-04 |  |  | 2024-09-04 | 4070 | [36 empty] | 360 |  |  |  |  | #REF! | #N/A
ITG-134687 | 1 | Active |  |  | PSA | SFU | PSA-2501PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 5 | Eden Prairie | 309 | 271 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  | 2024-05-10 | 2024-05-13 | 2024-05-20 | JACOB | 2024-05-20 | 2024-05-27 | 2024-05-27 | YES | 4069 | 12 | 36013 | 36025 | 116.5858 | 2024-06-12 | 2024-06-25 | 2024-06-27 |  |  | 432 | PFP 9145 EDEN PRAIRIE RD | 2024-06-27 | 2024-07-03 | 2024-07-17 | 2024-07-17 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 28719 | Jermaine Scott | 2024-06-27 | 2024-07-08 | 2024-07-05 | 2024-08-02 | 2024-08-06 |  |  | 2024-08-26 |  | 1 out of 2 | [11 empty] | 8/26 Nate: Reviewed CAD dated 8/12 redline corrections have been made and has been sent to premitting to amend existing permit. 8/1 Nate: Reviewed CAD dated 7/30 sent back to CAD for Redline corrections. 7/25 City HH requirement correction 6/27 sent Layout mark up to CAD | ATT-8873 | MIN001.G0000402 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-08-19 | [7 empty] | 361 | 1 | 2024 | 5 | 22 | #REF! | #N/A
ITG-135864 | 1 | Active |  |  | BBF |  | BBF-PI201-RT2-SEC6-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 6 | Eden Prairie | 636 |  |  | Joseph Smith | [7 empty] | JACOB | 2024-08-28 | 2024-09-03 | 2024-09-01 | NA | 3987 | 0 | 0 | 0 | 0 | [8 empty] | 2024-09-18 | 2024-10-29 | [41 empty] | 362 |  |  |  |  | #REF! | #N/A
ITG-134689 | 1 | Active |  |  | PSA | MDU | PSA-2601PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 6 | Eden Prairie | 636 | 633 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  |  |  | 2024-05-22 | JOSH | 2024-07-12 | 2024-07-19 | 2024-07-19 | YES | 519 | 1334 | 4291 | 5625 |  | 2024-07-26 | 2024-08-28 | 2024-09-04 |  |  | 864 | PFP 15498 LILAC DR |  | 2024-09-13 | 2024-10-02 | 2024-09-20 |  |  | 2024-09-20 | 6228 | James Lugo | 2024-09-04 | 2024-09-18 | 2024-09-09 | [18 empty] | 7/10 Junior is removing a church to be added to PSA 2901 | ATT-8874 | MIN001.G0000403 | 2024-07-19 | 2024-09-23 | [9 empty] | 363 |  | 2024 | 7 | 29 | #REF! | #N/A
ITG-135865 | 1 | NO BUILD |  |  | BBF |  | BBF-PI201-RT2-SEC7-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 7 | Eden Prairie | 277 |  |  | Joseph Smith |  |  | Joseph Smith | [58 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 364 |  |  |  |  | #REF! | #N/A
ITG-134690 | 1 | No Build - Ex Comp |  |  | PSA | SFU | PSA-2701PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 7 | Eden Prairie | 277 |  |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  | 2024-05-10 | 2024-05-13 | NA | [47 empty] | FIELDER FOUND EXISTING LUMEN FIBER TO THE HOMES IN THE WHOLE JOB AREA 5/13. | ATT-8812 | MIN001.G0000354 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-09-20 | Stop | [6 empty] | 365 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135866 |  | NO BUILD |  |  | BBF |  | BBF-PI201-RT2-SEC8-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 8 | Eden Prairie | 7 |  |  | Joseph Smith |  |  | Joseph Smith | [58 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 366 |  |  |  |  | #REF! | #N/A
ITG-134692 |  | NO BUILD |  |  | PSA | SFU | PSA-2801PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 8 | Eden Prairie | 7 |  |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  |  |  |  | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | [37 empty] | VACANT - no fielding needed, end of the BBF | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 367 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-135872 | 1 | Active |  |  | BBF |  | BBF-PI201-RT2-SEC9-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 9 | Eden Prairie | 572 |  |  | Joseph Smith | [25 empty] | 2024-09-03 | 2024-10-24 | [41 empty] | 368 |  |  |  |  | #REF! | #N/A
ITG-134695 | 1 | Active |  |  | PSA | SFU/MDU | PSA-2901PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 9 | Eden Prairie | 572 | 294 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  | 2024-05-10 | 2024-05-13 | 2024-05-16 | CODY | 2024-05-16 | 2024-06-03 | 2024-06-03 | YES | 25534 | 1226 | 29660 | 30886 | 53.9965 | 2024-06-14 | 2024-06-26 | 2024-06-28 |  |  | 864 | PFP 9279 BRAXTON DR | 2024-07-01 | 2024-07-05 | 2024-07-25 | 2024-07-23 | 2024-07-25 | 2024-07-30 | 2024-07-30 | 24245 | James Lugo | 2024-07-15 | 2024-07-19 | 2024-07-17 | 2024-07-30 | 2024-08-05 |  |  | 2024-08-06 |  | 1 out of 2 | [11 empty] | 8/6 Nate Revision approved and sent to permiting for amendment and resubmittal. 7/25 City HH requirement correction 7/23 CAD is ready for review. 7/10 Junior is adding a church from PSA 2601 5/15 Aubree to split PSA generating new PSA 2132 | ATT-8875 | MIN001.G0000404 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-08-19 | [7 empty] | 369 | 1 | 2024 | 6 | 23 | #REF! | #N/A
ITG-135874 | 1 | Active |  |  | BBF |  | BBF-PI201-RT2-SEC11-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 11 | Eden Prairie | 2932 |  |  | Joseph Smith | [25 empty] | 2024-09-05 | 2024-10-24 | [41 empty] | 370 |  |  |  |  | #REF! | #N/A
ITG-134696 | 1 | Active |  |  | PSA | SFU | PSA-2111PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 11 | Eden Prairie | 422 | 410 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  | 2024-05-10 | 2024-05-13 | 2024-05-15 | JACOB | 2024-05-15 | 2024-05-20 | 2024-05-20 | YES | 2942 | 867 | 40812 | 41679 | 98.7654 | 2024-06-04 | 2024-06-17 | 2024-06-11 | 2024-09-12 | 2024-09-12 | 576 | PFP 9060 WAVERLY CT |  | 2024-06-11 | 2024-07-19 | 2024-07-05 | 2024-08-28 | 2024-08-29 | 8/29 v3 | 27775 | Eric Lynn | 2024-06-11 | 2024-07-02 | 2024-07-01 | 2024-08-29 | 2024-09-13 |  |  | 2024-08-29 | [13 empty] | 8/29 Nate: Redline corrections have been made I have move this over to permitting. 8/28 NATE: REDLINES SENT TO CAD FOR REVISIONS. 7/25 City HH requirement correction | ATT-8876 | MIN001.G0000405 | 2024-07-18 | 2024-07-30 | 2024-08-16 | 2024-08-19 | [7 empty] | 371 | 1 | 2024 | 5 | 21 | #REF! | #N/A
ITG-134697 | 1 | Active |  |  | PSA | SFU | PSA-2112PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 11 | Eden Prairie | 486 | 449 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  | 2024-05-10 | 2024-05-13 | 2024-05-15 | ERIK | 2024-05-15 | 2024-05-28 | 2024-05-28 | YES | 0 | 330 | 56640 | 56970 | 117.2222 | 2024-06-02 | 2024-06-19 | 2024-06-14 |  |  | 864 | PFP 16868 CANDLEWOOD PKWY |  | 2024-06-17 | 2024-07-12 | 2024-07-22 | 2024-08-27 | 2024-08-29 | 2024-08-28 | 34383 | Cheryl Turk | 2024-06-14 | 2024-06-24 | 2024-06-27 | 2024-09-03 |  |  |  | 2024-08-29 | [13 empty] | 8/29 Nate: Redline corrections have been made I have move this over to permitting. 8/27 NATE: REDLINES SENT TO CAD FOR MINOR REVISIONS. 7/25 City HH requirement correction | ATT-8877 | MIN001.G0000406 | 2024-07-18 | 2024-08-15 | 2024-08-22 | 2024-08-23 | [7 empty] | 372 | 1 | 2024 | 5 | 22 | #REF! | #N/A
ITG-159225 |  | Active |  |  | BBF |  | BBF-PI201-RT2-SEC12-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 12 | Eden Prairie | 310 |  |  | Joseph Smith | [26 empty] | 2024-10-29 | [41 empty] | 373
ITG-134698 | 1 | HOLD FOR LATER |  |  | PSA | SFU/BCL | PSA-2121PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 12 | Eden Prairie | 310 |  |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  |  |  | 2024-06-28 | NA | NA | NA | NA | NA | NA | NA | NA | NA | [38 empty] | 7/9 fielding not needed, community is private and just need to leave fiber coil in the POF HH on the BBF route. PRIVATE AREA - GATED | ATT-8878 | MIN001.G0000407 | 2024-07-18 | 2024-09-23 |  |  | Stop | Stop | Stop | Stop | Stop | Stop | Per Ted PSA -2121 in Eden Prairie is all private road. I would not take this one further until Gigapower's sales team can arrange a deal with Bearpath. | 374 |  | #VALUE! | #VALUE! | #VALUE! | #REF! | #N/A
ITG-159228 |  | Active |  |  | BBF |  | BBF-PI201-RT2-SEC13-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 13 | Eden Prairie | 877 |  |  | Joseph Smith | [26 empty] | 2024-10-29 | [41 empty] | 375
ITG-134700 | 1 | Active |  |  | PSA | SFU | PSA-2131PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 11 | Eden Prairie | 527 | 502 |  | Eric Lynn |  | 2024-01-15 | Eric Lynn |  | 2024-05-10 | 2024-05-13 | 2024-05-16 | JAEGER | 2024-05-16 | 2024-05-29 | 2024-05-29 | YES | 7797 | 2940 | 46608 | 49548 | 94.019 | 2024-06-10 | 2024-06-21 | 2024-06-24 |  |  | 864 | PFP 18395 DELL DR | 2024-06-24 | 2024-06-28 | 2024-07-25 | 2024-07-16 | 2024-08-28 | 2024-09-26 | 2024-09-26 | 42469 | Cheryl Turk | 2024-06-24 | 2024-07-03 | 2024-07-09 | 2024-09-03 | 2024-09-27 |  |  | 2024-08-30 |  | 1 out of 2 | [11 empty] | 8/30 Nate: Redline corrections have been made I have move this over to permitting. 8/28 NATE: REDLINES SENT TO CAD FOR REVISIONS. 7/25 City HH requirement correction 5/15 Aubree to split PSA generating new PSA 2132 | ATT-8879 | MIN001.G0000408 | 2024-07-18 | 2024-07-30 | 2024-08-22 | 2024-08-23 | [7 empty] | 376 | 1 | 2024 | 5 | 22 | #REF! | #N/A
ITG-137177 | 1 | Active |  |  | PSA | SFU | PSA-2132PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #2 | BBF RTE 2 SEC 11 | Eden Prairie | 350 | 236 | [8 empty] | 2024-05-16 | SAM | 2024-05-16 | 2024-05-24 | 2024-05-24 | YES | 0 | 810 | 22415 | 23225 | 66.3571 | 2024-06-07 | 2024-07-02 | 2024-07-06 |  |  | 432 | PFP 9795 SIERRA TRAIL |  | 2024-07-08 | 2024-08-02 | 2024-08-02 |  |  |  | 20821 | James Lugo | 2024-07-11 | 2024-07-25 | 2024-07-12 | [18 empty] | 5/15 Aubree to split PSA generating new PSA 2132 | ATT-8880 | MIN001.G0000409 | 2024-07-18 | 2024-08-15 | 2024-08-22 | 2024-08-23 | [7 empty] | 377 | 1 |  |  |  | #REF! | #N/A
ITG-135875 | 1 | Active |  |  | BBF |  | BBF-PI301-RT3-SEC1-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 1 | Eden Prairie | 850 |  |  | Joseph Smith | [7 empty] | JAEGER | 2024-08-12 | 2024-08-20 | 2024-08-20 | [14 empty] | 2024-08-26 | 2024-10-04 | [41 empty] | 378 |  |  |  |  | #REF! | #N/A
ITG-134733 | 4 | HOLD FOR LATER |  |  | PSA | BCL/MDU | PSA-3101PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 1 | Eden Prairie | 540 | 536 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  |  |  | 2024-06-11 | ERIK | 2024-06-12 | 2024-06-24 | 2024-06-24 | YES | 5564 | 43 | 16141 | 16184 | 29.9704 | 2024-07-19 | 2024-08-09 | 2024-08-13 |  |  | 864 | PFP 990 PRAIRIE CENTER DRIVE |  | 2024-08-14 | 2024-09-24 | [5 empty] | Jordan Struck | 2024-08-20 | 2024-09-03 | 2024-08-23 | [18 empty] | PSA3102, PSA3103 and PSA3104 all combined into PSA3101 - Gigapower Priority will need to be evaluated. | ATT-8859 | MIN001.G0000388 | 2024-09-04 |  |  |  | ? | [5 empty] | Design complete, which MS do we want to bill through? | 379 |  | 2024 | 6 | 26 | #REF! | #N/A
ITG-134735 | 1 | NO BUILD |  |  | PSA |  | PSA-3102PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 1 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [15 empty] | 2024-08-28 | [35 empty] | PSA was combined into PSA3101 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 380 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134737 | 2 | NO BUILD |  |  | PSA |  | PSA-3103PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 1 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [15 empty] | 2024-08-28 | [35 empty] | PSA was combined into PSA3101 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 381 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134786 | 1 | NO BUILD |  |  | PSA |  | PSA-3104PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 1 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [15 empty] | 2024-08-29 | [35 empty] | PSA was combined into PSA3101 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 382 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134787 | 4 | NO BUILD |  |  | PSA |  | PSA-3105PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 1 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA was combined into PSA3108 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 383 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134788 | 2 | NO BUILD |  |  | PSA |  | PSA-3106PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 1 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA was combined into PSA3108 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 384 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134789 | 4 | NO BUILD |  |  | PSA |  | PSA-3107PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 1 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA was combined into PSA3108 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 385 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134790 | 4 | HOLD FOR LATER |  |  | PSA | BCL | PSA-3108PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 1 | Eden Prairie | 310 | 339 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  |  |  | 2024-06-11 | ERIK | 2024-06-12 | 2024-06-24 | 2024-06-24 | YES | 0 | 2059 | 10328 | 12387 | 39.9581 | 2024-07-22 | 2024-08-09 | 2024-08-14 |  |  | 432 | PFP 7752 MITCHELL RD |  | 2024-08-16 | 2024-09-25 | 2024-08-22 |  |  | 2024-08-20 | 10088 | [22 empty] | PSA3105, PSA3106, PSA3107 and PSA3503 all combined into PSA3108. Gigapower Priority will need to be evaluated | ATT-8860 | MIN001.G0000389 | 2024-07-22 | Rejected/Cancelled | [8 empty] | Has been cancelled in CMPM | 386 |  | 2024 | 6 | 26 | #REF! | #N/A
ITG-147262 |  | Active |  |  | PSA | SFU/MDU/BCL | PSA-3109PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 1 | Eden Prairie | 163 | 127 | [8 empty] | 2024-07-22 | JAEGER | 2024-07-25 | 2024-08-01 | 2024-07-30 | YES | 10624 | 10624 | 17832 | 28456 |  | 2024-08-01 | 2024-08-29 | 2024-09-04 |  |  | 288 | PFP 7300 BRYANT LAKE DR |  | 2024-09-16 | 2024-10-10 | [5 empty] | Jordan Struck | 2024-09-04 | 2024-09-18 | 2024-09-11 | [18 empty] | PSA1105 is now this PSA | ATT-8861 | MIN001.G0000390 | 2024-07-29 | 2024-08-15 | 2024-09-10 | 2024-09-20 | [7 empty] | 387
ITG-135876 | 1 | Active |  |  | BBF |  | BBF-PI301-RT3-SEC2-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 2 | Eden Prairie | 1295 |  |  | Joseph Smith | [25 empty] | 2024-08-30 | 2024-10-24 | 2024-09-04 |  |  | 2024-09-04 | [37 empty] | 388 |  |  |  |  | #REF! | #N/A
ITG-134791 | 1 | Active |  |  | PSA | SFU | PSA-3201PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 2 | Eden Prairie | 410 | 371 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-28 | 2024-05-28 | 2024-05-30 | JOSH | 2024-05-30 | 2024-06-14 | 2024-06-14 | YES | 0 | 912 | 30780 | 31692 | 77.2976 | 2024-06-26 | 2024-07-10 | 2024-07-12 |  |  | 576 | PFP 13140 ROBERTS DR |  | 2024-07-15 | 2024-08-14 | 2024-07-26 |  |  | 2024-07-25 | 29964 | Eric Lynn | 2024-07-18 | 2024-08-07 | 2024-08-12 | [18 empty] | PSA3202 combined into this PSA. | ATT-8834 | MIN001.G0000363 | 2024-07-18 | 2024-07-30 | 2024-08-19 | 2024-08-19 | [7 empty] | 389 | 1 | 2024 | 6 | 24 | #REF! | #N/A
ITG-134792 | 2 | NO BUILD |  |  | PSA |  | PSA-3202PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 2 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  |  | 2024-05-28 | [48 empty] | PSA combined into PSA3201 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 390 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-134794 | 1 | Active |  |  | PSA | SFU | PSA-3203PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 2 | Eden Prairie | 243 | 124 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-28 | 2024-05-28 | 2024-05-30 | CODY | 2024-05-30 | 2024-06-12 | 2024-06-12 | YES | 6461 | 5 | 13973 | 13978 |  | 2024-07-03 | 2024-07-19 | 2024-07-17 |  |  | 288 | PFP 13600 FENWICK CIR |  | 2024-07-18 | 2024-08-16 | 2024-08-16 |  |  | 2024-08-16 | 13118 | Eric Lynn | 2024-07-30 | 2024-08-23 | 2024-08-23 | [19 empty] | ATT-8835 | MIN001.G0000364 | 2024-07-18 | 2024-07-30 | 2024-08-19 | 2024-08-19 | [7 empty] | 391 | 1 | 2024 | 6 | 24 | #REF! | #N/A
ITG-135894 | 1 | Active |  |  | PSA | SFU/MDU | PSA-3204PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 2 | Eden Prairie | 517 | 221 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-28 | 2024-05-28 | 2024-05-30 | SAM | 2024-05-30 | 2024-06-03 | 2024-06-03 | YES | 680 | 5 | 20406 | 20411 | 0 | 2024-06-20 | 2024-07-09 | 2024-07-09 |  |  | 864 | PFP 6500 BAKER RD |  | 2024-07-15 | 2024-08-16 | 2024-08-13 |  |  | 2024-08-08 | 20291 | Eric Lynn | 2024-07-11 | 2024-07-31 | 2024-07-31 | [18 empty] | PSA3205, PSA3206, PSA3208 and PSA3209 combined into this PSA | ATT-8836 | MIN001.G0000365 | 2024-07-18 | 2024-07-30 | 2024-08-19 | 2024-08-19 | [7 empty] | 392 | 1 | 2024 | 6 | 23 | #REF! | #N/A
ITG-135899 | 2 | NO BUILD |  |  | PSA |  | PSA-3205PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 2 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3204 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 393 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135902 | 1 | NO BUILD |  |  | PSA |  | PSA-3206PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 2 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3204 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 394 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135903 | 4 | HOLD FOR LATER |  |  | PSA | BCL | PSA-3207PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 2 | Eden Prairie | 125 | 126 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  |  |  | 2024-06-11 | JACOB | 2024-06-12 | 2024-06-18 | 2024-06-18 | YES | 0 | 2533 | 5343 | 7876 | 63.008 | 2024-07-23 | 2024-08-12 | 2024-08-14 |  |  | 288 | PFP 6480 CARLSON DRIVE |  | 2024-08-16 | 2024-09-25 | [28 empty] | ATT-8837 | MIN001.G0000366 | 2024-07-22 | 2024-08-15 | 2024-09-10 | 2024-09-16 | Stop | Stop | Stop | Stop | Stop | Stop |  | 395 |  | 2024 | 6 | 25 | #REF! | #N/A
ITG-136767 | 1 | NO BUILD |  |  | PSA |  | PSA-3208PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 2 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3204 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 396 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-137069 | 4 | NO BUILD |  |  | PSA |  | PSA-3209PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 2 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3204 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 397 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135877 | 1 | Active |  |  | BBF |  | BBF-PI301-RT3-SEC3-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 3 | Eden Prairie | 977 |  |  | Joseph Smith | [25 empty] | 2024-09-04 | 2024-10-25 | 2024-09-05 |  |  | 2024-09-06 | [37 empty] | 398 |  |  |  |  | #REF! | #N/A
ITG-134648 | 4 | NO BUILD |  |  | PSA |  | PSA-3301PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 3 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3303 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 399 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136768 | 2 | NO BUILD |  |  | PSA |  | PSA-3302PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 3 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3303 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 400 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136769 | 1 | Active |  |  | PSA | SFU/MDU | PSA-3303PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 3 | Eden Prairie | 610 | 553 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-28 | 2024-05-28 | 2024-05-30 | ERIK | 2024-05-30 | 2024-06-04 | 2024-06-04 | YES | 0 | 1760 | 34379 | 36139 | 0 | 2024-06-18 | 2024-07-09 | 2024-07-09 |  |  | 864 | PFP 14335 GOLF VIEW DR |  | 2024-07-15 | 2024-08-01 | 2024-07-30 |  |  | 2024-07-30 | 24392 | Jordan Struck | 2024-07-11 | 2024-07-19 | 2024-07-17 | 2024-07-30 | 2024-08-23 | [16 empty] | PSA3301 and PSA3302 combined into PSA3303 | ATT-8838 | MIN001.G0000367 | 2024-07-18 | 2024-07-30 | 2024-08-19 | 2024-08-19 | [7 empty] | 401 | 1 | 2024 | 6 | 23 | #REF! | #N/A
ITG-138018 | 4 | NO BUILD |  |  | PSA |  | PSA-3304PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 3 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA combined into PSA3306 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 402 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136770 | 2 | NO BUILD |  |  | PSA |  | PSA-3305PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 3 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA combined into PSA3306 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 403 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136771 | 1 | Active |  |  | PSA | SFU | PSA-3306PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 3 | Eden Prairie | 367 | 301 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-28 | 2024-05-28 | 2024-06-03 | JACOB | 2024-06-03 | 2024-06-10 | 2024-06-10 | YES | 3026 | 792 | 9718 | 10510 |  | 2024-06-20 | 2024-07-03 | 2024-07-06 |  |  | 432 | PFP 7344 HOWARD LANE |  | 2024-07-10 | 2024-08-23 | 2024-08-21 |  |  | 2024-08-21 | 7373 | Jordan Struck | 2024-07-11 | 2024-07-25 | 2024-07-15 | [18 empty] | PSA3304, PSA3305 and PSA3307 combined into this PSA | ATT-8839 | MIN001.G0000368 | 2024-07-18 | 2024-07-30 | 2024-08-19 | 2024-08-19 | [7 empty] | 404 | 1 | 2024 | 6 | 24 | #REF! | #N/A
ITG-136772 | 1 | NO BUILD |  |  | PSA |  | PSA-3307PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 3 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA combined into PSA3306 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 405 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135878 | 1 | Active |  |  | BBF |  | BBF-PI301-RT3-SEC4-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 4 | Eden Prairie | 1205 |  |  | Joseph Smith | [25 empty] | 2024-09-05 | 2024-10-25 | 2024-09-06 |  |  | 2024-09-06 | [37 empty] | 406 |  |  |  |  | #REF! | #N/A
ITG-136773 | 1 | Active |  |  | PSA | SFU/MDU | PSA-3401PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 4 | Eden Prairie | 446 | 428 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-28 | 2024-05-28 | 2024-06-03 | JACOB | 2024-06-03 | 2024-06-10 | 2024-06-10 | YES | 0 | 3243 | 30294 | 33537 |  | 2024-06-25 | 2024-07-09 | 2024-07-12 | 2024-08-27 | 2024-08-28 | 576 | PFP 7000 SPRINGHILL CIR |  | 2024-07-15 | 2024-08-08 | 2024-07-24 | 2024-08-27 | 2024-08-30 | 2024-08-30 | 23209 | Spencer Lynn | 2024-08-23 | 2024-09-06 | 2024-09-10 | 2024-09-03 | 2024-09-10 |  |  | 2024-08-30 | [13 empty] | 8/30 Nate: Redline corrections have been made I have move this over to permitting. 8/27 Nate: Sent redlines back to CAD for corrections, also sent to Layout for corrections to the leep. PSA3402 and PSA3403 combined into this PSA | ATT-8840 | MIN001.G0000369 | 2024-07-18 | 2024-07-30 | 2024-08-19 | 2024-08-19 | [7 empty] | 407 | 1 | 2024 | 6 | 24 | #REF! | #N/A
ITG-136775 | 2 | NO BUILD |  |  | PSA |  | PSA-3402PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 4 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA combined into PSA3401 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 408 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136776 |  | NO BUILD |  |  | PSA |  | PSA-3403PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 4 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA combined into PSA3401 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 409 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136777 | 1 | Active |  |  | PSA | SFU/MDU | PSA-3404PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 4 | Eden Prairie | 397 | 266 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-28 | 2024-05-28 | 2024-06-03 | JACOB | 2024-06-12 | 2024-06-17 | 2024-06-17 | YES | 0 | 2821 | 22523 | 25344 | 63.8388 | 2024-07-02 | 2024-07-19 | 2024-07-17 |  |  | 576 | PFP 15526 MICHELE LN |  | 2024-07-24 | 2024-08-16 | 2024-08-16 |  |  | 2024-08-15 | 14797 | Jermaine Scott | 2024-07-18 | 2024-08-01 | 2024-07-23 | [19 empty] | ATT-8841 | MIN001.G0000370 | 2024-07-18 | 2024-07-30 | 2024-08-19 | 2024-08-19 | [7 empty] | 410 | 1 | 2024 | 6 | 25 | #REF! | #N/A
ITG-136778 | 1 | Active |  |  | PSA | SFU | PSA-3405PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 4 | Eden Prairie | 362 | 563 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-28 | 2024-05-28 | 2024-05-29 | HUNTER | 2024-05-29 | 2024-06-12 | 2024-06-12 | YES | 5643 | 1491 | 34660 | 36151 |  | 2024-06-17 | 2024-07-02 | 2024-07-05 |  |  | 576 | PFP 7502 SUPERIOR TERRACE |  | 2024-07-10 | 2024-08-30 | 2024-08-26 | 2024-09-20 | 2024-09-27 | 2024-09-27 | 25976 | Jermaine Scott | 2024-07-11 | 2024-08-05 | 2024-08-05 | 2024-09-27 |  |  |  | 2024-09-27 | [13 empty] | 9/27 Nate: Print has been reviewed and approved and sent to permitting. 9/20 Nate: CAD revisions needed, Sent redlines to CAD. PSA3405 combined into this PSA | ATT-8842 | MIN001.G0000371 | 2024-07-18 | 2024-07-30 | 2024-08-19 | 2024-08-19 | [7 empty] | 411 | 1 | 2024 | 6 | 24 | #REF! | #N/A
ITG-136794 | 4 | NO BUILD |  |  | PSA |  | PSA-3406PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 4 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3405 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 412 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135879 | 1 | Active |  |  | BBF |  | BBF-PI301-RT3-SEC5-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 5 | Eden Prairie | 1504 |  |  | Joseph Smith | [26 empty] | 2024-10-25 | [41 empty] | 413 |  |  |  |  | #REF! | #N/A
ITG-138022 | 4 | NO BUILD |  |  | PSA |  | PSA-3501PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 5 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3502 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 414 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136779 | 1 | Active |  |  | PSA | SFU/BCL | PSA-3502PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 5 | Eden Prairie | 502 | 288 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-24 | 2024-05-26 | 2024-05-28 | JACOB | 2024-05-29 | 2024-05-31 | 2024-05-31 | YES | 2749 | 615 | 19722 | 20337 | 0 | 2024-06-24 | 2024-07-05 | 2024-07-05 |  |  | 864 | PFP 16533 BISCAYNE BLVD |  | 2024-07-10 | 2024-08-02 | 2024-08-05 | 2024-09-03 | 2024-09-12 | 2024-09-12 | 14233 | Jermaine Scott | 2024-07-30 | 2024-08-13 | 2024-08-09 | 2024-08-29 | 2024-09-06 |  |  | 2024-08-29 |  | 1 out of 3 | [11 empty] | 9/3 MNDOT requesting revisions to place out at edge of ROW8/29 Nate: Redline corrections have been made I have move this over to permitting. 8/28 NATE: REDLINES SENT TO CAD FOR MINOR REVISIONS.PSA 3501, PSA3503 and PSA3504 combined into this PSA | ATT-8843 | MIN001.G0000372 | 2024-07-18 | 2024-07-30 | 2024-08-19 | 2024-08-19 | [7 empty] | 415 | 1 | 2024 | 5 | 22 | #REF! | #N/A
ITG-138024 | 4 | NO BUILD |  |  | PSA |  | PSA-3503PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 5 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3502 and PSA3108 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 416 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136780 | 1 | NO BUILD |  |  | PSA |  | PSA-3504PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 5 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3502 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 417 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136781 | 2 | NO BUILD |  |  | PSA |  | PSA-3505PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 5 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3507 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 418 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-138025 | 4 | NO BUILD |  |  | PSA | BCL/SFU | PSA-3506PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 5 | Eden Prairie | 501 |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA combined into PSA3507 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 419 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136782 | 1 | Active |  |  | PSA | SFU | PSA-3507PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 5 | Eden Prairie | 501 | 502 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-24 | 2024-05-26 | 2024-05-28 | JAEGER | 2024-05-29 | 2024-06-12 | 2024-06-12 | YES | 1542 | 0 | 21288 | 22830 |  | 2024-06-20 | 2024-07-05 | 2024-07-06 |  |  | 864 | PFP 7575 CARNELIAN LN |  | 2024-07-10 | 2024-08-08 | 2024-07-22 | 2024-09-11 | 2024-09-25 | 2024-09-25 | 14764 | Cheryl Turk | 2024-07-11 | 2024-07-19 | 2024-07-19 |  |  |  |  | 2024-08-06 |  | 1 out of 3 | [11 empty] | 9/11 Needd MNDOT permit for shts 9 & 10. 8/6 Nate Revision approved and sent to permiting for amendment and resubmittal. 7/25 City HH requirement correction PSA3506 and PSA3505 combined into this PSA. | ATT-8844 | MIN001.G0000373 | 2024-07-18 | 2024-07-30 | 2024-08-22 | 2024-08-23 | [7 empty] | 420 | 1 | 2024 | 6 | 24 | #REF! | #N/A
ITG-135881 | 1 | Active |  |  | BBF |  | BBF-PI301-RT3-SEC6-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 6 | Eden Prairie | 797 |  |  | Joseph Smith | [25 empty] | 2024-09-03 | 2024-10-25 | 2024-09-05 |  |  | 2024-09-05 | [37 empty] | 421 |  |  |  |  | #REF! | #N/A
ITG-136783 | 1 | Active |  |  | PSA | SFU | PSA-3601PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 6 | Eden Prairie | 188 | 184 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-28 | 2024-05-28 | 2024-06-04 | ERIK | 2024-06-04 | 2024-06-09 | 2024-06-09 | YES | 3336 | 255 | 26922 | 27177 | 144.5585 | 2024-06-27 | 2024-07-19 | 2024-07-17 |  |  | 288 | PFP 16391 N HILLCREST CT |  | 2024-07-26 | 2024-08-16 | 2024-08-26 |  |  | 2024-08-26 | 17251 | Jordan Struck | 2024-08-21 | 2024-09-04 | 2024-08-29 | [19 empty] | ATT-8845 | MIN001.G0000374 | 2024-07-18 | 2024-07-30 | 2024-08-22 | 2024-08-23 | [7 empty] | 422 | 1 | 2024 | 6 | 24 | #REF! | #N/A
ITG-136784 | 1 | Active |  |  | PSA | SFU/BCL | PSA-3602PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 6 | Eden Prairie | 244 | 243 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-24 | 2024-05-26 | 2024-05-30 | DREW | 2024-05-30 | 2024-06-21 | 2024-06-21 | YES | 3584 | 0 | 19326 | 19326 | 79.2049 | 2024-06-25 | 2024-07-10 | 2024-07-12 |  |  | 432 | PFP 6584 MERE DRIVE |  | 2024-07-22 | 2024-08-15 | 2024-08-05 |  |  |  | 17065 | Jordan Struck | 2024-07-18 | 2024-08-01 | 2024-07-26 | [18 empty] | PSA3603 and PSA3604 combined into this PSA | ATT-8846 | MIN001.G0000375 | 2024-07-18 | 2024-07-30 | 2024-08-22 | 2024-08-23 | [7 empty] | 423 | 1 | 2024 | 6 | 25 | #REF! | #N/A
ITG-138029 | 4 | NO BUILD |  |  | PSA |  | PSA-3603PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 6 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3602 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 424 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136785 | 1 | NO BUILD |  |  | PSA |  | PSA-3604PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 6 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3602 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 425 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136786 | 1 | NO BUILD |  |  | PSA |  | PSA-3605PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 6 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3606 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 426 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136787 | 1 | Active |  |  | PSA | SFU/MDU | PSA-3606PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 6 | Eden Prairie | 365 | 356 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-24 | 2024-05-26 | 2024-05-30 | DREW | 2024-05-30 | 2024-06-28 | 2024-06-28 | YES | 0 | 1490 | 29872 | 31362 | 85.9233 | 2024-07-02 | 2024-07-22 | 2024-07-22 |  |  | 576 | PFP 15701 S LUND RD |  | 2024-08-01 | 2024-09-03 | 2024-08-29 |  |  | 2024-08-29 | 26878 | Cheryl Turk | 2024-07-26 | 2024-08-09 | 2024-08-08 | [18 empty] | PSA3605 combined into this PSA | ATT-8847 | MIN001.G0000376 | 2024-07-18 | 2024-07-30 | [8 empty] | Pending ERP to move forward | 427 |  | 2024 | 6 | 26 | #REF! | #N/A
ITG-138035 | 4 | NO BUILD |  |  | PSA |  | PSA-3607PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 6 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [52 empty] | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 428 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135886 | 1 | Active |  |  | BBF |  | BBF-PI301-RT3-SEC7-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 7 | Eden Prairie | 401 |  |  | Joseph Smith | [26 empty] | 2024-10-29 | [41 empty] | 429 |  |  |  |  | #REF! | #N/A
ITG-138040 | 4 | HOLD FOR LATER |  |  | PSA | BCL | PSA-3701PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 7 | Eden Prairie | 3 | 7 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  |  |  | 2024-06-04 | JACOB | 2024-06-12 | 2024-06-18 | 2024-06-18 | YES | 3936 | 508 | 2912 | 3420 | 1140 | 2024-07-17 | 2024-08-12 | 2024-08-14 |  |  | 288 | PFP 16700 VALLEY VIEW RD |  | 2024-08-15 | 2024-09-26 | [5 empty] | Spencer Lynn | 2024-08-21 | 2024-09-04 | [20 empty] | ATT-8848 | MIN001.G0000377 | 2024-07-22 | 2024-08-15 | 2024-09-10 | 2024-09-16 | ? | [5 empty] | Field and Layout complete, which MS do we want to bill through? | 430 |  | 2024 | 6 | 25 | #REF! | #N/A
ITG-136788 | 1 | Active |  |  | PSA | SFU | PSA-3702PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 7 | Eden Prairie | 398 | 387 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-24 | 2024-05-26 | 2024-05-30 | HANNAH | 2024-05-30 | 2024-07-09 | 2024-07-09 | YES | 0 | 703 | 22723 | 23426 | 58.8593 | 2024-07-19 | 2024-08-20 | 2024-08-23 |  |  | 576 | PFP 7370 HAMES WAY |  | 2024-08-26 | 2024-10-04 | [5 empty] | Timothy Miller | 2024-09-04 | 2024-09-24 | [20 empty] | ATT-8849 | MIN001.G0000378 | 2024-07-18 | 2024-07-30 | 2024-08-22 | 2024-08-23 | [7 empty] | 431 | 1 | 2024 | 7 | 28 | #REF! | #N/A
ITG-135888 | 1 | Active |  |  | BBF |  | BBF-PI301-RT3-SEC8-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 8 | Eden Prairie | 2401 |  |  | Joseph Smith | [26 empty] | 2024-11-05 | [41 empty] | 432 |  |  |  |  | #REF! | #N/A
ITG-136790 | 1 | Active |  |  | PSA | SFU/School | PSA-3801PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 8 | Eden Prairie | 388 | 390 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-24 | 2024-05-26 | 2024-05-30 | JAEGER | 2024-05-30 | 2024-06-10 | 2024-06-10 | YES | 0 | 1342 | 38892 | 40234 | 103.6959 | 2024-06-27 | 2024-07-10 | 2024-07-12 |  |  | 576 | PFP 17180 MALLARD CT |  | 2024-07-18 | 2024-09-20 | [5 empty] | James Lugo | 2024-07-18 | 2024-08-01 | 2024-07-26 | [18 empty] | 9/6 MJ - CAD DD updated, waiting for BBF to be assigned, PSA3803 combined into this PSA | ATT-8850 | MIN001.G0000379 | 2024-07-18 | 2024-07-30 | 2024-08-13 | 2024-08-14 | [7 empty] | 433 | 1 | 2024 | 6 | 24 | #REF! | #N/A
ITG-136792 | 1 | Active |  |  | PSA | SFU | PSA-3802PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 8 | Eden Prairie | 552 | 547 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-24 | 2024-05-26 | 2024-05-30 | JARGER | 2024-05-30 | 2024-06-26 | 2024-06-26 | YES | 0 | 1612 | 56940 | 58552 | 106.0725 | 2024-07-16 | 2024-07-24 | 2024-07-24 |  |  | 864 | PFP 6534 GRANDVIEW DR |  | 2024-08-02 | 2024-08-22 | 2024-08-20 |  |  |  | 47305 | Jermaine Scott | 2024-07-26 | 2024-08-09 | 2024-08-05 | [18 empty] | PSA3804 combined into this PSA | ATT-8851 | MIN001.G0000380 | 2024-07-18 | 2024-07-30 | 2024-08-22 | 2024-08-23 | [7 empty] | 434 | 1 | 2024 | 6 | 26 | #REF! | #N/A
ITG-136793 | 1 | NO BUILD |  |  | PSA |  | PSA-3803PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 8 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3801 and PSA3805 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 435 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136798 | 1 | NO BUILD |  |  | PSA |  | PSA-3804PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 8 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA Combined into PSA3802 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 436 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136800 | 1 | Active |  |  | PSA | SFU | PSA-3805PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 8 | Eden Prairie | 487 | 455 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-24 | 2024-05-26 | 2024-06-10 | CODY | 2024-06-10 | 2024-07-12 | 2024-07-12 | YES | 4265 | 153 | 34796 | 34949 | 71.7639 | 2024-07-19 | 2024-08-29 | 2024-09-04 |  |  | 864 |  |  | 2024-09-09 | 2024-10-04 | [5 empty] | James Lugo | 2024-09-10 | 2024-09-24 | 2024-09-16 | [18 empty] | PSA3803 combined into this PSA | ATT-8852 | MIN001.G0000381 | 2024-07-18 | 2024-07-30 | 2024-08-22 | 2024-08-23 | [7 empty] | 437 | 1 | 2024 | 7 | 28 | #REF! | #N/A
ITG-136802 | 1 | Active |  |  | PSA | SFU | PSA-3806PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 8 | Eden Prairie | 473 | 475 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-24 | 2024-05-26 | 2024-06-03 | CODY | 2024-06-03 | 2024-06-27 | 2024-06-27 | YES | 0 | 501 | 37222 | 37723 | 79.7526 | 2024-07-17 | 2024-08-05 | 2024-08-14 |  |  | 864 | PFP 7151 TARTAN CURV |  | 2024-08-16 | 2024-08-30 | 2024-08-30 |  |  | 2024-08-30 | 38677 | James Lugo | 2024-08-23 | 2024-09-06 | 2024-08-28 | [19 empty] | ATT-8853 | MIN001.G0000382 | 2024-07-18 | 2024-07-30 | 2024-09-11 | 2024-09-16 | [7 empty] | 438 |  | 2024 | 6 | 26 | #REF! | #N/A
ITG-136803 | 1 | NO BUILD |  |  | PSA |  | PSA-3807PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 8 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-24 | 2024-05-26 | [48 empty] | PSA combined into PSA3808 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 439 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136804 | 1 | Active |  |  | PSA | SFU/BCL | PSA-3808PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 8 | Eden Prairie | 501 | 497 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-24 | 2024-05-26 | 2024-06-03 | HUNTER | 2024-06-04 | 2024-06-20 | 2024-06-20 | YES | 0 | 6112 | 37461 | 43573 | 86.9721 | 2024-07-03 | 2024-07-23 | 2024-07-24 |  |  | 576 | PFP 18973 PLEASANTVIEW RD |  | 2024-08-26 | 2024-09-25 | 2024-09-19 |  |  | 2024-09-19 | 43102 | Jermaine Scott | 2024-08-15 | 2024-08-29 | 2024-08-21 | [18 empty] | 8/26 MJ, Assigned to new drafter, PSA3807 and PSA3809 combined into this PSA | ATT-8854 | MIN001.G0000383 | 2024-07-18 | 2024-07-30 | 2024-08-13 | 2024-08-14 | [7 empty] | 440 | 1 | 2024 | 6 | 25 | #REF! | #N/A
ITG-138044 | 4 | NO BUILD |  |  | PSA |  | PSA-3809PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 8 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA combined into PSA3808 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 441 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-135889 | 1 | Active |  |  | BBF |  | BBF-PI301-RT3-SEC9-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 9 | Eden Prairie | 1140 |  |  | Joseph Smith | [26 empty] | 2024-11-05 | [41 empty] | 442 |  |  |  |  | #REF! | #N/A
ITG-138048 | 4 | NO BUILD |  |  | PSA |  | PSA-3901PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 9 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA combined into PSA3902 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 443 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136806 | 1 | Active |  |  | PSA | MDU/BCL | PSA-3902PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 9 | Eden Prairie | 255 | 2 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  |  |  | 2024-06-03 | SAM | 2024-06-05 | 2024-06-10 | 2024-06-10 | YES | 0 | 3215 | 97 | 3312 | 12.9882 | 2024-07-01 | 2024-07-09 | 2024-07-12 |  |  | 288 | PFP 17972 COBBLESTONE WAY |  | 2024-07-22 | 2024-08-21 | 2024-08-12 |  |  | 2024-08-12 | 3337 | Cheryl Turk | 2024-07-18 | 2024-07-25 | 2024-07-24 | [18 empty] | PSA3901 combined into this PSA | ATT-8855 | MIN001.G0000384 | 2024-07-22 | 2024-08-15 | 2024-09-11 | 2024-09-16 | [7 empty] | 444 |  | 2024 | 6 | 24 | #REF! | #N/A
ITG-136807 | 1 | Active |  |  | PSA | SFU/MDU | PSA-3903PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 9 | Eden Prairie | 585 | 681 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  | 2024-05-24 | 2024-05-26 | 2024-06-03 | SAM | 2024-06-05 | 2024-06-30 | 2024-06-30 | YES | 6421 | 70 | 44891 | 44961 | 76.8564 | 2024-07-15 | 2024-08-07 | 2024-07-24 |  |  | 864 | PFP 8055 LONG MEADOW PT |  | 2024-07-24 | 2024-08-30 | 2024-09-06 |  |  | 2024-09-06 | 44790 | Jordan Struck | 2024-07-26 | 2024-08-09 | 2024-08-10 | [18 empty] | PSA-3904 merged into this PSA 9/4. | ATT-8856 | MIN001.G0000385 | 2024-07-18 | 2024-07-30 | 2024-08-13 | 2024-08-14 | [7 empty] | 445 | 1 | 2024 | 6 | 27 | #REF! | #N/A
ITG-136809 | 1 | NO BUILD |  |  | PSA | MDU | PSA-3904PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 9 | Eden Prairie | 113 |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  |  |  | 2024-06-04 | JACOB | 2024-07-09 | 2024-07-13 | 2024-07-13 | YES | 0 | 415 | 886 | 1301 | 11.5133 | 2024-07-17 | NA | NA | NA | NA | NA | NA |  |  | 2024-09-17 | [27 empty] | 9/5Merged into PSA3903. PSA3905 combined into this PSA | ATT-8857 | MIN001.G0000386 | 2024-07-22 | 2024-08-15 | 2024-09-11 | 2024-09-16 | STOP | STOP | STOP | STOP | STOP | STOP |  | 446 |  | 2024 | 7 | 28 | #REF! | #N/A
ITG-138052 | 4 | NO BUILD |  |  | PSA |  | PSA-3905PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 9 | Eden Prairie |  |  |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman | [51 empty] | PSA combined into PSA3904 | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 447 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-136810 | 1 | Active |  |  | PSA | MDU | PSA-3906PA-EDPRMNPI-CHARLIE | EDPRMNPI | RTE #3 | BBF RTE 3 SEC 9 | Eden Prairie | 187 | 162 |  | Merylene Hickman |  | 2024-01-19 | Merylene Hickman |  |  |  | 2024-06-03 | SAM | 2024-06-05 | 2024-06-06 | 2024-06-06 | YES | 0 | 266 | 1063 | 1329 | 7.107 | 2024-07-12 | 2024-07-31 | 2024-07-30 |  |  | 288 | PFP 18274 CONEFLOWER LN |  | 2024-08-01 | 2024-08-28 | 2024-08-27 |  |  | 2024-08-26 | 801 | Spencer Lynn | 2024-09-04 | 2024-09-11 | 2024-09-11 | [19 empty] | ATT-8858 | MIN001.G0000387 | 2024-07-22 | 2024-08-15 | 2024-09-11 | 2024-09-16 | [7 empty] | 448 |  | 2024 | 6 | 23 | #REF! | #N/A
ITG-163469 |  | Active |  |  | BBF |  | BBF-YF101-RTE1-SEC1-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 1 | Apple Valley | 3032 |  |  | Carla Jeffers |  | 2024-09-24 | [14 empty] | 0 | [51 empty] | 449
ITG-163457 |  | No Build - Ex Comp |  |  | PSA | SFU | PSA-1101PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 1 | Apple Valley | 648 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | EX COMP | [47 empty] | fielder found competition in these PSA areas these can go NO BUILD. | [6 empty] | STOP | STOP | STOP | STOP | STOP | STOP |  | 450
ITG-163458 |  | No Build - Ex Comp |  |  | PSA | SFU/BCL | PSA-1102PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 1 | Apple Valley | 556 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | EX COMP | [47 empty] | fielder found competition in these PSA areas these can go NO BUILD. | [6 empty] | STOP | STOP | STOP | STOP | STOP | STOP |  | 451
ITG-163459 |  | No Build - Ex Comp |  |  | PSA | SFU/BCL/MDU | PSA-1103PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 1 | Apple Valley | 623 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | EX COMP | [47 empty] | fielder found competition in these PSA areas these can go NO BUILD. | [6 empty] | STOP | STOP | STOP | STOP | STOP | STOP |  | 452
ITG-163460 |  | No Build - Ex Comp |  |  | PSA | SFU/BCL/MDU | PSA-1104PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 1 | Apple Valley | 680 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | EX COMP | [47 empty] | fielder found competition in these PSA areas these can go NO BUILD. | [6 empty] | STOP | STOP | STOP | STOP | STOP | STOP |  | 453
ITG-163461 |  | No Build - Ex Comp |  |  | PSA | SFU/BCL | PSA-1105PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 1 | Apple Valley | 525 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | EX COMP | [47 empty] | fielder found competition in these PSA areas these can go NO BUILD. | [6 empty] | STOP | STOP | STOP | STOP | STOP | STOP |  | 454
ITG-163462 |  | Active |  |  | PSA | SFU/MDU | PSA-1106PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 1 | Apple Valley | 632 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | [62 empty] | 455
ITG-163463 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1107PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 1 | Apple Valley | 644 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | [62 empty] | 456
ITG-163465 |  | Active |  |  | PSA | SFU | PSA-1108PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 1 | Apple Valley | 614 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | [62 empty] | 457
ITG-163466 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1109PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 1 | Apple Valley | 499 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | [62 empty] | 458
ITG-163467 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1110PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 1 | Apple Valley | 652 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | [62 empty] | 459
ITG-163468 |  | Active |  |  | PSA | SFU/BCL | PSA-1111PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 1 | Apple Valley | 647 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | [62 empty] | 460
ITG-163506 |  | Active |  |  | BBF |  | BBF-YF101-RTE1-SEC2-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 2 | Apple Valley | 1214 |  |  | Carla Jeffers |  | 2024-09-24 | [66 empty] | 461
ITG-163507 |  | No Build - Ex Comp |  |  | PSA | SFU/MDU | PSA-1201PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 2 | Apple Valley | 572 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | EX COMP | [47 empty] | fielder found competition in these PSA areas these can go NO BUILD. | [6 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 462
ITG-163508 |  | Active |  |  | PSA | SFU | PSA-1202PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 2 | Apple Valley | 642 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | [62 empty] | 463
ITG-163509 |  | Active |  |  | BBF |  | BBF-YF101-RTE1-SEC3-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 3 | Apple Valley | 1979 |  |  | Carla Jeffers |  | 2024-09-24 | [66 empty] | 464
ITG-163510 |  | Active |  |  | PSA | MDU | PSA-1301PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 3 | Apple Valley | 457 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | [62 empty] | 465
ITG-163511 |  | Active |  |  | PSA | MDU | PSA-1302PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 3 | Apple Valley | 526 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | [62 empty] | 466
ITG-163512 |  | No Build - Ex Comp |  |  | PSA | SFU | PSA-1303PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 3 | Apple Valley | 470 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | EX COMP | [47 empty] | fielder found competition in these PSA areas these can go NO BUILD. | [6 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 467
ITG-163513 |  | Active |  |  | PSA | BCL/MDU | PSA-1304PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 3 | Apple Valley | 507 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | [62 empty] | 468
ITG-163514 |  | Active |  |  | PSA | SFU | PSA-1305PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 3 | Apple Valley | 476 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-25 | 2024-09-26 | [62 empty] | 469
ITG-163471 |  | Active |  |  | BBF |  | BBF-YF101-RTE1-SEC4-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Apple Valley and Rosemount | 11021 |  |  | Carla Jeffers |  | 2024-09-24 | [66 empty] | 470
ITG-163472 |  | Active |  |  | PSA | SFU/BCL | PSA-1401PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Apple Valley | 375 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 471
ITG-163473 |  | Active |  |  | PSA | MDU | PSA-1402PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Apple Valley | 344 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 472
ITG-163475 |  | Active |  |  | PSA | BCL/MDU | PSA-1403PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Apple Valley | 349 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 473
ITG-163476 |  | Active |  |  | PSA | BCL/MDU | PSA-1404PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Apple Valley | 450 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 474
ITG-163477 |  | Active |  |  | PSA | BCL/MDU | PSA-1405PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Apple Valley | 544 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 475
ITG-163478 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1406PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Apple Valley | 584 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 476
ITG-163479 |  | Active |  |  | PSA | SFU | PSA-1407PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Apple Valley | 390 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 477
ITG-163480 |  | Active |  |  | PSA | SFU/MDU/PRIVATE | PSA-1408PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Apple Valley | 527 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 478
ITG-163481 |  | Active |  |  | PSA | SFU/BCL | PSA-1409PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Apple Valley | 645 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 479
ITG-163482 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1410PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Apple Valley | 486 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 480
ITG-163483 |  | Active |  |  | PSA | SFU/BCL | PSA-1411PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Apple Valley | 343 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 481
ITG-163484 |  | Active |  |  | PSA | SFU | PSA-1412PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 642 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 482
ITG-163485 |  | Active |  |  | PSA | SFU/MDU | PSA-1413PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 630 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 483
ITG-163487 |  | Active |  |  | PSA | BCL/MDU | PSA-1414PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 639 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 484
ITG-163488 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1415PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 552 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 485
ITG-163489 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1416PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 567 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 486
ITG-163491 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1417PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 647 |  |  | Carla Jeffers | 1x64 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 487
ITG-163493 |  | Active |  |  | PSA | BCL | PSA-1418PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 50 |  |  | Carla Jeffers | 1x32 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 488
ITG-163494 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1419PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 373 |  |  | Carla Jeffers | 1x32 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 489
ITG-163496 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1420PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 374 |  |  | Carla Jeffers | 1x32 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 490
ITG-163497 |  | Active |  |  | PSA | SFU/MDU | PSA-1421PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 648 |  |  | Carla Jeffers | 1x32 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 491
ITG-163498 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1422PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 107 |  |  | Carla Jeffers | 1x32 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 492
ITG-163500 |  | Active |  |  | PSA | SFU/MDU | PSA-1423PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 623 |  |  | Carla Jeffers | 1x32 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 493
ITG-163501 |  | Active |  |  | PSA | SFU/BCL | PSA-1424PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 46 |  |  | Carla Jeffers | 1x32 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 494
ITG-163502 |  | Active |  |  | PSA | SFU/BCL | PSA-1425PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 68 |  |  | Carla Jeffers | 1x32 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 495
ITG-163504 |  | Active |  |  | PSA | BCL | PSA-1426PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 4 | Rosemount | 18 |  |  | Carla Jeffers | 1x32 | 2024-09-24 |  |  | 2024-09-26 | [63 empty] | 496
|  | Active |  |  | BBF |  | BBF-YF101-RTE1-SEC5-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Apple Valley and Rosemount | 8883 |  |  | Tammi Baker |  | 2024-09-27 | [66 empty] | 470
|  | Active |  |  | PSA | BCL | PSA-1501PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Apple Valley | 568 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU/BCL | PSA-1502PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Apple Valley | 623 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1503PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Apple Valley | 457 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU | PSA-1504PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Apple Valley | 680 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | BCL | PSA-1505PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Apple Valley | 400 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU | PSA-1506PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Apple Valley | 376 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU/BCL | PSA-1507PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Apple Valley | 555 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU | PSA-1508PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Apple Valley | 522 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU/BCL | PSA-1509PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Apple Valley & Rosemount | 562 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU | PSA-1510PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Apple Valley & Rosemount | 600 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU | PSA-1511PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Rosemount | 424 |  |  | Tammi Baker | 1X32 | 2024-09-27
|  | Active |  |  | PSA | SFU/MDU | PSA-1512PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Rosemount | 561 |  |  | Tammi Baker | 1x32 | 2024-09-27
|  | Active |  |  | PSA | SFU/BCL/MDU | PSA-1513PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Rosemount | 448 |  |  | Tammi Baker | 1x32 | 2024-09-27
|  | Active |  |  | PSA | SFU/MDU | PSA-1514PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Rosemount | 513 |  |  | Tammi Baker | 1x32 | 2024-09-27
|  | Active |  |  | PSA | SFU/BCL | PSA-1515PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Rosemount | 359 |  |  | Tammi Baker | 1x32 | 2024-09-27
|  | Active |  |  | PSA | SFU/BCL | PSA-1516PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Rosemount | 261 |  |  | Tammi Baker | 1x32 | 2024-09-27
|  | Active |  |  | PSA | SFU/MDU | PSA-1517PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Rosemount | 599 |  |  | Tammi Baker | 1x32 | 2024-09-27
|  | Active |  |  | PSA | SFU | PSA-1518PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 5 | Rosemount | 375 |  |  | Tammi Baker | 1x32 | 2024-09-27
[5 empty] | BBF |  | BBF-YF101-RTE1-SEC6-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 6 | Apple Valley and Rosemount | 3344 |  |  | Tammi Baker |  | 2024-09-27
|  | Active |  |  | PSA | SFU | PSA-1601PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 6 | Rosemount | 548 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU | PSA-1602PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 6 | Rosemount | 642 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU/MDU | PSA-1603PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 6 | Rosemount | 623 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU/BCL | PSA-1604PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 6 | Rosemount | 202 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU/BCL | PSA-1605PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 6 | Rosemount | 378 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU | PSA-1606PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 6 | Apple Valley & Rosemount | 352 |  |  | Tammi Baker | 1x32 | 2024-09-27
|  | Active |  |  | PSA | SFU/MDU | PSA-1607PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 6 | Apple Valley | 599 |  |  | Tammi Baker | 1x32 | 2024-09-27
[5 empty] | BBF |  | BBF-YF101-RTE1-SEC7-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 7 | Apple Valley | 1441 |  |  | Tammi Baker |  | 2024-09-27
|  | Active |  |  | PSA | SFU/MDU | PSA-1701PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 7 | Apple Valley | 307 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU | PSA-1702PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 7 | Apple Valley | 551 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | MDU/BCL | PSA-1703PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 7 | Apple Valley | 526 |  |  | Tammi Baker | 1x64 | 2024-09-27
|  | Active |  |  | PSA | SFU | PSA-1704PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #1 | BBF RTE 1 SEC 7 | Apple Valley | 364 |  |  | Tammi Baker | 1x64 | 2024-09-27
ITG-151770 |  | Active |  |  | BBF |  | BBF-YF201-RTE2-SEC1-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 1 | Lakeville | 2120 |  |  | Carla Jeffers | [7 empty] | JAEGER | 2024-08-09 | 2024-08-12 | 2024-08-10 | NA | 11342 | 0 | 0 | 0 | 0 | [8 empty] | 2024-08-13 | 2024-08-29 | 2024-09-04 | 2024-09-19 | 2024-09-20 | 2024-09-20 | [9 empty] | 2024-09-16 | 2024-09-18 | 2024-09-19 |  | In Construction | 2024-09-25 | [8 empty] | 9/19 Change in plan, remove pwr duct it will be placed by DEA. 9/16 CAD approved forwarded to Kaylie for permit. 9/13 sent CAD corrections back, pending decision on Loc 1 changing from VZ. | [13 empty] | 497
ITG-151775 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2101PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 1 | Lakeville | 279 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9420 | MIN001.G0000541 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 498
ITG-151777 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2102PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 1 | Lakeville | 492 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9421 | MIN001.G0000542 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 499
ITG-151778 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2103PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 1 | Lakeville | 403 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9422 | MIN001.G0000543 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 500
ITG-151779 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2104PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 1 | Lakeville | 446 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9309 | MIN001.G0000437 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 501
ITG-151780 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2105PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 1 | Lakeville | 500 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9310 | MIN001.G0000438 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 502
ITG-151781 |  | No Build - Ex Comp |  |  | BBF |  | BBF-YF201-RTE2-SEC2-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 2 | Lakeville | 718 | [64 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 503
ITG-151783 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2201PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 2 | Lakeville | 410 | [7 empty] | 2024-07-31 | 2024-08-02 | EX COMP | HUNTER |  | NA |  |  | 17000 |  |  | 0 | 0 | [37 empty] | 8/2 Fielder assigned 17,000' for prefield survey to check for existing competition in the area. | ATT-9311 | MIN001.G0000439 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 504
ITG-151784 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2202PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 2 | Lakeville | 308 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9423 | MIN001.G0000544 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 505
ITG-151786 |  | No Build - Ex Comp |  |  | BBF |  | BBF-YF201-RTE2-SEC3-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 3 | Lakeville | 444 | [64 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 506
ITG-151787 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2301PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 3 | Lakeville | 444 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9312 | MIN001.G0000440 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 507
ITG-151788 |  | No Build - Ex Comp |  |  | BBF |  | BBF-YF201-RTE2-SEC4-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 4 | Lakeville | 1239 | [64 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 508
ITG-151790 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2402PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 4 | Lakeville | 337 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9313 | MIN001.G0000441 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 509
ITG-151792 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2403PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 4 | Lakeville | 559 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9314 | MIN001.G0000442 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 510
ITG-151853 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2404PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 4 | Lakeville | 343 | [7 empty] | 2024-07-31 | 2024-08-02 | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9315 | MIN001.G0000443 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 511
ITG-151854 |  | Active |  |  | BBF |  | BBF-YF201-RTE2-SEC5-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 5 | Lakeville | 1069 | [13 empty] | 2024-09-25 | [15 empty] | 2024-11-05 | [41 empty] | 512
ITG-151927 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2501PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 5 | Lakeville | 497 | [7 empty] | 2024-07-31 | 2024-08-02 | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9317 | MIN001.G0000444 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 513
ITG-151929 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2502PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 5 | Lakeville | 572 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9318 | MIN001.G0000445 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 514
ITG-151930 |  | Active |  |  | BBF |  | BBF-YF201-RTE2-SEC6-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 6 | Lakeville | 2216 | [13 empty] | 2024-09-25 | [15 empty] | 2024-11-05 | [41 empty] | 515
ITG-151931 |  | Active |  |  | PSA | SFU/MDU | PSA-2601PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 6 | Lakeville | 683 | 467 | [6 empty] | 2024-07-31 | 2024-08-02 | 2024-08-06 | SAM | 2024-08-07 | 2024-08-23 | 2024-08-21 | YES | 17482 | 505 | 9389 | 9894 | 14.4861 | 2024-08-22 | 2024-09-05 | 2024-09-05 |  |  | 576 | PFP 17041 ENCINA PATH |  | 2024-09-09 | 2024-10-04 | [5 empty] | Timothy Miller | 2024-09-10 | 2024-10-08 | [19 empty] | Portion of PSA2604 has been added to this PSA | ATT-9319 | MIN001.G0000446 | [11 empty] | 516
ITG-151932 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2602PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 6 | Lakeville | 506 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9320 | MIN001.G0000447 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 517
ITG-151933 |  | Active |  |  | PSA |  | PSA-2603PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 6 | Lakeville | 497 | [7 empty] | 2024-07-31 | 2024-08-02 | 2024-08-06 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 |  | 2024-10-08 | [35 empty] | Trailer park are with no R/W, do not need to field job. Need to leave F1 count in the POF HH for future service. No permit needed. Ex. Comp area is now no build PSA2605 | ATT-9321 | MIN001.G0000448 | [11 empty] | 518
ITG-151934 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2604PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 6 | Lakeville | 530 | 210 | [6 empty] | 2024-07-31 | 2024-08-02 | 2024-08-06 | SAM | 2024-08-07 | 2024-08-23 | 2024-08-19 | YES | 0 | 1625 | 3812 | 5437 | 10.2585 | 2024-08-20 | 2024-09-05 | 2024-09-05 |  |  | 288 | PFP 5247 173RD ST W |  | 2024-09-09 | 2024-09-26 | [5 empty] | Timothy Miller | 2024-09-10 | 2024-10-01 | [19 empty] | Existing Competition | ATT-9322 | MIN001.G0000449 |  |  |  |  | ? | [5 empty] | Design and CAD complete, which MS do we want to bill through? | 519
ITG-163347 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2605PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 2 SEC 6 | Lakeville | 133 | [57 empty] | This is the existing comp portion of PSA2603. No a no build | ATT-9425 | MIN001.G0000546 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 520
ITG-151935 |  | Active |  |  | BBF |  | BBF-YF201-RTE2-SEC7-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 7 | Lakeville & Farmington | 3280 | [13 empty] | 2024-09-25 | [15 empty] | 2024-11-05 | [41 empty] | 521
ITG-151936 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2701PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 7 | Lakeville | 551 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9323 | MIN001.G0000450 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 522
ITG-151937 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2702PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 7 | Lakeville | 488 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9324 | MIN001.G0000451 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 523
ITG-151938 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2703PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 7 | Lakeville | 334 | [7 empty] | 2024-07-31 | 2024-08-02 | EX COMP | [48 empty] | ATT-9325 | MIN001.G0000452 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 524
ITG-151687 |  | Active |  |  | PSA |  | PSA-2704PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 7 | Farmington | 648 | 640 | [6 empty] | 2024-07-26 | 2024-07-28 | 2024-08-01 | SAM | 2024-08-02 | 2024-08-23 | 2024-08-15 | YES | 3718 | 572 | 34149 | 34721 | 53.5818 | 2024-08-22 | 2024-09-05 | 2024-09-05 |  |  | 864 | PFP 18298 ENGLISH AVE |  | 2024-09-11 | 2024-09-26 | 2024-09-25 |  |  | 2024-09-25 | 35550 | Elizabeth Heinl | 2024-09-10 | 2024-09-27 | [20 empty] | ATT-9326 | MIN001.G0000453 | [11 empty] | 525
ITG-151688 |  | Active |  |  | PSA |  | PSA-2705PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 7 | Farmington | 603 | [7 empty] | 2024-07-26 | 2024-07-28 | 2024-08-01 | HANNAH | 2024-08-02 | 2024-09-16 | 2024-09-16 | YES | 0 | 432 | 50287 | 50719 | 84.1111 | 2024-09-18 | 2024-10-01 | [7 empty] | 2024-10-22 | [28 empty] | ATT-9327 | MIN001.G0000454 | [11 empty] | 526
ITG-151689 |  | Active |  |  | PSA |  | PSA-2706PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 7 | Farmington | 656 | 654 | [6 empty] | 2024-07-26 | 2024-07-28 | 2024-08-01 | JOSH | 2024-08-02 | 2024-08-19 | 2024-08-15 | YES | 0 | 402 | 49817 | 50219 | 76.5534 | 2024-08-19 | 2024-09-02 | 2024-09-05 |  |  | 864 | PFP 18568 EUCLID PATH |  | 2024-09-09 | 2024-09-24 | 2024-09-20 |  |  | 2024-09-17 | 42047 | Jordan Struck | 2024-09-10 | 2024-09-24 | [20 empty] | ATT-9328 | MIN001.G0000455 | [11 empty] | 527
ITG-151686 |  | Active |  |  | PSA |  | PSA-2707PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 4 | Farmington | 450 | 431 | [6 empty] | 2024-07-26 | 2024-07-28 | 2024-08-01 | CODY | 2024-08-02 | 2024-08-26 | 2024-08-26 | YES | 3037 | 1523 | 37474 | 38997 | 86.66 | 2024-08-26 | 2024-09-10 | 2024-09-05 |  |  | 864 | PFP 17913 EVENTIDE WAY |  | 2024-09-06 | 2024-10-02 | [5 empty] | Yuliet Munoz | 2024-09-10 | 2024-09-27 | [19 empty] | 8/23 This PSA was previously 2401 - renamed to 2707. 8/9 job area is suspect for existing competition, waiting on direction on completing fielding. There are some fiber peds from Gigabit. Continuing with fielding on this job per Don 8/15. | ATT-9329 | MIN001.G0000456 | [11 empty] | 528
ITG-151939 |  | Active |  |  | BBF |  | BBF-YF201-RTE2-SEC8-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 8 | Farmington | 2986 | [13 empty] | 2024-09-25 | [15 empty] | 2024-11-05 | [41 empty] | 529
ITG-151690 |  | Active |  |  | PSA |  | PSA-2801PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 8 | Farmington | 643 | 641 | [6 empty] | 2024-07-26 | 2024-07-28 | 2024-08-01 | JAEGER | 2024-08-02 | 2024-08-16 | 2024-08-14 | YES | 5096 | 914 | 45590 | 46504 | 72.3235 | 2024-08-19 | 2024-08-30 | 2024-09-04 |  |  | 864 | PFP 19200 ESTATE AVE |  | 2024-09-09 | 2024-10-03 | [5 empty] | Eric Lynn | 2024-09-10 | 2024-09-24 | [20 empty] | ATT-9330 | MIN001.G0000457 | [11 empty] | 530
ITG-151691 |  | Active |  |  | PSA |  | PSA-2802PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 8 | Farmington | 508 | 493 | [6 empty] | 2024-07-26 | 2024-07-28 | 2024-08-06 | JACOB | 2024-08-06 | 2024-08-20 | 2024-08-11 | YES | 0 | 1026 | 48225 | 49251 | 96.9508 | 2024-08-14 | 2024-08-29 | 2024-09-05 |  |  | 864 | PFP 19229 DUNBURRY AVE |  | 2024-09-09 | 2024-10-04 | [5 empty] | James Lugo | 2024-09-10 | 2024-09-24 | 2024-09-20 | [19 empty] | ATT-9331 | MIN001.G0000458 | [11 empty] | 531
ITG-151692 |  | Active |  |  | PSA |  | PSA-2803PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 8 | Farmington | 561 | 376 | [6 empty] | 2024-07-26 | 2024-07-28 | 2024-08-01 | ERIK | 2024-08-02 | 2024-08-16 | 2024-08-11 | YES | 0 | 1968 | 25182 | 27150 | 48.3957 | 2024-08-14 | 2024-08-29 | 2024-09-05 |  |  | 864 | PFP 19540 EVEREST PATH |  | 2024-09-06 | 2024-10-04 | [5 empty] | Jermaine Scott | 2024-09-10 | 2024-09-24 | [20 empty] | ATT-9332 | MIN001.G0000459 | [11 empty] | 532
ITG-151940 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2804PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 8 | Farmington | 537 | [7 empty] | 2024-07-26 | 2024-07-28 | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9333 | MIN001.G0000460 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 533
ITG-151941 |  | Active |  |  | PSA |  | PSA-2805PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 8 | Farmington | 466 | 390 | [6 empty] | 2024-07-31 | 2024-08-02 | 2024-08-06 | CODY | 2024-08-07 | 2024-08-28 | 2024-08-27 | YES | 0 | 6296 | 28529 | 34825 | 74.7318 | 2024-08-28 | 2024-09-19 | 2024-09-18 |  |  | 864 | PFP 19785 DOVER DR |  | 2024-09-18 | 2024-10-04 | [28 empty] | ATT-9334 | MIN001.G0000461 | [11 empty] | 534
ITG-151942 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2806PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 8 | Farmington | 260 | [7 empty] | 2024-07-31 | 2024-08-02 | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9335 | MIN001.G0000462 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 535
ITG-151943 |  | Project Cancel |  |  | PSA |  | PSA-2807PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 8 | Farmington | 11 | [7 empty] | 2024-07-31 | 2024-08-02 | CANCEL | [8 empty] | 0 | 0 | [37 empty] | 8/7 job was combined with PSA-2401 and PSA-2803, can cancel. | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 536
ITG-151944 |  | Active |  |  | BBF |  | BBF-YF201-RTE2-SEC9-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 9 | Farmington | 793 | [13 empty] | 2024-09-25 | [15 empty] | 2024-11-05 | [41 empty] | 537
ITG-151693 |  | Active |  |  | PSA |  | PSA-2901PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 9 | Farmington | 524 | 411 | [6 empty] | 2024-07-26 | 2024-07-28 | 2024-08-01 | HUNTER | 2024-08-02 | 2024-08-16 | 2024-08-13 | YES | 5547 | 510 | 21932 | 22442 | 42.8282 | 2024-08-14 | 2024-08-30 | 2024-09-05 |  |  | 864 | PFP 20602 CLAIRE CT |  | 2024-09-09 | 2024-09-27 | 2024-09-24 |  |  |  |  | Elizabeth Heinl | 2024-09-10 | 2024-10-04 | [20 empty] | ATT-9336 | MIN001.G0000463 | [11 empty] | 538
ITG-151945 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2902PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 9 | Farmington | 269 | [7 empty] | 2024-07-31 | 2024-08-02 | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9424 | MIN001.G0000545 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 539
ITG-151946 |  | No Build - Ex Comp |  |  | BBF |  | BBF-YF201-RTE2-SEC11-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 11 | Farmington | 211 | [64 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 540
ITG-151948 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2111PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 11 | Farmington | 211 | [7 empty] | 2024-07-31 | 2024-08-02 | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9337 | MIN001.G0000464 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 541
ITG-151949 |  | Active |  |  | BBF |  | BBF-YF201-RTE2-SEC12-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 12 | Farmington | 1570 | [13 empty] | 2024-09-25 | [15 empty] | 2024-11-05 | [41 empty] | 542
ITG-151950 |  | Active |  |  | PSA |  | PSA-2121PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 12 | Farmington | 469 | 283 | [6 empty] | 2024-07-31 | 2024-08-02 | 2024-08-09 | HUNTER | 2024-08-09 | 2024-08-23 | 2024-08-20 | YES | 10785 | 56 | 25091 | 25147 | 53.6183 | 2024-08-23 | 2024-09-17 | 2024-09-18 |  |  | 576 | PFP 310 DIVISION ST |  | 2024-09-18 | 2024-10-02 | [5 empty] | Jordan Struck | 2024-09-26 | 2024-10-10 | [20 empty] | ATT-9426 | MIN001.G0000547 | [11 empty] | 543
ITG-151954 |  | Active |  |  | PSA |  | PSA-2122PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 12 | Farmington | 573 | 566 | [6 empty] | 2024-07-31 | 2024-08-02 | 2024-08-09 | JACOB | 2024-08-13 | 2024-08-23 | 2024-08-18 | YES | 2769 | 103 | 35692 | 35795 | 62.4695 | 2024-08-19 | 2024-09-02 | 2024-09-05 |  |  | 864 | PFP 421 ELM ST |  | 2024-09-05 | 2024-09-27 | 2024-09-27 |  |  | 2024-09-27 | 28522 | Cheryl Turk | 2024-09-10 | 2024-09-24 | [20 empty] | ATT-9427 | MIN001.G0000548 | [11 empty] | 544
ITG-151957 |  | No Build - Ex Comp |  |  | PSA |  | PSA-2123PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 12 | Farmington | 528 | [9 empty] | EX COMP | [8 empty] | 0 | 0 | [38 empty] | ATT-9428 | MIN001.G0000549 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 545
ITG-151959 |  | Active |  |  | BBF |  | BBF-YF201-RTE2-SEC13-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 13 | Farmington | 1876 | [29 empty] | 2024-11-05 | [41 empty] | 546
ITG-151962 |  | Active |  |  | PSA |  | PSA-2131PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 13 | Farmington | 630 | [7 empty] | 2024-07-31 | 2024-08-02 | 2024-08-09 | ERIK | 2024-08-14 | 2024-09-20 | 2024-09-19 |  | 0 | 3340 | 12034 | 15374 | 24.4032 |  | 2024-10-07 | [7 empty] | 2024-10-24 | [28 empty] | ATT-9429 | MIN001.G0000550 | [11 empty] | 547
ITG-151964 |  | Active |  |  | PSA |  | PSA-2132PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 13 | Farmington | 648 | 244 | [6 empty] | 2024-07-31 | 2024-08-02 | 2024-08-09 | CODY | 2024-08-14 | 2024-09-09 | 2024-09-09 | YES | 3534 | 34 | 23689 | 23723 | 36.6096 | 2024-09-09 | 2024-09-23 | 2024-09-24 |  |  | 576 | PFP 3478 220TH ST |  | 2024-09-23 | 2024-10-10 | [28 empty] | ATT-9430 | MIN001.G0000551 | [11 empty] | 548
ITG-151965 |  | Active |  |  | PSA |  | PSA-2133PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #2 | BBF RTE 2 SEC 13 | Farmington | 598 | 581 | [6 empty] | 2024-07-31 | 2024-08-02 | 2024-08-13 | HUNTER | 2024-08-14 | 2024-08-29 | 2024-08-29 | YES | 0 | 346 | 35603 | 35949 | 60.1154 | 2024-08-30 | 2024-09-23 | 2024-09-24 |  |  | 864 | PFP 718 ASH ST |  | 2024-09-20 | 2024-10-11 | [28 empty] | ATT-9431 | MIN001.G0000552 | [11 empty] | 549
ITG-148340 |  | No Build - Ex Comp |  |  | BBF |  | BBF-YF301-RTE3-SEC1-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 1 | Lakeville | 1608 | [64 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 550 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148343 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3101PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 1 | Lakeville | 588 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9338 | MIN001.G0000465 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 551 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148344 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3102PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 1 | Lakeville | 625 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9339 | MIN001.G0000466 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 552 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148345 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3103PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 1 | Lakeville | 395 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9340 | MIN001.G0000467 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 553 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148346 |  | No Build - Ex Comp |  |  | BBF |  | BBF-YF301-RTE3-SEC2-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 2 | Lakeville | 2025 | [64 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 554 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148347 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3201PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 2 | Lakeville | 548 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9341 | MIN001.G0000468 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 555 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148348 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3202PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 2 | Lakeville | 437 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9342 | MIN001.G0000469 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 556 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148349 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3203PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 2 | Lakeville | 420 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9343 | MIN001.G0000470 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 557 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148350 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3204PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 2 | Lakeville | 620 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9344 | MIN001.G0000471 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 558 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148354 |  | No Build - Ex Comp |  |  | BBF |  | BBF-YF301-RTE3-SEC3-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 3 | Lakeville | 1319 | [64 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 559 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148355 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3301PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 3 | Lakeville | 414 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9345 | MIN001.G0000472 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 560 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148356 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3302PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 3 | Lakeville | 319 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9346 | MIN001.G0000473 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 561 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148357 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3303PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 3 | Lakeville | 586 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9347 | MIN001.G0000474 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 562 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148358 |  | Active |  |  | BBF |  | BBF-YF301-RTE3-SEC4-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 4 | Lakeville | 580 | [71 empty] | 563 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148359 |  | Project Cancel |  |  | PSA |  | PSA-3401PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 4 | Lakeville | 9 | [7 empty] | 2024-07-16 | 2024-07-19 | [48 empty] | Combining Southern portion of this PSA with PSA-3131. Houses on Norhtern portion will be a no build. | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 564 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148360 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3402PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 4 | Lakeville | 571 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9348 | MIN001.G0000475 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 565 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148450 |  | Active |  |  | BBF |  | BBF-YF301-RTE3-SEC5-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 5 | Lakeville | 2142 | [71 empty] | 566 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148451 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3501PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 5 | Lakeville | 423 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9349 | MIN001.G0000476 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 567 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148453 |  | Active |  |  | PSA | SFU | PSA-3502PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 5 | Lakeville | 540 | 381 | [6 empty] | 2024-07-16 | 2024-07-19 | 2024-08-19 | SAM | 2024-08-23 | 2024-09-06 | 2024-09-02 | YES | 6093 | 1697 | 23008 | 24705 | 45.75 | 2024-09-04 | 2024-09-23 | 2024-09-25 |  |  | 864 | PFP 16932 ISLAND TERRACE |  | 2024-09-20 | 2024-10-08 | [28 empty] | ATT-9350 | MIN001.G0000477 | [11 empty] | 568 |  | 2024 | 9 | 36 | #REF! | #N/A
ITG-148454 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3503PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 5 | Lakeville | 577 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9351 | MIN001.G0000478 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 569 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148456 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3504PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 5 | Lakeville | 602 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9353 | MIN001.G0000479 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 570 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148458 |  | No Build - Ex Comp |  |  | BBF |  | BBF-YF301-RTE3-SEC6-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 6 | Lakeville | 860 | [64 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 571 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148461 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3601PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 6 | Lakeville | 459 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9357 | MIN001.G0000480 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 572 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148467 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3602PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 6 | Lakeville | 401 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9358 | MIN001.G0000481 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 573 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148469 |  | Active |  |  | BBF |  | BBF-YF301-RTE3-SEC7-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 7 | Lakeville | 1796 | [71 empty] | 574 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148470 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3701PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 7 | Lakeville | 455 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9359 | MIN001.G0000482 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 575 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148472 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-3702PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 7 | Lakeville | 232 | [7 empty] | 2024-07-16 | 2024-07-19 | 2024-07-19 | JOSH | 2024-08-23 | 2024-09-11 | 2024-09-06 | YES | 7062 | 237 | 24567 | 24804 | 106.9138 | 2024-09-13 | 2024-09-27 | [6 empty] | 2024-09-25 | 2024-10-11 | [28 empty] | ATT-9360 | MIN001.G0000483 | [11 empty] | 576 |  | 2024 | 9 | 36 | #REF! | #N/A
ITG-148473 |  | Active |  |  | PSA | SFU/MDU | PSA-3703PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 7 | Lakeville | 552 | [7 empty] | 2024-07-16 | 2024-07-19 | 2024-07-22 | SAM | 2024-09-04 | 2024-09-12 | 2024-09-11 | YES | 2804 | 3673 | 21203 | 24876 | 45.0652 | 2024-09-11 | 2024-09-27 | [6 empty] | 2024-09-26 | 2024-10-16 | [27 empty] | need to find reroute to get to PSA to avoid HWY overpass crossing, sent email on 8/15 for more direction. | ATT-9361 | MIN001.G0000484 | [11 empty] | 577 |  | 2024 | 9 | 37 | #REF! | #N/A
ITG-148475 |  | Active |  |  | PSA | SFU | PSA-3704PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 7 | Lakeville | 557 | [7 empty] | 2024-07-16 | 2024-07-19 | 2024-07-22 | SAM | 2024-09-04 | 2024-09-23 | 2024-09-22 | YES | 0 | 0 | 40692 | 40692 | 73.0557 |  | 2024-10-09 | [7 empty] | 2024-10-29 | [27 empty] | need to find reroute to get to PSA to avoid HWY overpass crossing, sent email on 8/15 for more direction. | ATT-9362 | MIN001.G0000485 | [11 empty] | 578 |  | 2024 | 9 | 39 | #REF! | #N/A
ITG-148476 |  | Active |  |  | BBF |  | BBF-YF301-RTE3-SEC8-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 8 | Lakeville | 1132 | [71 empty] | 579 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148477 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3801PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 8 | Lakeville | 585 | [7 empty] | 2024-07-16 | 2024-07-19 | EX COMP | [48 empty] | ATT-9363 | MIN001.G0000486 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 580 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148479 |  | Active |  |  | PSA | SFU | PSA-3802PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 8 | Lakeville | 547 | 536 | [6 empty] | 2024-07-16 | 2024-07-19 | 2024-07-23 | JAEGER | 2024-08-15 | 2024-08-23 | 2024-08-28 | YES | 0 | 894 | 45486 | 46380 | 84.7898 | 2024-09-03 | 2024-09-23 | 2024-09-25 |  |  | 864 | PFP 18950 IRVONA AVE |  | 2024-09-19 | 2024-10-11 | [5 empty] | Yuliet Munoz | 2024-09-27 | 2024-10-11 | [20 empty] | ATT-9364 | MIN001.G0000487 | [11 empty] | 581 |  | 2024 | 8 | 35 | #REF! | #N/A
ITG-148480 |  | Active |  |  | BBF |  | BBF-YF301-RTE3-SEC9-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 9 | Lakeville | 871 | [71 empty] | 582 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148482 |  | Active |  |  | PSA | SFU | PSA-3901PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 9 | Lakeville | 558 | [7 empty] | 2024-07-16 | 2024-07-19 | 2024-07-22 | HANNAH | 2024-08-15 | 2024-09-19 | 2024-09-23 | YES | 6455 | 480 | 29979 | 30459 | 54.586 | [38 empty] | ATT-9365 | MIN001.G0000488 | [11 empty] | 583 |  | 2024 | 9 | 39 | #REF! | #N/A
ITG-148484 |  | Active |  |  | PSA | SFU/BCL | PSA-3902PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 9 | Lakeville | 313 | [7 empty] | 2024-07-16 | 2024-07-19 | 2024-07-24 | JOSH | 2024-08-15 | 2024-08-27 | 2024-08-23 | YES | 0 | 2222 | 21250 | 23472 | 74.9904 | 2024-09-19 | 2024-10-01 | [6 empty] | 2024-09-18 | 2024-10-02 | [27 empty] | Fielder found some existing competition in the southern half of the job, northern half was fielded and sent for post field layout and permit. | ATT-9366 | MIN001.G0000489 | [11 empty] | 584 |  | 2024 | 8 | 34 | #REF! | #N/A
ITG-148487 |  | Active |  |  | BBF |  | BBF-YF301-RTE3-SEC11-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 11 | Lakeville | 526 | [71 empty] | 585 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148493 |  | Active |  |  | PSA | BCL/MDU | PSA-3111PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 11 | Lakeville | 526 | 477 | [6 empty] | 2024-07-31 | 2024-08-03 | 2024-07-24 | JACOB | 2024-08-23 | 2024-09-03 | 2024-09-01 | YES | 4100 | 536 | 12588 | 13124 | 24.9506 | 2024-09-04 | 2024-09-18 | 2024-09-18 |  |  | 864 | PFP 20250 HERITAGE DR |  | 2024-09-19 | 2024-10-07 | 2024-09-27 |  |  | 2024-09-26 | 11831 | Jermaine Scott | 2024-09-25 | 2024-10-09 | [19 empty] | 18,000' assigned to Jacob Messer for fielding for existing competition check in southern portion of Burnsville Route 3. | ATT-9367 | MIN001.G0000490 | [11 empty] | 586 |  | 2024 | 9 | 36 | #REF! | #N/A
ITG-148494 |  | Active |  |  | BBF |  | BBF-YF301-RTE3-SEC12-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 12 | Lakeville | 1080 | [71 empty] | 587 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148495 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-3121PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 12 | Lakeville | 493 | [7 empty] | 2024-07-31 | 2024-08-03 | 2024-07-24 | JAEGER | 2024-08-23 | 2024-09-10 | 2024-09-10 | YES | 6800 | 247 | 16474 | 16721 | 33.9168 | 2024-09-11 | 2024-09-26 | [6 empty] | 2024-09-25 | 2024-10-11 | [28 empty] | ATT-9368 | MIN001.G0000491 | [11 empty] | 588 |  | 2024 | 9 | 37 | #REF! | #N/A
ITG-148496 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-3122PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 12 | Lakeville | 587 | [7 empty] | 2024-07-31 | 2024-08-03 | 2024-07-24 | HUNTER | 2024-08-23 | 2024-09-09 | 2024-09-09 | YES | 0 | 2489 | 15107 | 17596 | 29.9761 | 2024-09-09 | 2024-09-26 | [6 empty] | 2024-09-24 | 2024-10-11 | [28 empty] | ATT-9369 | MIN001.G0000492 | [11 empty] | 589 |  | 2024 | 9 | 37 | #REF! | #N/A
ITG-148497 |  | Active |  |  | BBF |  | BBF-YF301-RTE3-SEC13-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 13 | Lakeville | 2368 | [71 empty] | 590 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148498 |  | Active |  |  | PSA | SFU | PSA-3131PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 13 | Lakeville | 410 | [7 empty] | 2024-07-31 | 2024-08-03 | 2024-07-24 | ERIK | 2024-08-23 | 2024-09-20 | 2024-09-09 | YES | 0 | 3171 | 23074 | 26245 | 64.0122 | 2024-09-23 | 2024-10-07 | [7 empty] | 2024-10-24 | [27 empty] | Southern portion of PSA3401 being merged into this PSA | ATT-9370 | MIN001.G0000493 | [11 empty] | 591 |  | 2024 | 9 | 37 | #REF! | #N/A
ITG-148499 |  | Active |  |  | PSA | SFU | PSA-3132PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 13 | Lakeville | 369 | [7 empty] | 2024-07-31 | 2024-08-03 | 2024-07-24 | CODY | 2024-08-27 | 2024-09-12 | 2024-09-13 | YES | 93 | 2359 | 21777 | 24136 | 65.4092 | 2024-09-13 | 2024-09-27 | [7 empty] | 2024-10-18 | [27 empty] | PARTIAL COMPETITION | ATT-9371 | MIN001.G0000494 | [11 empty] | 592 |  | 2024 | 9 | 37 | #REF! | #N/A
ITG-148500 |  | Active |  |  | PSA |  | PSA-3133PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 13 | Lakeville | 385 | [7 empty] | 2024-07-31 | 2024-08-03 | 2024-07-24 | CODY | 2024-08-28 | 2024-09-19 | 2024-09-19 | YES | 0 | 598 | 22344 | 22942 | 59.5896 |  | 2024-10-08 | [7 empty] | 2024-10-28 | [28 empty] | ATT-9372 | MIN001.G0000495 | [11 empty] | 593 |  | 2024 | 9 | 38 | #REF! | #N/A
ITG-148501 |  | Active |  |  | PSA | SFU | PSA-3134PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 13 | Lakeville | 402 | [7 empty] | 2024-07-31 | 2024-08-03 | 2024-07-24 | JACOB | 2024-08-30 | 2024-09-11 | 2024-09-11 | YES | 0 | 272 | 32965 | 33237 | 82.6791 | 2024-09-12 | 2024-09-26 | [6 empty] | 2024-09-26 | 2024-10-16 | [27 empty] | PARTIAL COMPETITION | ATT-9373 | MIN001.G0000496 | [11 empty] | 594 |  | 2024 | 9 | 37 | #REF! | #N/A
ITG-148502 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3135PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 13 | Lakeville | 200 | [7 empty] | 2024-07-31 | 2024-08-03 | EX COMP | [48 empty] | ATT-9374 | MIN001.G0000497 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 595 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148503 |  | Active |  |  | PSA |  | PSA-3136PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 13 | Lakeville | 602 | [7 empty] | 2024-07-31 | 2024-08-03 | NO BUILD? | [8 empty] | 0 | 0 | [37 empty] | 8/30 job area is a trailer park with no R/W or plat map available and may be private. Sent email for further direction and possible no build. | ATT-9375 | MIN001.G0000498 | [11 empty] | 596 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148505 |  | Active |  |  | BBF |  | BBF-YF301-RTE3-SEC14-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 14 | Lakeville | 2093 | [71 empty] | 597 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148507 |  | Active |  |  | PSA |  | PSA-3141PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 14 | Lakeville | 576 | [7 empty] | 2024-07-31 | 2024-08-03 | 2024-08-19 | JOSH | 2024-09-05 | 2024-10-04 | [5 empty] | 0 | 0 | [38 empty] | ATT-9376 | MIN001.G0000499 | [11 empty] | 598 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148508 |  | Active |  |  | PSA |  | PSA-3142PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 14 | Lakeville | 641 | [7 empty] | 2024-07-31 | 2024-08-03 | 2024-08-22 | JAEGER | 2024-08-30 | 2024-09-16 | 2024-09-17 | YES | 3044 | 372 | 50081 | 50453 | 78.7098 | 2024-09-20 | 2024-10-02 | [7 empty] | 2024-10-23 | [27 empty] | Portions of PSA3151 and 3153 merged into this PSA | ATT-9377 | MIN001.G0000500 | [11 empty] | 599 |  | 2024 | 9 | 38 | #REF! | #N/A
ITG-148509 |  | Active |  |  | PSA |  | PSA-3143PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 14 | Lakeville | 632 | [7 empty] | 2024-07-31 | 2024-08-03 | 2024-08-22 | CODY | 2024-09-05 | 2024-09-25 | [5 empty] | 0 | 0 | [37 empty] | PSA3144 merged into this PSA | ATT-9378 | MIN001.G0000501 | [11 empty] | 600 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148510 |  | Project Cancel |  |  | PSA |  | PSA-3144PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 14 | Lakeville | [8 empty] | 2024-07-31 | 2024-08-03 | EX COMP | [47 empty] | looking to combine this PSA with PSA-3143 and cancel this job. | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build | No Build |  | 601 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148511 |  | Active |  |  | PSA |  | PSA-3145PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 14 | Lakeville | 222 | [7 empty] | 2024-07-31 | 2024-08-03 | PARTIAL COMP | [8 empty] | 0 | 0 | [37 empty] | To get to this area there is a HWY underpass crossing and a large area of the PSA has existing competition, sent email on 8/15 for more direction. Likely a no build, minimal LUs, sent to Don 9/3. | ATT-9379 | MIN001.G0000502 | [11 empty] | 602 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148512 |  | Active |  |  | PSA |  | PSA-3146PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 14 | Lakeville | 22 | [7 empty] | 2024-07-31 | 2024-08-03 | NO BUILD? | [8 empty] | 0 | 0 | [37 empty] | To get to this area there is a HWY underpass crossing and a large area of the PSA has existing competition, sent email on 8/15 for more direction. Likely a no build, waiting on response back 9/5. | ATT-9380 | MIN001.G0000503 | [11 empty] | 603 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148513 |  | NO BUILD |  |  | BBF |  | BBF-YF301-RTE3-SEC15-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 15 | Lakeville | 987 | [64 empty] | Stop | Stop | Stop | Stop | Stop | Stop |  | 604 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148514 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3151PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 15 | Lakeville | 599 | [7 empty] | 2024-07-31 | 2024-08-03 | EX COMP | [47 empty] | Large area of the PSA has existing competition, looking take out school area and combine with PSA-3142 and can no build PSA-3151 for existing comp. | ATT-9382 | MIN001.G0000504 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 605 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148516 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3152PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 15 | Lakeville | 372 | [7 empty] | 2024-07-31 | 2024-08-03 | EX COMP | [48 empty] | ATT-9383 | MIN001.G0000505 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 606 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-148517 |  | No Build - Ex Comp |  |  | PSA |  | PSA-3153PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #3 | BBF RTE 3 SEC 15 | Lakeville | 16 | [7 empty] | 2024-07-31 | 2024-08-03 | EX COMP | [47 empty] | Large area of the PSA has existing competition, looking take out school area and combine with PSA-3142 and can no build PSA-3153 for existing comp. | ATT-9384 | MIN001.G0000506 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 607 |  | 1900 | 1 | 0 | #REF! | #N/A
ITG-158156 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC1-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 1 | Burnsville | 2882 | [71 empty] | 608
ITG-158149 |  | Active |  |  | PSA | SFU | PSA-4101PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 1 | Burnsville | 399 | [7 empty] | 2024-08-29 | 2024-09-02 | 2024-09-12 | JACOB | 2024-09-18 | 2024-09-25 | [5 empty] | 0 | 0 | [38 empty] | ATT-9385 | MIN001.G0000507 | [11 empty] | 609
ITG-158150 |  | No Build - Ex Comp |  |  | PSA |  | PSA-4102PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 1 | Burnsville | 291 | [7 empty] | 2024-08-29 | 2024-09-02 | EX COMP | [8 empty] | 0 | 0 | [37 empty] | Fielder found existing competition throughout the whole PSA area, need to no build 9/9. | ATT-9432 | MIN001.G0000553 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 610
ITG-158151 |  | NO BUILD |  |  | PSA |  | PSA-4103PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 1 | Burnsville | 417 | [58 empty] | ATT-9433 | MIN001.G0000554 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 611
ITG-158152 |  | Active |  |  | PSA | SFU/MDU | PSA-4104PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 1 | Burnsville | 297 | [7 empty] | 2024-08-29 | 2024-09-02 | 2024-09-05 | HUNTER | 2024-09-05 | 2024-09-12 | 2024-09-11 | YES | 0 | 1616 | 7110 | 8726 | 29.3805 | 2024-09-09 | 2024-09-26 | [6 empty] | 2024-09-26 | 2024-10-16 | [28 empty] | ATT-9386 | MIN001.G0000508 | [11 empty] | 612
ITG-158153 |  | No Build - Ex Comp |  |  | PSA |  | PSA-4105PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 1 | Burnsville | 625 | [7 empty] | 2024-08-29 | 2024-09-02 | EX COMP | [8 empty] | 0 | 0 | [37 empty] | Fielder found existing competition throughout the whole PSA area, need to no build 9/5. | ATT-9434 | MIN001.G0000555 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 613
ITG-158154 |  | Active |  |  | PSA | MDU/BCL | PSA-4106PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 1 | Burnsville | 599 | [7 empty] | 2024-08-29 | 2024-09-02 | 2024-09-12 | SAM | 2024-09-26 | 2024-10-03 | [5 empty] | 0 | 0 | [38 empty] | ATT-9435 | MIN001.G0000556 | [11 empty] | 614
ITG-158155 |  | No Build - Ex Comp |  |  | PSA |  | PSA-4107PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 1 | Burnsville | 254 | [7 empty] | 2024-08-29 | 2024-09-02 | EX COMP | [8 empty] | 0 | 0 | [37 empty] | Fielder found existing competition throughout the whole PSA area, need to no build 9/5. | ATT-9436 | MIN001.G0000557 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 615
ITG-158158 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC2-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 2 | Burnsville | 2115 | [71 empty] | 616
ITG-158159 |  | Active |  |  | PSA | SFU/MDU/BCL | PSA-4201PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 2 | Burnsville | 542 | [7 empty] | 2024-08-29 | 2024-09-02 | 2024-09-05 | JACOB | 2024-09-09 | 2024-09-17 | 2024-09-16 | YES | 2852 | 10 | 16343 | 16353 | 30.1716 | 2024-09-18 | 2024-09-30 | [7 empty] | 2024-10-18 | [28 empty] | ATT-9437 | MIN001.G0000558 | [11 empty] | 617
ITG-158160 |  | Active |  |  | PSA | MDU/BCL | PSA-4202PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 2 | Burnsville | 394 | [7 empty] | 2024-08-29 | 2024-09-02 | 2024-09-04 | HANNAH | 2024-09-19 | 2024-09-26 |  |  |  | 10 | 7712 | 7722 | 19.599 | [38 empty] | ATT-9438 | MIN001.G0000559 | [11 empty] | 618
ITG-158161 |  | Active |  |  | PSA | MDU/BCL | PSA-4203PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 2 | Burnsville | 337 | [7 empty] | 2024-08-29 | 2024-09-02 | 2024-09-05 | JAEGER | 2024-09-12 | 2024-09-19 | 2024-09-18 | YES | 0 | 1754 | 5077 | 6831 | 20.27 | 2024-09-19 | 2024-10-02 | [7 empty] | 2024-10-23 | [27 empty] | Job area is a private MDU | ATT-9439 | MIN001.G0000560 | [11 empty] | 619
ITG-158162 |  | NO BUILD |  |  | PSA |  | PSA-4204PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 2 | Burnsville | 73 | [58 empty] | ATT-9387 | MIN001.G0000509 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 620
ITG-158173 |  | NO BUILD |  |  | PSA |  | PSA-4205PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 2 | Burnsville | 359 | [58 empty] | ATT-9440 | MIN001.G0000561 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 621
ITG-160793 |  | NO BUILD |  |  | PSA |  | PSA-4206PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 2 | Burnsville | 410 | [58 empty] | ATT-9441 | MIN001.G0000562 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 622
ITG-158170 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC3-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 3 | Burnsville | 2725 | [71 empty] | 623
ITG-158169 |  | Active |  |  | PSA | MDU/BCL | PSA-4301PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 3 | Burnsville | 443 | [7 empty] | 2024-08-29 | 2024-09-02 | 2024-09-05 | CODY | 2024-09-19 | 2024-09-25 | [5 empty] | 0 | 0 | [38 empty] | ATT-9442 | MIN001.G0000563 | [11 empty] | 624
ITG-158175 |  | Active |  |  | PSA | MDU/BCL | PSA-4302PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 3 | Burnsville | 414 | [7 empty] | 2024-08-29 | 2024-09-02 | 2024-09-05 | ERIK | 2024-09-24 | 2024-10-01 | [5 empty] | 0 | 0 | [38 empty] | ATT-9443 | MIN001.G0000564 | [11 empty] | 625
ITG-158178 |  | Active |  |  | PSA | SFU/MDU/BCL | PSA-4303PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 3 | Burnsville | 504 | [7 empty] | 2024-08-29 | 2024-09-02 | 2024-09-04 | HUNTER | 2024-09-09 | 2024-09-20 | 2024-09-19 | YES | 5008 | 113 | 28520 | 28633 | 56.8115 |  | 2024-10-08 | [7 empty] | 2024-10-28 | [28 empty] | ATT-9388 | MIN001.G0000510 | [11 empty] | 626
ITG-158180 |  | Active |  |  | PSA | SFU | PSA-4304PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 3 | Burnsville | 370 | [7 empty] | 2024-08-29 | 2024-09-02 | 2024-09-04 | JAEGER | 2024-09-09 | 2024-09-23 | [5 empty] | 0 | 0 | [38 empty] | ATT-9389 | MIN001.G0000511 | [11 empty] | 627
ITG-158183 |  | Active |  |  | PSA | SFU | PSA-4305PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 3 | Burnsville | 343 | [7 empty] | 2024-08-29 | 2024-09-02 | 2024-09-12 | HUNTER | 2024-09-17 | 2024-09-27 | [5 empty] | 0 | 0 | [38 empty] | ATT-9390 | MIN001.G0000512 | [11 empty] | 628
ITG-158188 |  | Active |  |  | PSA | SFU/MDU/BCL | PSA-4306PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 3 | Burnsville | 651 | [7 empty] | 2024-08-29 | 2024-09-02 | 2024-09-05 | JAEGER | 2024-09-24 | 2024-10-01 | [5 empty] | 0 | 0 | [38 empty] | ATT-9391 | MIN001.G0000513 | [11 empty] | 629
ITG-158193 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC4-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 4 | Burnsville | 1908 | [71 empty] | 630
ITG-159244 |  | Active |  |  | PSA | SFU | PSA-4401PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 4 | Burnsville | 492 | [7 empty] | 2024-09-02 | 2024-09-02 | 2024-09-05 | SAM | 2024-09-11 | 2024-09-26 | [5 empty] | 0 | 0 | [38 empty] | ATT-9392 | MIN001.G0000514 | [11 empty] | 631
ITG-159245 |  | Active |  |  | PSA | SFU | PSA-4402PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 4 | Burnsville | 565 | [7 empty] | 2024-09-02 | 2024-09-02 | 2024-09-05 | HANNAH | 2024-09-25 | 2024-10-04 | [5 empty] | 0 | 0 | [38 empty] | ATT-9393 | MIN001.G0000515 | [11 empty] | 632
ITG-159251 |  | Active |  |  | PSA | SFU | PSA-4403PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 4 | Burnsville | 228 | [7 empty] | 2024-09-02 | 2024-09-02 | 2024-09-05 | ERIK | 2024-09-20 | 2024-09-30 | 2024-09-22 | YES | 0 | 1147 | 17808 | 18955 | 83.136 |  | 2024-10-08 | [7 empty] | 2024-10-28 | [28 empty] | ATT-9395 | MIN001.G0000516 | [11 empty] | 633
ITG-159252 |  | Active |  |  | PSA | SFU/MDU/BCL | PSA-4404PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 4 | Burnsville | 623 | [7 empty] | 2024-09-02 | 2024-09-02 | 2024-09-05 | JACOB | 2024-09-11 | 2024-09-18 | 2024-09-16 | YES | 0 | 2682 | 30872 | 33554 | 53.8587 | 2024-09-19 | 2024-10-02 | [7 empty] | 2024-10-23 | [28 empty] | ATT-9396 | MIN001.G0000517 | [11 empty] | 634
ITG-159253 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC5-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 5 | Burnsville | 4137 | [71 empty] | 635
ITG-159254 |  | Active |  |  | PSA | BCL/MDU | PSA-4501PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 5 | Burnsville | 549 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9397 | MIN001.G0000518 | [11 empty] | 636
ITG-159256 |  | Active |  |  | PSA | BCL/MDU | PSA-4502PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 5 | Burnsville | 480 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9398 | MIN001.G0000519 | [11 empty] | 637
ITG-159257 |  | Active |  |  | PSA | BCL/MDU | PSA-4503PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 5 | Burnsville | 645 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9399 | MIN001.G0000520 | [11 empty] | 638
ITG-159259 |  | Active |  |  | PSA | BCL/MDU | PSA-4504PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 5 | Burnsville | 334 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9400 | MIN001.G0000521 | [11 empty] | 639
ITG-159260 |  | Active |  |  | PSA | SFU/BCL/MDU | PSA-4505PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 5 | Burnsville | 451 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9401 | MIN001.G0000522 | [11 empty] | 640
ITG-159261 |  | Active |  |  | PSA | BCL/MDU | PSA-4506PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 5 | Burnsville | 548 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9402 | MIN001.G0000523 | [11 empty] | 641
ITG-159262 |  | Active |  |  | PSA | SFU/MDU/BCL | PSA-4507PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 5 | Burnsville | 466 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9403 | MIN001.G0000524 | [11 empty] | 642
ITG-159263 |  | Active |  |  | PSA | SFU/MDU | PSA-4508PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 5 | Burnsville | 246 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9404 | MIN001.G0000525 | [11 empty] | 643
ITG-159264 |  | Active |  |  | PSA | BCL | PSA-4509PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 5 | Burnsville | 418 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9405 | MIN001.G0000526 | [11 empty] | 644
ITG-159265 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC6-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 6 | Burnsville | 1975 | [71 empty] | 645
ITG-159266 |  | Active |  |  | PSA | MDU/SFU | PSA-4601PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 6 | Burnsville | 520 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9406 | MIN001.G0000527 | [11 empty] | 646
ITG-159267 |  | Active |  |  | PSA | MDU/BCL | PSA-4602PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 6 | Burnsville | 527 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9407 | MIN001.G0000528 | [11 empty] | 647
ITG-159269 |  | Active |  |  | PSA | MDU/BCL | PSA-4603PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 6 | Burnsville | 538 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9408 | MIN001.G0000529 | [11 empty] | 648
ITG-159272 |  | Active |  |  | PSA | MDU/SFU | PSA-4604PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 6 | Burnsville | 390 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9409 | MIN001.G0000530 | [11 empty] | 649
ITG-159273 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC7-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 7 | Burnsville | 2530 | [71 empty] | 650
ITG-159275 |  | Active |  |  | PSA | SFU | PSA-4701PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 7 | Burnsville | 386 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9410 | MIN001.G0000531 | [11 empty] | 651
ITG-159276 |  | Active |  |  | PSA | SFU/MDU/BCL | PSA-4702PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 7 | Burnsville | 599 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9411 | MIN001.G0000532 | [11 empty] | 652
ITG-159277 |  | Active |  |  | PSA | SFU/MDU/BCL | PSA-4703PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 7 | Burnsville | 519 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9412 | MIN001.G0000533 | [11 empty] | 653
ITG-159280 | 2 | Active |  |  | PSA | SFU/MDU | PSA-4704PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 7 | Burnsville | 564 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | 2024-09-26 |  | 2024-04-18 | DREW | 2024-04-18 | 2024-05-06 | 2024-05-06 | YES | 15324 | 2 | 16698 | 16700 | 29.6099 | 2024-09-04 | 2024-10-07 | [7 empty] | 2024-10-04 | [5 empty] | Jordan Struck | 2024-05-31 | 2024-06-07 | 2024-06-05 | 2024-09-04 | [17 empty] | 8/15 Pending Major MNDOT Reroute decision 9/25 LAYOUT ASSIGNED, MAJOR CHANGES, ECD 10/7 | ATT-9417 | MIN001.G0000538 | NA | NA | NA | NA | [6 empty] | New GP Project number needed - Previously Eagan 1805 and 1806 | 654
ITG-159281 | 2 | Active |  |  | PSA | SFU/BCL | PSA-4705PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 7 | Burnsville | 462 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | 2024-09-26 |  | 2024-04-18 | SAM | 2024-04-18 | 2024-04-25 | 2024-04-25 |  |  |  |  | 0 | 0 | 2024-06-11 | 2024-06-26 | 2024-06-26 | 2024-09-04 |  | 576 | PFP 2223 JAMES ST | 2024-06-27 | 2024-06-28 | 2024-07-19 | 2024-07-11 | 2024-09-04 |  | 2024-07-11 | 29027 | James Lugo | 2024-06-28 | 2024-07-09 | 2024-07-03 | 2024-09-04 | 2024-09-10 | [16 empty] | 9/4/24 Job was previously Eagan PSA1807. 6/27/2024 sent redline layout to CAD, needs BBF updates , COMMERCIAL | ATT-9418 | MIN001.G0000539 | NA | NA | NA | NA | [6 empty] | New GP Project number needed - Previously Eagan 1807 | 655
ITG-159282 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC8-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 8 | Burnsville | 2368 | [71 empty] | 656
ITG-159283 |  | Active |  |  | PSA | MDU/BCL | PSA-4801PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 8 | Burnsville | 613 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9413 | MIN001.G0000534 | [11 empty] | 657
ITG-159284 |  | Active |  |  | PSA | SFU | PSA-4802PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 8 | Burnsville | 567 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9414 | MIN001.G0000535 | [11 empty] | 658
ITG-159285 |  | Active |  |  | PSA | SFU | PSA-4803PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 8 | Burnsville | 615 | [7 empty] | 2024-09-26 | [10 empty] | 0 | 0 | [38 empty] | ATT-9415 | MIN001.G0000536 | [11 empty] | 659
ITG-159384 | 3 | Active |  |  | PSA | BCL/MDU/PR | PSA-4804PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 8 | Burnsville | 572 |  |  | Carla Jeffers |  | 2024-01-04 | Cheryl Turk | 2024-01-19 | 2024-09-26 |  | 2024-07-22 | HUNTER | 2024-07-25 | 2024-08-05 | 2024-08-05 | YES | 0 | 1379 | 6112 | 7491 | 13.0962 | 2024-08-07 | 2024-09-27 | [6 empty] | 2024-09-18 | 2024-10-11 | [27 empty] | 9/3 was previously Eagan 1802, now Burnsville 6/27 PSA1803 and PSA1804 combined into this. 5/10 Moved back to active 4/29 Hold for BCL/MDU direction. COMMERCIAL | ATT-9419 | MIN001.G0000540 | NA | NA | NA | NA | [6 empty] | Budget sheet shows 14 LU, Tracker shows 445. New GP Project number needed - Previously Eagan PSA1802 | 660 | 1 | 2024 | 8 | 32 | #REF! | #N/A
ITG-159287 |  | NO BUILD |  |  | PSA |  | PSA-4805PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 8 | Burnsville | 1 | [58 empty] | ATT-9416 | MIN001.G0000537 |  |  |  |  | Stop | Stop | Stop | Stop | Stop | Stop |  | 661
ITG-163532 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC9-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 9 | Burnsville | 3656 | [71 empty] | 662
ITG-163533 |  | Active |  |  | PSA | SFU | PSA-4901PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 9 | Burnsville | 441 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 663
ITG-163534 |  | Active |  |  | PSA | SFU/MDU | PSA-4902PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 9 | Burnsville | 543 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 664
ITG-163535 |  | Active |  |  | PSA | BCL | PSA-4903PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 9 | Burnsville | 398 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 665
ITG-163536 |  | Active |  |  | PSA | MDU | PSA-4904PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 9 | Burnsville | 285 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 666
ITG-163537 |  | Active |  |  | PSA | MDU | PSA-4905PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 9 | Burnsville | 391 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 667
ITG-163538 |  | Active |  |  | PSA | MDU | PSA-4906PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 9 | Burnsville | 387 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 668
ITG-163539 |  | Active |  |  | PSA | SFU | PSA-4907PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 9 | Burnsville | 473 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 669
ITG-163540 |  | Active |  |  | PSA | SFU/MDU | PSA-4908PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 9 | Burnsville | 319 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 670
ITG-163541 |  | Active |  |  | PSA | MDU/BCL | PSA-4909PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 9 | Burnsville | 419 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 671
ITG-163542 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC11-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 11 | Burnsville | 69065 | [71 empty] | 672
ITG-163543 |  | Active |  |  | PSA | MDU | PSA-4111PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 11 | Burnsville | 532 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 673
ITG-163544 |  | Active |  |  | PSA | MDU/BCL | PSA-4112PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 11 | Burnsville | 306 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 674
ITG-163545 |  | Active |  |  | PSA | SFU/MDU/BCL | PSA-4113PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 11 | Burnsville | 460 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 675
ITG-163546 |  | Active |  |  | PSA | SFU/MDU | PSA-4114PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 11 | Burnsville | 344 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 676
ITG-163547 |  | Active |  |  | PSA | SFU/MDU | PSA-4115PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 11 | Burnsville | 553 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 677
ITG-163548 |  | Active |  |  | PSA | SFU | PSA-4116PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 11 | Burnsville | 261 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 678
ITG-163550 |  | Active |  |  | PSA | SFU/MDU | PSA-4117PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 11 | Burnsville | 530 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 679
ITG-163551 |  | Active |  |  | PSA | SFU/MDU | PSA-4118PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 11 | Burnsville | 450 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 680
ITG-163552 |  | Active |  |  | PSA | SFU | PSA-4119PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 11 | Burnsville | 551 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 681
ITG-163553 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC12-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 12 | Burnsville | 32539 | [71 empty] | 682
ITG-163554 |  | Active |  |  | PSA | MDU | PSA-4121PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 12 | Burnsville | 532 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 683
ITG-163556 |  | Active |  |  | PSA | MDU/BCL | PSA-4122PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 12 | Burnsville | 306 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 684
ITG-163557 |  | Active |  |  | PSA | SFU/MDU/BCL | PSA-4123PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 12 | Burnsville | 460 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 685
ITG-163558 |  | Active |  |  | PSA | SFU/MDU | PSA-4124PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 12 | Burnsville | 344 |  |  | Aubre Thompson | 1 X 32 | [67 empty] | 686
ITG-163559 |  | Active |  |  | PSA | SFU/MDU | PSA-4125PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 12 | Burnsville | 553 |  |  | Aubre Thompson | 1 X 32 | [67 empty] | 687
ITG-163560 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC13-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 13 | Burnsville | 15172 | [71 empty] | 688
ITG-163561 |  | Active |  |  | PSA | MDU | PSA-4131PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 13 | Burnsville | 532 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 689
ITG-163562 |  | Active |  |  | PSA | MDU/BCL | PSA-4132PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 13 | Burnsville | 306 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 690
ITG-163563 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC14-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 14 | Burnsville | 7167 | [71 empty] | 691
ITG-163564 |  | Active |  |  | PSA | MDU | PSA-4141PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 14 | Burnsville | 318 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 692
ITG-163565 |  | Active |  |  | PSA | MDU/BCL | PSA-4142PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 14 | Burnsville | 418 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 693
ITG-163566 |  | Active |  |  | PSA | SFU/MDU/BCL | PSA-4143PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 14 | Burnsville | 620 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 694
ITG-163567 |  | Active |  |  | PSA | SFU/MDU | PSA-4144PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 14 | Burnsville | 258 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 695
ITG-163568 |  | Active |  |  | PSA | SFU/MDU | PSA-4145PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 14 | Burnsville | 456 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 696
ITG-163569 |  | Active |  |  | PSA | SFU/MDU | PSA-4146PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 14 | Burnsville | 361 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 697
ITG-163570 |  | Active |  |  | BBF |  | BBF-YF401-RTE4-SEC15-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 15 | Burnsville | 2368 | [71 empty] | 698
ITG-163571 |  | Active |  |  | PSA | MDU | PSA-4151PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 15 | Burnsville | 551 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 699
ITG-163572 |  | Active |  |  | PSA | MDU/BCL | PSA-4152PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 16 | Burnsville | 575 |  |  | Aubre Thompson | 1 X 64 | [67 empty] | 700
ITG-163573 |  | Active |  |  | PSA | SFU/MDU/BCL | PSA-4153PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 17 | Burnsville | 636 |  |  | Aubre Thompson | 1 X 32 | [67 empty] | 701
ITG-163574 |  | Active |  |  | PSA | SFU/MDU | PSA-4154PA-BRVLMNYF-CHARLIE | BRVLMNYF | RTE #4 | BBF RTE 4 SEC 18 | Burnsville | 606 |  |  | Aubre Thompson | 1 X 32 | [67 empty] | 702
ITG-158203 |  | Active |  |  |  |  | Chaska Open Trench | CHASKA |  |  | Burnsville | [45 empty] | 2024-08-28 | [26 empty] | 703
Formulas:
Fld Cmp Wk = WEEKNUM([FIELDING COMPLETE])

## CAD Pivot Tables
GIGAPOWER CAD PIVOT TABLES (Update Filters each Week, Refresh All Pivot Tables when Viewing)
New CAD Complete Last Week | Count 13 | CAD Revisions Complete Last Week | Count 9 | New CAD in Progress | Count 23 | CAD Revisions in Progress | Count 9 |  | Sent to Permitting in Last Week |  | Count 13 | CAD Complete, Not Yet Sent to Permitting |  | Count 107
PROJECT STATUS | (Multiple Items) | PROJECT STATUS | (Multiple Items) | PROJECT STATUS | (Multiple Items) |  |  |  | PROJECT STATUS | (Multiple Items)
PROJECT TYPE | (All) | PROJECT TYPE | (All) | PROJECT TYPE | (All) | PROJECT STATUS | (Multiple Items) |  | PROJECT TYPE | (All)
CAD PERMIT ASSIGNED | (All) | CAD PERMIT ASSIGNED | (All) | CAD PERMIT ASSIGNED | (Multiple Items) | PROJECT TYPE | (All) |  | CAD PERMIT ASSIGNED | (All) |  | PROJECT STATUS | (Multiple Items)
CAD DD (FACTOR 80 HRS) | (All) | CAD DD (FACTOR 80 HRS) | (All) | CAD COMPLETE | (blank) | CAD PERMIT ASSIGNED | (All) |  | CAD DD (FACTOR 80 HRS) | (All) |  | PROJECT TYPE | (All)
CAD COMPLETE | (Multiple Items) | CAD COMPLETE | (All) | CAD REVISION REQUESTED | (All) | CAD DD (FACTOR 80 HRS) | (All) |  | CAD COMPLETE | (All) |  | CAD PERMIT ASSIGNED | (All)
CAD REVISION REQUESTED | (All) | CAD REVISION REQUESTED | (All) | CAD REVISION COMPLETE | (All) | CAD COMPLETE | (All) |  | CAD REVISION REQUESTED | (All) |  | CAD DD (FACTOR 80 HRS) | (All)
CAD REVISION COMPLETE | (All) | CAD REVISION COMPLETE | (Multiple Items) | [5 empty] | CAD REVISION COMPLETE | (All) |  | FINAL CAD REVIEW COMPLETE & SENT TO PERMITTING | (blank)
|  |  |  | NAME | CAD DD | NAME | CAD REVISION REQUESTED | CAD REVISION COMPLETE
NAME | Sum of PATH FOOTAGE | NAME | Sum of PATH FOOTAGE | BBF-82101-RT1-SEC5-EAGNMN82-CHARLIE | 2024-10-04 | BBF-AT301-RT3-SEC14-BLTNMNAT-CHARLIE | 2024-09-13 | (blank) | NAME | PATH FOOTAGE | FINAL CAD REVIEW COMPLETE & SENT TO PERMITTING | NAME | CAD COMPLETE | CAD REVISION REQUESTED | CAD REVISION COMPLETE | PATH FOOTAGE
BBF-AT401-RT4-SEC2-BLTNMNAT-CHARLIE | 5608 | BBF-YF201-RTE2-SEC1-BRVLMNYF-CHARLIE |  | BBF-82101-RT1-SEC6-EAGNMN82-CHARLIE | 2024-09-27 | BBF-AT401-RT4-SEC3-BLTNMNAT-CHARLIE | 2024-09-18 | (blank) | BBF-82201-RT2-SEC7-EAGNMN82-CHARLIE |  |  | BBF-82101-RT1-SEC1-EAGNMN82-CHARLIE | 2024-05-31 | 2024-07-15 | 2024-07-17 | 16225
BBF-PI201-RT2-SEC3-EDPRMNPI-CHARLIE |  | PSA-1305PA-EDPRMNPI-CHARLIE | 18567 | BBF-AT301-RT3-SEC14-BLTNMNAT-CHARLIE | 2024-09-20 | BBF-PI101-RT1-SEC2-EDPRMNPI-CHARLIE | 2024-08-27 | (blank) |  | 9853 |  | BBF-82101-RT1-SEC4-EAGNMN82-CHARLIE | 2024-08-26 | 2024-09-11 | ECD 9/30 | 12154
PSA-1307PA-BLTNMNAT-CHARLIE | 0 | PSA-2201PA-BLTNMNAT-CHARLIE | 21589 | BBF-AT401-RT4-SEC11-BLTNMNAT-CHARLIE | 2024-09-20 | PSA-2312PA-EAGNMN82-CHARLIE | 2024-09-12 | (blank) |  |  | 2024-09-18 | BBF-AT101-RT1-SEC1-BLTNMNAT-CHARLIE | 2024-02-14 | 2024-07-17 | 2024-07-18 | 6869
PSA-1308PA-BLTNMNAT-CHARLIE | 0 | PSA-2204PA-BLTNMNAT-CHARLIE | 40275 | BBF-AT401-RT4-SEC4-BLTNMNAT-CHARLIE | 2024-09-23 | PSA-2603PA-EAGNMN82-CHARLIE | 2024-09-11 | (blank) | BBF-82201-RT2-SEC8-EAGNMN82-CHARLIE |  |  | BBF-AT301-RT3-SEC12-BLTNMNAT-CHARLIE | 2024-08-14 | (blank) | (blank) | 1938
PSA-1507PA-EAGNMN82-CHARLIE | 6168 | PSA-2301PA-EAGNMN82-CHARLIE | 39547 | BBF-AT401-RT4-SEC5-BLTNMNAT-CHARLIE | 2024-09-27 | PSA-3144PA-BLTNMNAT-CHARLIE | 2024-09-04 | Pend Layout |  | 6783 |  | BBF-AT301-RT3-SEC15-BLTNMNAT-CHARLIE | 2024-08-15 | (blank) | (blank) | 2242
PSA-1508PA-EAGNMN82-CHARLIE | 5 | PSA-2302PA-EAGNMN82-CHARLIE | 22347 | BBF-PI101-RT1-SEC3-EDPRMNPI-CHARLIE | 2024-10-04 | PSA-3145PA-BLTNMNAT-CHARLIE | 2024-09-04 | Pend Layout |  |  | 2024-09-16 | BBF-AT301-RT3-SEC16-BLTNMNAT-CHARLIE | 2024-08-14 | (blank) | (blank) | 3940
PSA-2401PA-EDPRMNPI-CHARLIE | 25471 | PSA-2701PA-EAGNMN82-CHARLIE | 31084 | BBF-PI201-RT2-SEC11-EDPRMNPI-CHARLIE | 2024-10-24 | PSA-3192PA-BLTNMNAT-CHARLIE | 2024-09-18 | (blank) | BBF-82201-RT2-SEC9-EAGNMN82-CHARLIE |  |  | BBF-AT301-RT3-SEC17-BLTNMNAT-CHARLIE | 2024-08-21 | (blank) | (blank) | 2759
PSA-2402PA-EDPRMNPI-CHARLIE | 37019 | PSA-2803PA-EAGNMN82-CHARLIE | 12618 | BBF-PI201-RT2-SEC2-EDPRMNPI-CHARLIE | 2024-10-10 | PSA-4705PA-BRVLMNYF-CHARLIE | 2024-09-04 | (blank) |  | 5578 |  | BBF-AT301-RT3-SEC19-BLTNMNAT-CHARLIE | 2024-08-23 | (blank) | (blank) | 1628
PSA-2601PA-EDPRMNPI-CHARLIE | 6228 | PSA-3162PA-BLTNMNAT-CHARLIE | 23752 | BBF-PI201-RT2-SEC9-EDPRMNPI-CHARLIE | 2024-10-24 | [5 empty] | 2024-09-17 | BBF-AT301-RT3-SEC2-BLTNMNAT-CHARLIE | 2024-08-15 | (blank) | (blank) | 3733
PSA-2706PA-BRVLMNYF-CHARLIE | 42047 | Grand Total | 209779 | BBF-PI301-RT3-SEC1-EDPRMNPI-CHARLIE | 2024-10-04 |  |  |  | BBF-AT301-RT3-SEC13-BLTNMNAT-CHARLIE |  |  | BBF-AT301-RT3-SEC4-BLTNMNAT-CHARLIE | 2024-04-10 | 2024-07-30 | 2024-08-12 | 5542
PSA-3161PA-BLTNMNAT-CHARLIE | 6111 |  |  | PSA-1503PA-EAGNMN82-CHARLIE | 2024-09-27 |  |  |  |  | 2242 |  | BBF-AT301-RT3-SEC5-BLTNMNAT-CHARLIE | 2024-08-16 | (blank) | (blank) | 5771
PSA-3808PA-EDPRMNPI-CHARLIE | 43102 |  |  | PSA-2122PA-BRVLMNYF-CHARLIE | 2024-09-27 | [5 empty] | 2024-09-17 | BBF-AT401-RT4-SEC3-BLTNMNAT-CHARLIE | 2024-08-30 | 2024-09-18 | (blank) | 2228
PSA-4301PA-BLTNMNAT-CHARLIE | 9087 |  |  | PSA-2403PA-EDPRMNPI-CHARLIE | 2024-09-27 |  |  |  | BBF-AT301-RT3-SEC1-BLTNMNAT-CHARLIE |  |  | BBF-AT401-RT4-SEC7-BLTNMNAT-CHARLIE | 2024-09-06 | (blank) | (blank) | (blank)
Grand Total | 180846 |  |  | PSA-2601PA-BRVLMNYF-CHARLIE | 2024-10-04 |  |  |  |  | 12227 |  | BBF-AT401-RT4-SEC9-BLTNMNAT-CHARLIE | 2024-09-09 | (blank) | (blank) | (blank)
|  |  |  | PSA-2707PA-BRVLMNYF-CHARLIE | 2024-10-02 | [5 empty] | 2024-09-16 | BBF-PI101-RT1-SEC2-EDPRMNPI-CHARLIE | 2024-08-05 | 2024-08-27 | (blank) | (blank)
|  |  |  | PSA-2801PA-BRVLMNYF-CHARLIE | 2024-09-27 |  |  |  | BBF-AT401-RT4-SEC8-BLTNMNAT-CHARLIE |  |  | BBF-PI101-RT1-SEC4-EDPRMNPI-CHARLIE | 2024-08-06 | (blank) | (blank) | (blank)
|  |  |  | PSA-2802PA-BRVLMNYF-CHARLIE | 2024-09-27 |  |  |  |  | (blank) |  | BBF-PI101-RT1-SEC9-EDPRMNPI-CHARLIE | 2024-08-14 | (blank) | (blank) | (blank)
|  |  |  | PSA-2803PA-BRVLMNYF-CHARLIE | 2024-10-04 | [5 empty] | 2024-09-17 | BBF-PI201-RT2-SEC1-EDPRMNPI-CHARLIE | 2024-09-09 | (blank) | (blank) | (blank)
|  |  |  | PSA-3109PA-EDPRMNPI-CHARLIE | 2024-10-10 |  |  |  | BBF-PI101-RT1-SEC11-EDPRMNPI-CHARLIE |  |  | BBF-PI201-RT2-SEC4-EDPRMNPI-CHARLIE | 2024-09-09 | (blank) | (blank) | (blank)
|  |  |  | PSA-3702PA-EDPRMNPI-CHARLIE | 2024-10-04 |  |  |  |  | (blank) |  | BBF-PI201-RT2-SEC5-EDPRMNPI-CHARLIE | 2024-09-04 | (blank) | (blank) | 4070
|  |  |  | PSA-3801PA-EDPRMNPI-CHARLIE | 2024-09-20 | [5 empty] | 2024-09-19 | BBF-PI301-RT3-SEC2-EDPRMNPI-CHARLIE | 2024-09-04 | (blank) | (blank) | (blank)
|  |  |  | PSA-3805PA-EDPRMNPI-CHARLIE | 2024-10-04 |  |  |  | BBF-PI101-RT1-SEC1-EDPRMNPI-CHARLIE |  |  | BBF-PI301-RT3-SEC3-EDPRMNPI-CHARLIE | 2024-09-05 | (blank) | (blank) | (blank)
[10 empty] | (blank) |  | BBF-PI301-RT3-SEC4-EDPRMNPI-CHARLIE | 2024-09-06 | (blank) | (blank) | (blank)
[11 empty] | 2024-09-19 | BBF-PI301-RT3-SEC6-EDPRMNPI-CHARLIE | 2024-09-05 | (blank) | (blank) | (blank)
[9 empty] | BBF-YF201-RTE2-SEC1-BRVLMNYF-CHARLIE |  |  | PSA-1101PA-EAGNMN82-CHARLIE | 2024-09-10 | (blank) | (blank) | 802
[10 empty] | (blank) |  | PSA-1106PA-EAGNMN82-CHARLIE | 2024-08-06 | (blank) | (blank) | 43841
[11 empty] | 2024-09-16 | PSA-1201PA-EAGNMN82-CHARLIE | 2024-08-13 | (blank) | (blank) | 1150
[9 empty] | PSA-2204PA-BLTNMNAT-CHARLIE |  |  | PSA-1203PA-EDPRMNPI-CHARLIE | 2024-09-12 | (blank) | (blank) | 2905
[10 empty] | 40275 |  | PSA-1301PA-EAGNMN82-CHARLIE | 2024-08-27 | (blank) | (blank) | 1924
[11 empty] | 2024-09-19 | PSA-1303PA-EDPRMNPI-CHARLIE | 2024-09-03 | (blank) | (blank) | 3982
[9 empty] | PSA-2204PA-EAGNMN82-CHARLIE |  |  | PSA-1304PA-EAGNMN82-CHARLIE | 2024-07-03 | (blank) | (blank) | 21103
[10 empty] | 31500 |  | PSA-1401PA-EAGNMN82-CHARLIE | 2024-08-26 | (blank) | (blank) | 2159
[11 empty] | 2024-09-16 | PSA-1402PA-EDPRMNPI-CHARLIE | 2024-09-03 | (blank) | (blank) | 3602
[9 empty] | PSA-2803PA-EAGNMN82-CHARLIE |  |  | PSA-1403PA-EAGNMN82-CHARLIE | 2024-08-19 | 2024-09-25 | ECD 9/30 | 6271
[10 empty] | 12618 |  | PSA-1405PA-EAGNMN82-CHARLIE | 2024-07-03 | (blank) | (blank) | 3689
[11 empty] | 2024-09-23 | PSA-1406PA-EAGNMN82-CHARLIE | 2024-08-22 | (blank) | (blank) | 1835
[9 empty] | PSA-3162PA-BLTNMNAT-CHARLIE |  |  | PSA-1502PA-EAGNMN82-CHARLIE | 2024-08-26 | (blank) | (blank) | 4558
[10 empty] | 23752 |  | PSA-1506PA-EAGNMN82-CHARLIE | 2024-07-08 | (blank) | (blank) | 14359
[11 empty] | 2024-09-23 | PSA-1507PA-EAGNMN82-CHARLIE | 2024-09-16 | (blank) | (blank) | 6168
[12 empty] | PSA-1508PA-EAGNMN82-CHARLIE | 2024-09-16 | (blank) | (blank) | 5
[12 empty] | PSA-1509PA-EAGNMN82-CHARLIE | 2024-07-04 | (blank) | (blank) | 22720
[12 empty] | PSA-1601PA-EAGNMN82-CHARLIE | 2024-09-05 | (blank) | (blank) | 1178
[12 empty] | PSA-1603PA-EAGNMN82-CHARLIE | 2024-09-09 | (blank) | (blank) | 8491
[12 empty] | PSA-1608PA-EAGNMN82-CHARLIE | 2024-09-11 | (blank) | (blank) | 33074
[12 empty] | PSA-1702PA-EAGNMN82-CHARLIE | 2024-08-27 | (blank) | (blank) | 25098
[12 empty] | PSA-1705PA-EAGNMN82-CHARLIE | 2024-08-22 | (blank) | (blank) | 3873
[12 empty] | PSA-1801PA-EAGNMN82-CHARLIE | 2024-08-22 | (blank) | (blank) | 4164
[12 empty] | PSA-2102PA-EAGNMN82-CHARLIE | 2024-07-18 | 2024-09-26 | (blank) | 2252
[12 empty] | PSA-2106PA-EAGNMN82-CHARLIE | 2024-08-27 | (blank) | (blank) | 3899
[12 empty] | PSA-2107PA-EAGNMN82-CHARLIE | 2024-09-12 | (blank) | (blank) | 5687
[12 empty] | PSA-2132PA-EDPRMNPI-CHARLIE | 2024-08-02 | (blank) | (blank) | 20821
[12 empty] | PSA-2201PA-EDPRMNPI-CHARLIE | 2024-08-23 | (blank) | (blank) | 2349
[12 empty] | PSA-2202PA-EDPRMNPI-CHARLIE | 2024-09-05 | (blank) | (blank) | 2133
[12 empty] | PSA-2203PA-BLTNMNAT-CHARLIE | 2024-05-01 | 2024-08-15 | 2024-08-27 | 35863
[12 empty] | PSA-2203PA-EDPRMNPI-CHARLIE | 2024-08-23 | (blank) | (blank) | 2419
[12 empty] | PSA-2205PA-EAGNMN82-CHARLIE | 2024-08-20 | (blank) | (blank) | 1395
[12 empty] | PSA-2206PA-BLTNMNAT-CHARLIE | 2024-05-08 | (blank) | (blank) | 30669
[12 empty] | PSA-2207PA-BLTNMNAT-CHARLIE | 2024-05-01 | 2024-09-10 | 2024-09-12 | 4328
[12 empty] | PSA-2311PA-EAGNMN82-CHARLIE | 2024-07-16 | (blank) | (blank) | 4171
[12 empty] | PSA-2312PA-EAGNMN82-CHARLIE | 2024-08-22 | 2024-09-12 | (blank) | 5463
[12 empty] | PSA-2402PA-EDPRMNPI-CHARLIE | 2024-09-16 | (blank) | (blank) | 37019
[12 empty] | PSA-2502PA-EAGNMN82-CHARLIE | 2024-07-09 | (blank) | (blank) | 33856
[12 empty] | PSA-2602PA-BLTNMNAT-CHARLIE | 2024-03-14 | (blank) | (blank) | 52909
[12 empty] | PSA-2604PA-BLTNMNAT-CHARLIE | 2024-03-08 | (blank) | (blank) | 28826
[12 empty] | PSA-2604PA-EAGNMN82-CHARLIE | 2024-07-16 | (blank) | (blank) | 44453
[12 empty] | PSA-2805PA-EAGNMN82-CHARLIE | 2024-08-22 | (blank) | (blank) | 11348
[12 empty] | PSA-2903PA-EAGNMN82-CHARLIE | 2024-04-26 | 2024-06-28 | 2024-07-26 | 7102
[12 empty] | PSA-3121PA-BLTNMNAT-CHARLIE | 2024-07-01 | (blank) | (blank) | 18391
[12 empty] | PSA-3141PA-BLTNMNAT-CHARLIE | 2024-09-11 | (blank) | (blank) | 3167
[12 empty] | PSA-3143PA-BLTNMNAT-CHARLIE | 2024-06-06 | (blank) | (blank) | 38796
[12 empty] | PSA-3144PA-BLTNMNAT-CHARLIE | 2024-06-06 | 2024-09-04 | Pend Layout | 18523
[12 empty] | PSA-3145PA-BLTNMNAT-CHARLIE | 2024-06-12 | 2024-09-04 | Pend Layout | 19965
[12 empty] | PSA-3151PA-BLTNMNAT-CHARLIE | 2024-09-04 | (blank) | (blank) | 210
[12 empty] | PSA-3163PA-BLTNMNAT-CHARLIE | 2024-08-30 | (blank) | (blank) | 3358
[12 empty] | PSA-3171PA-BLTNMNAT-CHARLIE | 2024-09-05 | (blank) | (blank) | 4749
[12 empty] | PSA-3191PA-BLTNMNAT-CHARLIE | 2024-08-23 | (blank) | (blank) | 24070
[12 empty] | PSA-3192PA-BLTNMNAT-CHARLIE | 2024-07-03 | 2024-09-18 | (blank) | 18111
[12 empty] | PSA-3201PA-BLTNMNAT-CHARLIE | 2024-06-20 | 2024-08-14 | 2024-08-22 | 32853
[12 empty] | PSA-3201PA-EDPRMNPI-CHARLIE | 2024-07-26 | (blank) | (blank) | 29964
[12 empty] | PSA-3203PA-EDPRMNPI-CHARLIE | 2024-08-16 | (blank) | (blank) | 13118
[12 empty] | PSA-3204PA-EDPRMNPI-CHARLIE | 2024-08-13 | (blank) | (blank) | 20291
[12 empty] | PSA-3211PA-BLTNMNAT-CHARLIE | 2024-07-09 | (blank) | (blank) | (blank)
[12 empty] | PSA-3221PA-BLTNMNAT-CHARLIE | 2024-06-26 | (blank) | (blank) | 18472
[12 empty] | PSA-3223PA-BLTNMNAT-CHARLIE | 2024-06-26 | (blank) | (blank) | 26800
[12 empty] | PSA-3303PA-EDPRMNPI-CHARLIE | 2024-07-30 | (blank) | (blank) | 24392
[12 empty] | PSA-3306PA-EDPRMNPI-CHARLIE | 2024-08-21 | (blank) | (blank) | 7373
[12 empty] | PSA-3404PA-EDPRMNPI-CHARLIE | 2024-08-16 | (blank) | (blank) | 14797
[12 empty] | PSA-3405PA-EDPRMNPI-CHARLIE | 2024-08-26 | 2024-09-20 | 2024-09-26 | 25976
[12 empty] | PSA-3503PA-BLTNMNAT-CHARLIE | 2024-08-09 | (blank) | (blank) | (blank)
[12 empty] | PSA-3601PA-EDPRMNPI-CHARLIE | 2024-08-26 | (blank) | (blank) | 17251
[12 empty] | PSA-3602PA-EDPRMNPI-CHARLIE | 2024-08-05 | (blank) | (blank) | 17065
[12 empty] | PSA-3606PA-EDPRMNPI-CHARLIE | 2024-08-29 | (blank) | (blank) | 26878
[12 empty] | PSA-3802PA-EDPRMNPI-CHARLIE | 2024-08-20 | (blank) | (blank) | 47305
[12 empty] | PSA-3806PA-EDPRMNPI-CHARLIE | 2024-08-30 | (blank) | (blank) | 38677
[12 empty] | PSA-3902PA-EDPRMNPI-CHARLIE | 2024-08-12 | (blank) | (blank) | 3337
[12 empty] | PSA-3903PA-EDPRMNPI-CHARLIE | 2024-09-06 | (blank) | (blank) | 44790
[12 empty] | PSA-3906PA-EDPRMNPI-CHARLIE | 2024-08-27 | (blank) | (blank) | 801
[12 empty] | PSA-4102PA-BLTNMNAT-CHARLIE | 2024-04-11 | 2024-09-23 | 2024-09-24 | 52302
[12 empty] | PSA-4111PA-BLTNMNAT-CHARLIE | 2024-06-14 | (blank) | (blank) | 12344
[12 empty] | PSA-4202PA-BLTNMNAT-CHARLIE | 2024-08-30 | (blank) | (blank) | 1463
[12 empty] | PSA-4506PA-BLTNMNAT-CHARLIE | 2024-08-28 | (blank) | (blank) | 6696
[12 empty] | PSA-4705PA-BRVLMNYF-CHARLIE | 2024-07-11 | 2024-09-04 | (blank) | 29027
[12 empty] | PSA-4801PA-BLTNMNAT-CHARLIE | 2024-08-19 | (blank) | (blank) | 13693
[12 empty] | PSA-4802PA-BLTNMNAT-CHARLIE | 2024-08-09 | (blank) | (blank) | 26123
[12 empty] | PSA-4803PA-BLTNMNAT-CHARLIE | 2024-08-16 | (blank) | (blank) | 4310
[12 empty] | PSA-4808PA-BLTNMNAT-CHARLIE | 2024-08-30 | (blank) | (blank) | 13103
[12 empty] | PSA-4901PA-BLTNMNAT-CHARLIE | 2024-07-25 | (blank) | (blank) | 24187